## Summary & Notes
The Facility Status Update describes the current status of facilities that were applied for, are under construction or have been placed on-stream since the 2022 Annual Plan was issued on December 15, 2022 and maintains a record of the facilities for two years prior to the current year. Periodic updates are being provided based on the level of activity occurring with respect to facilities. Facilities with (AP) after the project name refer to facilities in the ATCO Pipelines footprint.
| Summary: | 2021 | 2022 | 2023 | 2024+ | 2025 | 2026+
| Total Costs by In-Service Year * | 1246.2 | 3247.5 | 1762.2 | 443.8 | 0 | 1395
Forecast Costs For NGTL projects greater than $25 million, the estimate type for the forecasted costs have been provided. The typical expected accuracy for the various estimate types are shown in the table below. These accuracy ranges are for typical TC Energy projects with established technological complexity. It should be noted that for non-typical TC Energy projects the accuracy range could widen towards the upper limit of the AACE ranges for a class of estimate (i.e. depending on area knowledge, technological complexity, level of expertise, and certainty of facility scope). If a cost estimate for an NGTL project is based on the wider accuracy range, the estimate range will be provided in the Variance Explanation column. Forecasted costs reflect the dollar value, economic conditions, and estimation procedures at the time the estimates were completed.
Total Costs by In-Service Total Costs by In-Service Year are a summation of the last provided costs of all NGTL capacity capital projects with expected or realized in-service dates within a calendar year. Costs for non NGTL capacity capital projects, such as ATCO Pipelines, CIAC, decommissioning or abandonment projects, are excluded. These annual summations of costs will not match other regulatory filings with different costs bases. Variance Explanation Variance explanations are provided for all NGTL capacity capital projects with EAC costs equal to or greater than $25 million with a variance greater than 10% between the EAC and applied-for costs.
North Montney Project Variance Application NEB Approval Order Received May 23, 2018. All Facilites in-service. 2021 NGTL System Expansion Project GPML Loop No.2 (Colt Section) in-service March 24, 2023, acheiving 100% Project capacity. GPML Loop No. 2 (Simonette River) target in-service Nov 2023. Disclaimer The information provided in this document has been prepared to the best of management’s ability. TC does not represent or warrant that the information contained herein is accurate and complete in all respects or is fit for any purpose. Any of use of the information in its current or any manipulated form is the sole responsibility of the user. TC Energy is not responsible for any changes made to downloaded copies and/or results in data compiled, assumptions, and actions resulting from those changes. NGTL can only support use of the official PDF version as posted on TC Customer Express.

## Facilities Update
Report Updates | Facility Category | Applied-for Facilities | Description | Target In-Service Date | Status | Date of Status | References * | Forecast Cost * ($Millions) | 2021 | 2022 | 2023 | 2024 | 2025 | 2026+ | Variance Explanation
| Meter Station & Lateral Abandonment | 2017 Meter Stations and Laterals Abandonment Program | Meter Stations w/Laterals Acadia East Acadia North Acadia Valley Bear Canyon West Big Bend East Blueberry Hill Blue Jay Donatville Hines Creek Hines Creek West Last Lake Lawrence Lake Manir Mills Tangent East Stand-Alone Meters Elinor Lake East Mega River Mega River No. 2 Rod Lake Rod Lake Sales Rossbear Lake Snowfall Creek Squirrel Mountain Owl Lake South Owl Lake South No. 2 Owl Lake South No. 3 Stand-Alone Laterals Alderson Lateral Kaybob South Lateral McNeill X-Over | Q1 2021 | Complete | 2021-03-01 | Jun 29, 2017 - TTFP Notification Aug 21, 2017 - NEB Application Filed 1 | 16.4
| Meter Station & Lateral Abandonment | 2018 Meter Station and Laterals Abandonment Program | Meter Stations w/Laterals AECO A AECO I Andrew Chard Donnelly Esther Border Meadow Creek Mons Lake Mons Lake East Princess South Retlaw Rock Island Lake Rumsey West Saddle Lake West West Viking Stand-Alone Meter Stations Rock Island Lake South No. 2 Stand-Alone Laterals Boundary Lake South Flat Lake Lateral Ext. Marten Hills White Earth Creek | Q3 2022 | Complete | 2022-09-01 | Aug 16, 2018 - TTFP Notification Sept 28, 2018 - NEB Application filed 2 | 17.9 18.1
| Pipeline & Associated Decommissioning | 2018 Pipelines and Associated Facilities Decommissioning Program | Pipeline Laterals Baxter Lake Calling Lake East Calling Lake South East Lat Loop Edgerton Flat Lake Lat Loop Flat Lake Lat Ext Judy Creek Sales North Lat Ext Loop Wainwright Wapiti Zama Lake Associated Facilities Edgerton Rec Judy Creek Sales Zama Lake No. 1 Rec Zama Lake No. 2 Rec Wapiti Rec PTI 360m Cross-over | Q4 2022 | Complete | 2023-03-03 | . | 14.3 28 - Class 5
| Meter Station & Lateral Abandonment | 2021 Meter Station and Laterals Abandonment Program | Pipeline Laterals & Meters 12 - 151.2 km 9 Receipt 1 Delivery Stand-Alone Meters 3 Receipt 1 Delivery | Q2 2024 | Approved | 2023-03-31 | Mar 7, 2022 - TTFP Notification May 3, 2022 - CER Application Filed 43 | 13
| Meter Station & Lateral Decommisioning | 2021 Meter Station and Laterals Decommisioning Program | Pipeline Laterals & Meters 5 - 120.7 km 2 Receipt 1 Delivery | Q4 2023 | Approved | 2022-12-21 | Jun 13, 2022 - TTFP Notification Aug 22, 2022 - CER Application Filed 44 | 7.1
| NGTL System Expansion | 2021 NGTL System Expansion Project: Beiseker Compressor Station Unit Addition | 30 MW | Apr 2021 - Apr 2022 | In-service | 2021-09-30 | Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 4 Feb 19, 2020 - CER Recommendation 5 Sep 8, 2020 - Facility Status Class Estimate Update Jun 7, 2022 - Facility Status Update (Estimate at Complete) | 120 - ROM 116 - Class 5 164 - Class 3 150 - EAC | 150 | [5 empty] | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Didsbury Compressor Station & Coolers | 30 MW | Apr 2021 - Apr 2022 | In-service | 2021-09-22 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 4 Feb 19, 2020 - CER Recommendation 5 Sep 8, 2020 - Facility Status Class Estimate Update Jun 7, 2022 - Facility Status Update (Estimate at Complete) | 166 - ROM 116 - Class 5 153 - Class 3 151- EAC | 151 | [5 empty] | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Brewster) | 49 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2022-04-29 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 4 Feb 19, 2020 - CER Recommendation 5 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Nov 15, 2022 - Facility Status Update (Estimate at Complete) | 270 - ROM 287 - Class 5 315 - Class 3 378 - Class 3 393 - EAC |  | 393 |  |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Dismal Creek) | 32 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2022-04-14 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 4 Feb 19, 2020 - CER Recommendation 5 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Nov 15, 2022 - Facility Status Update (Estimate at Complete) | 156 - ROM 179 - Class 5 285 - Class 3 375 - Class 3 298 - EAC |  | 298 |  |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Robb) | 42 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2022-06-02 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 4 Feb 19, 2020 - CER Recommendation 5 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Nov 15, 2022 - Facility Status Update (Estimate at Complete) | 232 - ROM 232 - Class 5 274 - Class 3 378 - Class 3 402 - EAC |  | 402 |  |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Colt Section) | 14 km NPS 48 | Apr 2021 - Apr 2022 | In-service | 2023-03-24 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 4 Feb 19, 2020 - CER Recommendation 5 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Sept 12, 2023 - Facility Status Update (Estimate at Complete) | 73 - ROM 80 - Class 5 117 - Class 3 134 - Class 3 220 - EAC |  |  | 220 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Deep Valley) | 69 km NPS 48 | Apr 2021 - Apr 2022 | Under Construction | 2021-01-29 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 4 Feb 19, 2020 - CER Recommendation 5 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate | 332 - ROM 377 - Class 5 530 - Class 3 665 - Class 3 |  | 665 |  |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Karr) | 57 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2022-04-01 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 4 Feb 19, 2020 - CER Recommendation 5 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Nov 15, 2022 - Facility Status Update (Estimate at Complete) | 298 - ROM 327 - Class 5 409 - Class 3 454 - Class 3 463 - EAC |  | 463 |  |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.3 (Elmworth Section 2 & 3) | 44 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2021-11-10 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 4 Feb 19, 2020 - CER Recommendation 5 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Nov 15, 2022 - Facility Status Update (Estimate at Complete) | 283 - ROM 283 - Class 5 328 - Class 3 357 - Class 3 334 - EAC | 334 | [5 empty] | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.4 (Valhalla) | 36 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2021-11-25 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 4 Feb 19, 2020 - CER Recommendation 5 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Nov 15, 2022 - Facility Status Update (Estimate at Complete) | 152 - ROM 187 - Class 5 235 - Class 3 228 - Class 3 195 - EAC | 195 | [5 empty] | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: January Creek Control Valve Addition | Control Valve Addition | Apr 2021 - Apr 2022 | In-service | 2021-04-12 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 4 Feb 19, 2020 – CER Recommendation 5 Sep 8, 2020 - Facility Status Class Estimate Update | 5 5 4 - Class 3 | 4
| NGTL System Expansion | 2021 NGTL System Expansion Project: Nordegg Compressor Station Unit Addition | 30 MW | Apr 2021 - Apr 2022 | In-service | 2021-08-18 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 4 Feb 19, 2020 – CER Recommendation 5 Sep 8, 2020 - Facility Status Class Estimate Update Nov 18, 2021 - Facility Status Update (Estimate at Complete) | 145 - ROM 119 - Class 5 149 - Class 3 143 - EAC | 143
| Meter Station & Lateral Abandonment | 2022 Meter Station and Laterals Abandonment Program | Pipeline Laterals & Meters 23 - 167.5 km 22 Receipt 1 Delivery 7 Producer Tie-ins | Q4 2024 | Applied for | 2023-05-23 | Apr 6, 2023 - TTFP Facility Notification May 23, 2023 - CER Application Filed 48 | 23
| Meter Station & Lateral Decommisioning | 2022 Meter Station and Laterals Decommissioning Program | Pipeline Laterals & Meters 23 - 310.34 km 2 Receipt | Q4 2024 | Proposed | 2023-06-19 | Jun 19, 2023 - TTFP Notification | 18.6
| Compressor Station Unit Addition | Berland River Compressor Station Unit and Coolers Addition | 30 MW | 2026-04-01 | Applied for | 2023-08-01 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix Sep 7, 2022 - TTFP Facilites Update Aug 1, 2023 - CER Application Filed49 | 166 - ROM 254 - Class 5 255 - Class 4 | [5 empty] | 255
| Receipt Meter Station | Chambers Creek Receipt Meter Station | 860U-4 | 2022-04-01 | In-Service | 2022-03-31 | May 25, 2021 - TTFP Notification Jun 16, 2021 - CER Application Filed 33 | 4 |  | 4
| 2021 Clearwater Unit Addition | Clearwater Compressor Station Unit Addition & Coolers | 30 MW | 2021-11-01 | In-Service | 2021-11-01 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jul 20, 2018 - TTFP Update Sep 26, 2018 - CER Application Filed 6 Feb 8, 2022 - Facility Status Update (Estimate at Complete) | 145 - ROM 128 - Class 5 153 - EAC | 153 | [5 empty] | Increased costs related to constructability, site complexity and elevated prime contractor costs due to unfavorable market conditions
| Compressor Station Upgrades | Cloverbar Compressor Station Upgrades (AP) | Station Upgrades | 2026-2028 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2022-12-13 | Dec 13, 2022 - TTFP Presentation, 2022 Annual Plan x | 10 - ROM
| Delivery Meter Station Replacement | Cold Lake Border Sales Meter Station Replacement | 1010U Ultrasonic Meter | 2021-11-01 | In-Service | 2021-07-07 | Aug 9, 2019 - TTFP Notification Aug 23, 2019 - NEB Application Filed 7 | 3.2 | 3.2
| Edson Mainline Expansion | Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Alford Creek) | 45 km NPS 48 | 2022-11-01 | In-Service | 2022-10-31 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 3, 2019 - NEB Application Filed 8 June 18, 2021 - CER Approval 34 Jan 17, 2023 - Facility Status Update (Estimate at Complete) | 269 - ROM 269 - Class 5 332 - EAC |  | 332 |  |  |  |  | Elevated costs due to constrained supply chain and labor market conditions
| Edson Mainline Expansion | Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Elk River) | 40 km NPS 48 | 2022-11-01 | In-Service | 2022-10-07 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 3, 2019 - NEB Application Filed 8 June 18, 2021 - CER Approval 34 Jan 17, 2023 - Facility Status Update (Estimate at Complete) | 240 - ROM 240 - Class 5 333 - EAC |  | 333 |  |  |  |  | Elevated costs due to constrained supply chain and labor market conditions
| Compressor Station | Emerson Creek Compressor Station | 2-30 MW Units | 2024-04-01 | Under Construction | 2022-07-11 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii June 1, 2021 - CER Application Filed 32 Dec 22, 2021- CER Approval40 | 257 - ROM 278 - Class 5 |  |  |  | 278
| Lateral Loop | Gleichen Transmission Looping (AP) Cluny Transmission Looping (AP) | 2.7 km NPS 3 2.3 km NPS 3 | 2022 | In-Service | Apr 23, 2022 Oct 26, 2022 | Jun 16, 2020 – GRA Application Filed 20 Mar 1, 2021 - GRA Application Approved 28 | 2.7
| Pipe Looping | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) | 33km NPS 48 | 2026-04-01 | Applied for | 2023-08-01 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix Sep 7, 2022 - TTFP Facilites Update Aug 1, 2023 - CER Application Filed49 | 281 - ROM 342 - Class 5 323 - Class 4 | [5 empty] | 323
In-service | Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition | Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Groundbirch Mainline Loop (Saturn Section) | 24 km NPS 42 | 2023-12-01 | In-service | 2023-12-01 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Nov 5, 2020 - CER Application Filed 23 May, 13, 2021 - CER Approval 31 | 143 - ROM 140 - Class 5 |  |  | 140
| Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition | Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Saddle Hills Compressor Station Unit Addition | 30 MW | 2024-04-01 | Under Construction | 2023-03-15 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Nov 5, 2020 - CER Application Filed 23 May, 13, 2021 - CER Approval 31 | 159 - ROM 151 - Class 5 |  |  |  | 151
| Pipe Looping | Groundbirch Mainline Loop (BC Section) | 25 km NPS 42 | 2026-2028 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2022-12-13 | Dec 13, 2022 - TTFP Presentation, 2022 Annual Plan x | 175 - ROM | [5 empty] | 175
| Groundbirch Mainline Loop | Groundbirch Mainline Loop (Sunrise Section) | 24 km NPS 42 | 2023-04-01 | In-Service | 2023-04-16 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Oct 3, 2018 - TTFP Facility Update Apr 29, 2019 - NEB Application Filed 9 Sep 12, 2023 - Facility Status Update (Estimate at Complete) | 107 - ROM 155 - ROM 135 - ROM 140 - Class 4 176 - EAC |  |  | 176 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| North Montney Project | Gundy West No. 2 | 880U Ultrasonic Meter | 2021-11-21 | In-Service | 2021-10-25 | Nov 30, 2020 - TTFP Notification Jan 12, 2021 - CER Application Filed 25 | 3.6 | 3.6
| Compressor Station Coolers | Hidden Lake & Hidden Lake North Station Coolers | Coolers | 2023-04-01 | In-service | 2023-03-30 | Dec 7, 2020 - TTFP Notification Jun 22, 2021 - CER Application Filed 35 Dec 10, 2021 - CER Approval 39 Sept 12, 2023 - Facility Status Update (Estimate at Complete) | 45 - ROM 47 - Class 4 53 - EAC |  |  | 53 |  |  |  | Elevated prime contractor costs.
| Compressor Station | Inland Compressor Station (AP) | 15 MW | 2026-2028 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2022-12-13 | Dec 13, 2022 - TTFP Presentation, 2022 Annual Plan x | 115 - ROM
| Pipe Looping | Inland Looping - Phase 2 (AP) | 27km NPS 24 | 2026-2028 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2022-12-13 | Dec 13, 2022 - TTFP Presentation, 2022 Annual Plan x | 110 - ROM
| Pipe Looping | Inland Looping (AP) | 9km NPS 20 | 2025-11-01 | Proposed | 2021-12-06 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix June 21, 2023 - Facility Status Update | 40 - ROM
| Keephills Expansion | Keephills Expansion (AP) | Control Station Meter Station | 2021 | In-Service | 2021-04-22 | Jun 16, 2020 - GRA Application Filed 17 Mar 1, 2021 - GRA Application Approved 28 | 5.8
| Connection Facility | Leismer Ethane Extraction Plant Tie-in | NPS 30 Connection, Valves, Tees | 2023-04-01 | In-Service | 2023-05-01 | Apr 06, 2022 - TTFP Notification Apr 26, 2022 - CER Application Filed42 | 3.2 |  |  | 3.2
| Pipe Looping | Leming Loop | 17 km NPS 20 | Apr 2026 | Proposed | 2022-12-13 | Dec 13, 2022 - TTFP Presentation, 2022 Annual Plan x May 9, 2023 - TTFP Facility Update Presentation | 270 - ROM 107 - Class 5 | [5 empty] | 107
| Pipeline Upgrade | Lethbridge Urban Pipeline Upgrade (AP) | 10.8 km NPS 8 2.4 km NPS 6 Control Station 3 Delivery Stations | Q3 2024 | Under Construction | 2022-12-05 | Aug 7, 2018 - TTFP Notification Jul 30, 2018 - GRA Application Filed 10 Jun 16, 2020 - GRA Application Filed 21 Mar 1, 2021 - GRA Application Approved 28 | 40
| Compressor Station | Mackie Compressor Station | 15 MW | 2026-2028 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2022-12-13 | Dec 13, 2022 - TTFP Presentation, 2022 Annual Plan x | 210 - ROM | [5 empty] | 210
| Receipt Meter Station | Mackie Creek North Receipt Meter Station Expansion | 682U Ultrasonic Meter | 2024-01-01 | Proposed | 2023-06-20 | Jun 20, 2023, - TTFP Notification | 1.1 |  |  |  | 1.1
| Delivery Meter Station | McLeod River Sales Meter Station | 860U Ultrasonic Meter | 2022-10-01 | In-Service | 2022-09-28 | Oct 12, 2021 - TTFP Notification Oct 26, 2021 - CER Application Filed 38 | 4 |  | 4
| Delivery Meter Station | Mildred Lake West Sales Meter Station | 2-1010U Ultrasonic Meter | 2024-04-01 | Approved | 2023-07-07 | Nov 30, 2022 - TTFP Notification Mar 13, 2023 - CER Application Filed 47 | 6.6 |  |  |  | 6.6
| North Corridor Expansion | North Corridor Expansion Project: Hidden Lake North Compressor Station Unit Addition | 30 MW | 2023-04-01 | In-Service | 2023-05-07 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 11 May 5, 2021 - CER Approval 30 Sept 12, 2023 - Facility Status Update (Estimate at Complete) | 138 - ROM 138 - Class 5 195 - EAC |  |  | 195 |  |  |  | Elevated prime contractor costs.
| North Corridor Expansion | North Corridor Expansion Project: North Central Corridor Loop (North Star Section 2) | 24 km NPS 48 | 2023-04-01 | In-Service | 2023-01-19 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 11 May 5, 2021 - CER Approval 30 Apr 11, 2023 - Facility Status Update (Estimate at Complete) | 155 - ROM 155 - Class 5 198 - EAC |  |  | 198 |  |  |  | Issuance of a Stop Work Order by the CER, resulting in unplanned standby and delay with commencement of work.
| North Corridor Expansion | North Corridor Expansion Project: North Central Corridor Loop (Red Earth Section 3) | 32 km NPS 48 | 2023-04-01 | In-Service | 2023-04-11 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 11 May 5, 2021 - CER Approval 30 July 11, 2023 - Facility Status Update (Estimate at Complete) | 205 - ROM 205 - Class 5 289 - EAC |  |  | 289 |  |  |  | Elevated prime contractor costs due to unfavorable market conditions. Issuance of a Stop Work Order by the CER, resulting in unplanned standby and delay with commencement of work.
| North Corridor Expansion | North Corridor Expansion Project: Northwest Mainline Loop No.2 (Bear Canyon North Extension Section) | 25 km NPS 36 | 2023-04-01 | In-service | 2023-03-23 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 11 May 5, 2021 - CER Approval 30 Sept 12, 2023 - Facility Status Update (Estimate at Complete) | 134 - ROM 134 - Class 5 132 - EAC |  |  | 132 |  |  |  | Favourable prime contractor costs due to competitive market conditions for smaller diameter pipelines.
| Pipe Looping | North Lateral Loop | 25 km NPS 30 | 2026-2028 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2022-12-13 | Dec 13, 2022 - TTFP Presentation, 2022 Annual Plan x | 135 - ROM | [5 empty] | 135
| Compressor Station Unit Addition | Oakland Compressor Station Unit Addition | 30 MW | 2026-2028 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2022-12-13 | Dec 13, 2022 - TTFP Presentation, 2022 Annual Plan x | 170 - ROM | [5 empty] | 170
| North Montney Project | Old Alaska No. 2 | 660-2U Ultrasonic Meter | 2021-11-21 | In-Service | 2021-10-25 | Nov 30, 2020 - TTFP Notification Jan 14, 2021 - CER Application Filed 26 | 3.4 | 3.4
| Yellowhead Mainline Expansion | Peers Compressor Station Unit Addition (AP) | 5-10 MW | 2027 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2023-05-09 | May 9, 2023 - TTFP Facility Update Presentation | 103 - ROM
| Interconnect | Pioneer Interconnect | Interconnect | 2021-08-01 | In-Service | 2021-11-05 | Feb 9, 2021 - TTFP Notification Sep 17, 2021 - Streamlining Order Notification | 2 | 2
| Acquisition | Pioneer Pipeline Asset Purchase (AP) | 101 km NPS 20 | 2021 | In-Service | 2021-06-30 | Oct 2, 2020 - TTFP Presentation Oct 9, 2020 - AUC Application Filed 24 Jan 15, 2021 - NGTL CER Application Filed 27 Jun 15, 2021 - AUC Approval 36 Aug 9, 2022 - Facility Status Update (Estimate at Complete) | 276 266 198 193 - EAC
| Acquisition | Pioneer South Pipeline Acquisition | 30 km NPS 20 | 2021-10-01 | In-Service | 2022-02-25 | Jan 15, 2021 - CER Application Filed 27 Dec 22, 2021 - CER Approval 41 Aug 9, 2022 - Facility Status Update (Estimate at Complete) | 68 64 - EAC |  | 64
| Control Valve | Princess Control Valve Addition | Control Valve Addition | 2026-2028 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2022-12-13 | Dec 13, 2022 - TTFP Presentation, 2022 Annual Plan x | 20 - ROM | [5 empty] | 20
| Lateral Loop | Saddle Lake Lateral Loop (Cold Lake Section) | 20 km NPS 20 | 2021-11-01 | In-Service | 2021-06-29 | Feb 13, 2018 - TTFP Facility Update Aug 23, 2019 - NEB Application Filed 7 Oct 6,2021 - Appendix 2 Update (Estimate at Complete) | 42 - ROM 65 - Class 4 66 - EAC | 66
| Delivery Meter Station | Scotford PDH Delivery Meter Station (AP) | 860T Turbine Meter | 2021-07-13 | In-Service | 2021-03-26 | May 1, 2018 - TTFP Notification | 2.6 (Includes $1.7M CIAC)
| Delivery Meter Station | Smoky River South Sales Meter Station | NPS 3 Positive Displacement Meter | 2022-09-01 | In-Service | 2023-07-05 | May 20, 2021 - TTFP Notification Aug 26, 2021 - NEB Application Filed 37 | 4.5 |  | 4.5
| Pipeline Acquisition | South Airdrie Lateral - Pipeline Acquisition (AP) | 8.7 km NPS 6 | 2021 | In-Service | 2021-07-05 | Aug 7, 2018 - TTFP Notification Jul 30, 2018 - GRA Application Filed 14 Jun 16, 2020 - GRA Application Filed 18 | 1.9 1.4
Target In-Service Date | Installation (AP) | Spruce Grove and Stony Plain UPU – Installation (AP) | 5.4 km NPS 8 3 Delivery Stations | Q1 2024 | Approved | 2021-03-01 | Jun 16, 2020 - GRA Application Filed 18 Mar 1,2021 - GRA Application Approved 28 | 13.2
| Pipeline Replacement | Urban Pipeline Replacement Project: Edmonton UPR – NE Connector (AP) | Control Station | 2024 | Approved |  | Oct 30, 2014 - TTFP Presentation Dec 4, 2018 – AUC Project Update Filed 15 Jun 16, 2020 - AUC Project Update Filed 19 | 11
| North Montney Project | Variance Application Meters Blair Creek Gundy Kobes Altares Aitken Creek Interconnect | 2-16104U Ultrasonic 2-1284U Ultrasonic 2-1064U Ultrasonic 2-1064U Ultrasonic 2-2416U Ultrasonic | Apr 2020 Sep 2019 Apr 2021 Sep 2019 Q3 2021 | ISD May 19, 2020 ISD Jan 31, 2020 ISD Feb 26, 2021 ISD Jan 31, 2020 ISD Jun 25, 2021 | 2021-11-18 | Variance Application 13 Nov 18, 2021 - Facility Status Update (Estimate at Complete) | 39 - Class 4 38 - EAC | 38
| West Path Delivery 2022 | West Path Delivery 2022 ABC Border Meter Station Expansion | 5 - NPS 20U Ultrasonic Meters | 2022-11-01 | In-Service | 2022-06-10 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Jun 1, 2020 - NEB Application Filed 16 April 30, 2021 - Approval 29 | 8 |  | 8
| West Path Delivery 2022 | West Path Delivery 2022 Edson Mainline No. 4 (Raven River) | 18 km NPS 48 | 2022-11-01 | In-service | 2022-10-31 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Jun 1, 2020 - NEB Application Filed 16 April 30, 2021 - Approval 29 Mar 13, 2023 - Facility Status Update (Estimate at Complete) | 128 - ROM 141 - EAC |  | 141 |  |  |  |  | Elevated costs due to construction cost increases
| West Path Delivery 2022 | West Path Delivery 2022 WAML Loop No. 2 (Alberta British Columbia) | 6 km NPS 48 | 2022-11-01 | In-service | 2022-11-24 | Jan 21, 2020 - TTFP 2019 Annual Plan Update vii Jun 1, 2020 - NEB Application Filed 16 April 30, 2021 - Approval 29 Apr 11, 2023 - Facility Status Update (Estimate at Complete) | 57 - ROM 136 - EAC |  | 136 |  |  |  |  | Elevated costs as a result of significant delays due to wildlife zones and terrain complexity. Elevated prime contractor costs due to unfavorable market conditions.
| West Path Delivery 2023 | West Path Delivery 2023 WAML Loop No. 2 (Longview) | 9 km NPS 48 | 2023-11-01 | In-service | 2023-10-19 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 22 Dec 1, 2022 - CER Approval 45 | 65 - ROM 75 - Class 5 |  |  | 75
| West Path Delivery 2023 | West Path Delivery 2023 WAML Loop No. 2 (Lundbreck) | 7 km NPS 48 | 2023-11-01 | In-service | 2023-10-27 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 22 Dec 1, 2022 - CER Approval 45 | 83 - ROM 72 - Class 5 |  |  | 72
| West Path Delivery 2023 | West Path Delivery 2023 WAML Loop No. 2 (Turner Valley) | 24 km NPS 48 | 2023-11-01 | In-service | 2023-11-01 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 22 Dec 1, 2022 - CER Approval 45 | 209 - ROM 209 - Class 5 |  |  | 209
| Delivery Meter Station | Willow Valley Interconnect Project | 2-1610U Ultrasonic Meter | 2024-04-24 | Approved | 2023-05-17 | Jan 5, 2023 - TTFP Notification Jan 18, 2023 - CER Application Filed 46 | 7.1 |  |  |  | 7.1
| Yellowhead Mainline Expansion | Yellowhead Mainline (AP) | 200 km NPS 30-42 | 2027 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2023-05-09 | May 9, 2023 - TTFP Facility Update Presentation | 1,024 - ROM

## References
References
Annual Plans
i. | NGTL 2013 Annual Plan
ii. | NGTL 2014 Annual Plan
iii. | NGTL 2015 Annual Plan
iv. | NGTL 2016 Annual Plan
v. | NGTL 2017 Annual Plan
vi. | NGTL 2018 Annual Plan
vii. | NGTL 2019 Annual Plan
viii. | NGTL 2020 Annual Plan
ix. | NGTL 2021 Annual Plan
x. | NGTL 2022 Annual Plan
1 | Application for 2017 Meter Station and Associated Lateral Abandonment
2 | 2018 Meter Stations and Laterals Abandonment Program
3 | 2018 Pipeline Decommissioning Program
4 | 2021 NGTL System Expansion Project
5 | Canada Energy Regulator Report for the 2021 NGTL System Expansion Project
6 | Clearwater Compressor Station C7 Unit Addition
7 | Saddle Lake Lateral Loop (Cold Lake Section) Project
8 | Application for the Construction of Edson Mainline Expansion Project
9 | Application for the Construction of Groundbirch Mainline Loop (Sunrise Section)
10 | GRA Application Filed
11 | Application for the Construction of North Corridor Expansion Project
12 | Application for North Montney Project
13 | North Montney Mainlne Project - Application for Variance
14 | Jul 30, 2018 GRA Application Filed
15 | Dec 4, 2018 – AUC Project Update Filed
16 | NGTL West Path Delivery 2022 CER
17 | GRA Application Filed
18 | GRA Application Filed
19 | (GRA) AUC Project Update Filed
20 | Gleichen-Cluny GRA Filed
21 | GRA Application Filed
22 | NGTL West Path Delivery 2023 CER
23 | NGTL GBML Loop (Saturn Section) & Saddle Hills CS C4 Unit Addition
24 | ATCO Pioneer AUC Application
25 | Gundy West No. 2 Receipt Meter Station
26 | Old Alaska No. 2 Receipt Meter Station
27 | Canada Energy Regulator - REGDOCS - C10955 NOVA Gas Transmission Ltd. - Pioneer South Pipeline Acquisition (cer-rec.gc.ca)
28 | March 1, 2021 - GRA Application Approved
29 | April 30, 2021 - West Path Delivery Project
30 | North Corridor Expansion - GIC Approval
31 | GBML (Saturn) and Saddle Hills UA Application
32 | Emerson Creek Compressor Station
33 | Application for the construction of Chambers Creek Receipt Meter Station
34 | Edson Mainline Expansion CER Approval
35 | Hidden Lake and Hidden Lake North Cooler Additions Application
36 | Pioneer (AP) AUC Approval
37 | Smoky River South Sales Meter Station Application
38 | McLeod River Sales Meter Station Application
39 | Hidden Lake and Hidden Lake North Cooler Additions CER Approval
40 | Emerson Creek Compressor Station Approval
41 | Pioneer South Pipeline Acquisition CER Approval
42 | Leismer Ethane Extraction Plant Tie-in
43 | 2021 Meter Station and Laterals Abandonment Program
44 | 2021 Meter Station and Laterals Decommissioning Program
45 | West Path Delivery 2023 Project CER Approval
46 | Willow Valley Interconnect Project
47 | Mildred Lake West Sales Meter Station Application
48 | 2022 Meter Stations and Laterals Abandonment Program
49 | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) and Berland River CS C3 Unit Addition Application

## Facility Type Analysis (hidden)
Facility Type | Frequency
Abandonment | 0
Clearwater West Expansion | 0
Cogen Delivery Station | 0
Compressor Station | 3
Compressor Station Coolers | 1
Compressor Station Decomissioning | 0
Compressor Station Modifications | 0
Compressor Station Unit Addition | 2
Compressor Station Unit Addition & Coolers | 0
Connection Piping | 0
Control Valve Addition | 0
Crossover | 0
Delivery Meter Station | 4
Edson Mainline Expansion | 2
Expansion & Lateral Loop | 0
Extraction Connections | 0
Forestburg | 0
Grande Prairie Mainline Loop | 0
Groundbirch Mainline Loop | 1
Lateral Expansion | 0
Lateral Loop | 2
Meter Station & Lateral Abandonment | 4
NGTL System Expansion | 12
North Central Corridor Loop | 0
North Corridor Expansion | 4
North Montney Project | 3
North Path Delivery | 0
Northwest Mainline Loop | 0
Peace River Mainline Abandonment | 0
Pembina-Keephills Transmission Project | 0
Pipeline & Associated Decommissioning | 1
Pipeline Acquisition | 1
Pipeline Asset Purchase | 0
Pipeline Decommissioning | 0
Pipeline Replacement | 1
Pipeline Upgrade | 1
Receipt Meter Station | 2
Receipt Meter Station Expansion | 0
Saddle West Expansion | 0
Sales Meter Station | 0
Sales Meter Station Expansion | 0
Sales Meter Station Replacement | 0
Transmission Loop | 0
West Path Delivery 2022 | 3
West Path Delivery 2023 | 2
West Path Delivery Project | 0

## Forecast Costs (hidden)
Applied-for Facilities | Forecast Cost ($Millions)
Hidden Lake & Hidden Lake North Station Coolers
Old Alaska No. 2 | 3.4
#REF!
#REF!
#REF!
#REF!
West Path Delivery 2022 Edson Mainline No. 4 (Raven River) | 128 - ROM 141 - EAC
Groundbirch Mainline Loop (Sunrise Section)
Inland Looping - Phase 2 (AP)
Pioneer Interconnect | 2
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Cold Lake Border Sales Meter Station Replacement | 3.2
#REF!
#REF!
#REF!
Gleichen Transmission Looping (AP) Cluny Transmission Looping (AP) | 2.7
#REF!
#REF!
West Path Delivery 2023 WAML Loop No. 2 (Lundbreck) | 83 - ROM 72 - Class 5
West Path Delivery 2022 WAML Loop No. 2 (Alberta British Columbia) | 57 - ROM 136 - EAC
#REF!
#REF!
#REF!
#REF!
#REF!
Chambers Creek Receipt Meter Station | 4
#REF!
#REF!
#REF!
#REF!
Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Saddle Hills Compressor Station Unit Addition
#REF!
#REF!
#REF!
#REF!
#REF!
#REF! | #REF!
#REF!
#REF!
#REF! | #REF!
#REF!
#REF!
2017 Meter Stations and Laterals Abandonment Program | 16.4
#REF!
#REF!
Emerson Creek Compressor Station
#REF!
#REF!
2018 Meter Station and Laterals Abandonment Program
2018 Pipelines and Associated Facilities Decommissioning Program
2021 NGTL System Expansion Project: Didsbury Compressor Station & Coolers
2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Brewster)
2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Dismal Creek)
2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Robb)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Colt Section)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Deep Valley)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Karr)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.3 (Elmworth Section 2 & 3)
#REF!
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.4 (Valhalla)
2021 NGTL System Expansion Project: January Creek Control Valve Addition
2021 NGTL System Expansion Project: Nordegg Compressor Station Unit Addition
2022 Meter Station and Laterals Abandonment Program | 23
#REF!
#REF!
#REF!
#REF!
Clearwater Compressor Station Unit Addition & Coolers
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Alford Creek)
Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Elk River)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Grande Prairie Mainline Loop No. 4 (Valhalla North Section)
Groundbirch Mainline Loop (BC Section)
Gundy West No. 2 | 3.6
#REF!
#REF!
Keephills Expansion (AP) | 5.8
#REF!
McLeod River Sales Meter Station | 4
#REF!
#REF!
#REF!
#REF!
#REF!
Mildred Lake West Sales Meter Station | 6.6
North Corridor Expansion Project: Hidden Lake North Compressor Station Unit Addition
North Corridor Expansion Project: North Central Corridor Loop (North Star Section 2)
North Corridor Expansion Project: North Central Corridor Loop (Red Earth Section 3)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Pioneer Pipeline Asset Purchase (AP)
Pioneer South Pipeline Acquisition
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Saddle Lake Lateral Loop (Cold Lake Section)
#REF!
#REF!
Scotford PDH Delivery Meter Station (AP)
#REF!
#REF!
Smoky River South Sales Meter Station | 4.5
#REF!
South Airdrie Lateral - Pipeline Acquisition (AP)
Spruce Grove and Stony Plain UPU – Installation (AP)
#REF!
#REF!
#REF!
Urban Pipeline Replacement Project: Edmonton UPR – NE Connector (AP)
Variance Application Meters Blair Creek Gundy Kobes Altares Aitken Creek Interconnect
West Path Delivery 2023 WAML Loop No. 2 (Longview)
#REF!