## Summary & Notes
The Facility Status Update describes the current status of facilities that were applied for, are under construction or have been placed on-stream since the 2023 Annual Plan was issued on February 22, 2024 and maintains a record of the facilities for two years prior to the current year. Periodic updates are being provided based on the level of activity occurring with respect to facilities. Facilities with (AP) after the project name refer to facilities in the ATCO Pipelines footprint.
| Summary: | 2022 | 2023 | 2024 | 2025 | 2026 | 2027+
| Total Costs by In-Service Year * | 3247.5 | 1927.2 | 453 | 0 | 683 | 3445
Forecast Costs There are two methodologies for forecasting costs and for NGTL projects greater than $25 million, the estimate type are identified. For a Class Estimate, the target accuracy for the various estimate types are shown in the table below. These accuracy ranges are for typical TC Energy projects with established technological complexity. It should be noted that for non-typical TC Energy projects the accuracy range could widen towards the upper limit of the AACE ranges for a class of estimate (i.e. depending on area knowledge, technological complexity, level of expertise, and certainty of facility scope). If a cost estimate for an NGTL project is based on the wider accuracy range, the estimate range will be provided in the Variance Explanation column. Forecasted costs reflect the dollar value, economic conditions, and estimation procedures at the time the estimates were completed. For a Parametic Estimate, TC Energy may also baseline cost estimates using a probabilistic assessment driven by the risks and uncertainties associated with the project. Typically, the plausible outcomes are expressed as a P-Value and range between P10-P90. The Value indicates the confidence level of a particular cost estimate and indicates the expected probability that the final cost will be equal-to or less-than the specified estimate value. For example, a 70% confidence level for an estimate value (often noted as a P70) indicates an expected 70% probability that the final result will be less than (more favorable) or equal to the P70 cost estimate.
Total Costs by In-Service Total Costs by In-Service Year are a summation of the last provided costs of all NGTL capacity capital projects with expected or realized in-service dates within a calendar year. Costs for non NGTL capacity capital projects, such as ATCO Pipelines, CIAC, decommissioning or abandonment projects, are excluded. These annual summations of costs will not match other regulatory filings with different costs bases. Variance Explanation Variance explanations are provided for all NGTL capacity capital projects with EAC costs equal to or greater than $25 million with a variance greater than 10% between the EAC and applied-for costs.
2021 NGTL System Expansion Project GPML Loop No.2 (Colt Section) in-service March 24, 2023, acheiving 100% Project capacity. GPML Loop No. 2 (Simonette River) target in-service April 2024. Disclaimer The information provided in this document has been prepared to the best of management’s ability. TC does not represent or warrant that the information contained herein is accurate and complete in all respects or is fit for any purpose. Any of use of the information in its current or any manipulated form is the sole responsibility of the user. TC Energy is not responsible for any changes made to downloaded copies and/or results in data compiled, assumptions, and actions resulting from those changes. NGTL can only support use of the official PDF version as posted on TC Customer Express.

## Facilities Update
Report Updates | Facility Category | Applied-for Facilities | Description | Target In-Service Date | Status | Date of Status | References * | Forecast Cost * ($Millions) | 2022 | 2023 | 2024 | 2025 | 2026 | 2027+ | Variance Explanation
| Meter Station & Lateral Abandonment | 2018 Meter Station and Laterals Abandonment Program | Meter Stations w/Laterals AECO A AECO I Andrew Chard Donnelly Esther Border Meadow Creek Mons Lake Mons Lake East Princess South Retlaw Rock Island Lake Rumsey West Saddle Lake West West Viking Stand-Alone Meter Stations Rock Island Lake South No. 2 Stand-Alone Laterals Boundary Lake South Flat Lake Lateral Ext. Marten Hills White Earth Creek | Q3 2022 | Complete | 2022-09-01 | Aug 16, 2018 - TTFP Notification Sept 28, 2018 - NEB Application filed 1 | 17.9 18.1
| Pipeline & Associated Decommissioning | 2018 Pipelines and Associated Facilities Decommissioning Program | Pipeline Laterals Baxter Lake Calling Lake East Calling Lake South East Lat Loop Edgerton Flat Lake Lat Loop Flat Lake Lat Ext Judy Creek Sales North Lat Ext Loop Wainwright Wapiti Zama Lake Associated Facilities Edgerton Rec Judy Creek Sales Zama Lake No. 1 Rec Zama Lake No. 2 Rec Wapiti Rec PTI 360m Cross-over | Q4 2022 | Complete | 2023-03-03 | Nov 14, 2018 - TTFP Notification Dec 7, 2018 - TTFP Notification Update Dec 18, 2018 - NEB Application Filed 2 | 14.3 28 - Class 5
| Meter Station & Lateral Abandonment | 2021 Meter Station and Laterals Abandonment Program | Pipeline Laterals & Meters 12 - 151.2 km 9 Receipt 1 Delivery Stand-Alone Meters 3 Receipt 1 Delivery | Q1 2025 | Approved | 2023-03-31 | Mar 7, 2022 - TTFP Notification May 3, 2022 - CER Application Filed 33 | 13
In-service Date | Meter Station & Lateral Decommisioning | 2021 Meter Station and Laterals Decommisioning Program | Pipeline Laterals & Meters 5 - 120.7 km 2 Receipt 1 Delivery | Q4 2024 | Approved | 2022-12-21 | Jun 13, 2022 - TTFP Notification Aug 22, 2022 - CER Application Filed 34 | 7.1
| NGTL System Expansion | 2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Brewster) | 49 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2022-04-29 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 3 Feb 19, 2020 - CER Recommendation 4 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Nov 15, 2022 - Facility Status Update (Estimate at Complete) | 270 - ROM 287 - Class 5 315 - Class 3 378 - Class 3 393 - EAC | 393 | [5 empty] | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Dismal Creek) | 32 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2022-04-14 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 3 Feb 19, 2020 - CER Recommendation 4 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Nov 15, 2022 - Facility Status Update (Estimate at Complete) | 156 - ROM 179 - Class 5 285 - Class 3 375 - Class 3 298 - EAC | 298 | [5 empty] | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Robb) | 42 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2022-06-02 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 3 Feb 19, 2020 - CER Recommendation 4 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Nov 15, 2022 - Facility Status Update (Estimate at Complete) | 232 - ROM 232 - Class 5 274 - Class 3 378 - Class 3 402 - EAC | 402 | [5 empty] | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Colt Section) | 14 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2023-03-24 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 3 Feb 19, 2020 - CER Recommendation 4 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Sept 12, 2023 - Facility Status Update (Estimate at Complete) | 73 - ROM 80 - Class 5 117 - Class 3 134 - Class 3 220 - EAC |  | 220 |  |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Deep Valley) | 69 km NPS 48 | Apr 2021 - Apr 2022 | Under Construction | 2021-01-29 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 3 Feb 19, 2020 - CER Recommendation 4 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate | 332 - ROM 377 - Class 5 530 - Class 3 665 - Class 3 | 665 | [5 empty] | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Karr) | 57 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2022-04-01 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 3 Feb 19, 2020 - CER Recommendation 4 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Nov 15, 2022 - Facility Status Update (Estimate at Complete) | 298 - ROM 327 - Class 5 409 - Class 3 454 - Class 3 463 - EAC | 463 | [5 empty] | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
In-service Date | Meter Station & Lateral Abandonment | 2022 Meter Station and Laterals Abandonment Program | Pipeline Laterals & Meters 23 - 167.5 km 22 Receipt 1 Delivery 7 Producer Tie-ins | Q3 2025 | Approved | 2023-12-15 | Apr 6, 2023 - TTFP Facility Notification May 23, 2023 - CER Application Filed 38 | 23
In-service Date | Meter Station & Lateral Decommisioning | 2022 Meter Station and Laterals Decommissioning Program | Pipeline Laterals & Meters 23 - 310.34 km 2 Receipt | Q2 2025 | Approved | 2023-12-21 | Jun 19, 2023 - TTFP Notification Aug 21, 2023 - CER Application Filed41 | 18.6
| Compressor Station Unit Addition | Berland River Compressor Station Unit and Coolers Addition | 30 MW | 2026-04-01 | Approved | 2023-12-21 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix Sep 7, 2022 - TTFP Facilites Update Aug 1, 2023 - CER Application Filed39 | 166 - ROM 254 - Class 5 255 - Class 4 |  |  |  |  | 255
| Receipt Meter Station | Chambers Creek Receipt Meter Station | 864U | 2022-04-01 | In-Service | 2022-03-31 | May 25, 2021 - TTFP Notification Jun 16, 2021 - CER Application Filed 24 | 4 | 4
| Edson Mainline Expansion | Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Alford Creek) | 45 km NPS 48 | 2022-11-01 | In-Service | 2022-10-31 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 3, 2019 - NEB Application Filed 5 June 18, 2021 - CER Approval 25 Jan 17, 2023 - Facility Status Update (Estimate at Complete) | 269 - ROM 269 - Class 5 332 - EAC | 332 | [5 empty] | Elevated costs due to constrained supply chain and labor market conditions
| Edson Mainline Expansion | Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Elk River) | 40 km NPS 48 | 2022-11-01 | In-Service | 2022-10-07 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 3, 2019 - NEB Application Filed 5 June 18, 2021 - CER Approval 25 Jan 17, 2023 - Facility Status Update (Estimate at Complete) | 240 - ROM 240 - Class 5 333 - EAC | 333 | [5 empty] | Elevated costs due to constrained supply chain and labor market conditions
| Compressor Station | Emerson Creek Compressor Station | 2-30 MW Units | 2024-04-01 | Under Construction | 2022-07-11 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii June 1, 2021 - CER Application Filed 23 Dec 22, 2021- CER Approval30 | 257 - ROM 278 - Class 5 |  |  | 278
| Lateral Loop | Gleichen Transmission Looping (AP) Cluny Transmission Looping (AP) | 2.7 km NPS 3 2.3 km NPS 3 | 2022 | In-Service | Apr 23, 2022 Oct 26, 2022 | Jun 16, 2020 – GRA Application Filed 14 Mar 1, 2021 - GRA Application Approved 19 | 2.7
Proposed | Pipe Looping | Grande Prairie Mainline Loop (Colt Section) | 20 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 404 - P70 | [5 empty] | 404
Proposed | Pipe Looping | Grande Prairie Mainline Loop (Deep Valley North Section) | 14 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 254 - P70 | [5 empty] | 254
Proposed | Pipe Looping | Grande Prairie Mainline Loop (Deep Valley South Section) | 23 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 379 - P70 | [5 empty] | 379
Proposed | Pipe Looping | Grande Prairie Mainline Loop (Hornbeck Section) | 13 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 238 - P70 | [5 empty] | 238
Proposed | Pipe Looping | Grande Prairie Mainline Loop (Karr Section 1) | 15 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 205 - P70 | [5 empty] | 205
Proposed | Pipe Looping | Grande Prairie Mainline Loop (Karr Section 2) | 16 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 238 - P70 | [5 empty] | 238
Proposed | Pipe Looping | Grande Prairie Mainline Loop (Karr Section 3) | 25 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 332 - P70 | [5 empty] | 332
Proposed | Pipe Looping | Grande Prairie Mainline Loop (McLeod Section) | 21 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 321 - P70 | [5 empty] | 321
Proposed | Pipe Looping | Grande Prairie Mainline Loop (McLeod North Section) | 13 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 211 - P70 | [5 empty] | 211
| Pipe Looping | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) | 33km NPS 48 | 2026-04-01 | Approved | 2023-12-21 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix Sep 7, 2022 - TTFP Facilites Update Aug 1, 2023 - CER Application Filed39 Dec 21, 2023 - CER Approval40 | 281 - ROM 342 - Class 5 323 - Class 4 |  |  |  |  | 323
| Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition | Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Groundbirch Mainline Loop (Saturn Section) | 24 km NPS 42 | 2023-12-01 | In-Service | 2023-12-01 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Nov 5, 2020 - CER Application Filed 17 May, 13, 2021 - CER Approval 22 | 143 - ROM 140 - Class 5 |  | 140
| Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition | Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Saddle Hills Compressor Station Unit Addition | 30 MW | 2024-04-01 | Under Construction | 2023-03-15 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Nov 5, 2020 - CER Application Filed 17 May, 13, 2021 - CER Approval 22 | 159 - ROM 151 - Class 5 |  |  | 151
| Groundbirch Mainline Loop | Groundbirch Mainline Loop (Sunrise Section) | 24 km NPS 42 | 2023-04-01 | In-Service | 2023-04-16 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Oct 3, 2018 - TTFP Facility Update Apr 29, 2019 - NEB Application Filed 6 Sep 12, 2023 - Facility Status Update (Estimate at Complete) | 107 - ROM 155 - ROM 135 - ROM 140 - Class 4 176 - EAC |  | 176 |  |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| Compressor Station Coolers | Hidden Lake & Hidden Lake North Station Coolers | Coolers | 2023-04-01 | In-Service | 2023-03-30 | Dec 7, 2020 - TTFP Notification Jun 22, 2021 - CER Application Filed 26 Dec 10, 2021 - CER Approval 29 Sept 12, 2023 - Facility Status Update (Estimate at Complete) | 45 - ROM 47 - Class 4 53 - EAC |  | 53 |  |  |  |  | Elevated prime contractor costs.
| Pipe Looping | Inland Looping (AP) | 9km NPS 20 | 2025-11-01 | Proposed | 2021-12-06 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix June 21, 2023 - Facility Status Update | 40 - ROM
Approved | Delivery Meter Station | Iosegun Sales Meter Station | 440T Turbine Meter | 2024-09-01 | Approved | 2024-02-15 | Sep 11, 2023 - CER Application Filed42 Feb 15, 2024 - TTFP Notification | 3.3 |  |  | 3.3
| Connection Facility | Leismer Ethane Extraction Plant Tie-in | NPS 30 Connection, Valves, Tees | 2023-04-01 | In-Service | 2023-05-01 | Apr 06, 2022 - TTFP Notification Apr 26, 2022 - CER Application Filed32 | 3.2 |  | 3.2
Update to Facility Name, Applied for | Pipe Looping | Leming Loop (Field Lake Section) | 17 km NPS 20 | Apr 2026 | Applied for | 2024-03-12 | Dec 13, 2022 - TTFP Presentation, 2022 Annual Plan x May 9, 2023 - TTFP Facility Update Presentation Mar 01, 2024 - CER Application Filed43 | 270 - ROM 107 - Class 5 105 - Class 4 |  |  |  |  | 105
Proposed | Pipe Looping | Leming Loop (Sand River Section) | 22 km NPS 20 | 2027 | Proposed | Feb 15, 2024 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 149 - ROM | [5 empty] | 149
| Pipeline Upgrade | Lethbridge Urban Pipeline Upgrade (AP) | 10.8 km NPS 8 2.4 km NPS 6 Control Station 3 Delivery Stations | Q3 2024 | In-Service | 2024-01-11 | Aug 7, 2018 - TTFP Notification Jul 30, 2018 - GRA Application Filed 7 Jun 16, 2020 - GRA Application Filed 15 Mar 1, 2021 - GRA Application Approved 19 | 40
| Receipt Meter Station | Mackie Creek North Receipt Meter Station Expansion | 682U Ultrasonic Meter | 2024-01-01 | In-Service | 2023-12-15 | Jun 20, 2023, - TTFP Notification | 1.1 |  |  | 1.1
| Delivery Meter Station | McLeod River Sales Meter Station | 860U Ultrasonic Meter | 2022-10-01 | In-Service | 2022-09-28 | Oct 12, 2021 - TTFP Notification Oct 26, 2021 - CER Application Filed 28 | 4 | 4
| Delivery Meter Station | Mildred Lake West Sales Meter Station | 2-1010U Ultrasonic Meter | 2024-04-01 | Under Construction | 2023-10-30 | Nov 30, 2022 - TTFP Notification Mar 13, 2023 - CER Application Filed 37 | 6.6 |  |  | 6.6
| North Corridor Expansion | North Corridor Expansion Project: Hidden Lake North Compressor Station Unit Addition | 30 MW | 2023-04-01 | In-Service | 2023-05-07 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 8 May 5, 2021 - CER Approval 21 Sept 12, 2023 - Facility Status Update (Estimate at Complete) | 138 - ROM 138 - Class 5 195 - EAC |  | 195 |  |  |  |  | Elevated prime contractor costs.
| North Corridor Expansion | North Corridor Expansion Project: North Central Corridor Loop (North Star Section 2) | 24 km NPS 48 | 2023-04-01 | In-Service | 2023-01-19 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 8 May 5, 2021 - CER Approval 21 Apr 11, 2023 - Facility Status Update (Estimate at Complete) | 155 - ROM 155 - Class 5 198 - EAC |  | 198 |  |  |  |  | Issuance of a Stop Work Order by the CER, resulting in unplanned standby and delay with commencement of work.
| North Corridor Expansion | North Corridor Expansion Project: North Central Corridor Loop (Red Earth Section 3) | 32 km NPS 48 | 2023-04-01 | In-Service | 2023-04-11 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 8 May 5, 2021 - CER Approval 21 July 11, 2023 - Facility Status Update (Estimate at Complete) | 205 - ROM 205 - Class 5 289 - EAC |  | 289 |  |  |  |  | Elevated prime contractor costs due to unfavorable market conditions. Issuance of a Stop Work Order by the CER, resulting in unplanned standby and delay with commencement of work.
| North Corridor Expansion | North Corridor Expansion Project: Northwest Mainline Loop No.2 (Bear Canyon North Extension Section) | 25 km NPS 36 | 2023-04-01 | In-Service | 2023-03-23 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 8 May 5, 2021 - CER Approval 21 Sept 12, 2023 - Facility Status Update (Estimate at Complete) | 134 - ROM 134 - Class 5 132 - EAC |  | 132 |  |  |  |  | Favourable prime contractor costs due to competitive market conditions for smaller diameter pipelines.
Scope & Cost Update | Yellowhead Mainline Expansion | Peers Compressor Station Unit Addition (AP) | 5-15 MW | 2027 | Proposed | 2023-05-09 | May 9, 2023 - TTFP Facility Update Presentation Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 103 - ROM 138 - Class 5
| Acquisition | Pioneer South Pipeline Acquisition | 30 km NPS 20 | 2021-10-01 | In-Service | 2022-02-25 | Jan 15, 2021 - CER Application Filed 18 Dec 22, 2021 - CER Approval 31 Aug 9, 2022 - Facility Status Update (Estimate at Complete) | 68 64 - EAC | 64
| Delivery Meter Station | Smoky River South Sales Meter Station | NPS 3 Positive Displacement Meter | 2022-09-01 | In-Service | 2023-07-05 | May 20, 2021 - TTFP Notification Aug 26, 2021 - NEB Application Filed 27 | 4.5 | 4.5
| Installation (AP) | Spruce Grove and Stony Plain UPU – Installation (AP) | 5.4 km NPS 6 3 Delivery Stations | Q1 2024 | Approved | 2021-03-01 | Jun 16, 2020 - GRA Application Filed 12 Mar 1,2021 - GRA Application Approved 19 | 13.2 11.5
| Pipeline Replacement | Urban Pipeline Replacement Project: Edmonton UPR – NE Connector (AP) | Control Station | 2024 | Approved |  | Oct 30, 2014 - TTFP Presentation Dec 4, 2018 – AUC Project Update Filed 10 Jun 16, 2020 - AUC Project Update Filed 13 | 11
Proposed | Compressor Station Unit Addition & Coolers | Vetchland Compressor Station Unit and Cooler Additions | 30 MW | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 352 - P70 | [5 empty] | 352
| West Path Delivery 2022 | West Path Delivery 2022 ABC Border Meter Station Expansion | 5 - NPS 20U Ultrasonic Meters | 2022-11-01 | In-Service | 2022-06-10 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Jun 1, 2020 - NEB Application Filed 11 April 30, 2021 - Approval 20 | 8 | 8
| West Path Delivery 2022 | West Path Delivery 2022 Edson Mainline No. 4 (Raven River) | 18 km NPS 48 | 2022-11-01 | In-Service | 2022-10-31 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Jun 1, 2020 - NEB Application Filed 11 April 30, 2021 - Approval 20 Mar 13, 2023 - Facility Status Update (Estimate at Complete) | 128 - ROM 141 - EAC | 141 | [5 empty] | Elevated costs due to construction cost increases
| West Path Delivery 2022 | West Path Delivery 2022 WAML Loop No. 2 (Alberta British Columbia) | 6 km NPS 48 | 2022-11-01 | In-Service | 2022-11-24 | Jan 21, 2020 - TTFP 2019 Annual Plan Update vii Jun 1, 2020 - NEB Application Filed 11 April 30, 2021 - Approval 20 Apr 11, 2023 - Facility Status Update (Estimate at Complete) | 57 - ROM 136 - EAC | 136 | [5 empty] | Elevated costs as a result of significant delays due to wildlife zones and terrain complexity. Elevated prime contractor costs due to unfavorable market conditions.
| West Path Delivery 2023 | West Path Delivery 2023 WAML Loop No. 2 (Longview) | 9 km NPS 48 | 2023-11-01 | In-Service | 2023-10-19 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 16 Dec 1, 2022 - CER Approval 35 Feb 15, 2024 - Facility Status Update (Estimate at Complete) | 65 - ROM 75 - Class 5 108 - EAC |  | 108 |  |  |  |  | Elevated costs due to construction scope of work (material cost increases, design changes and rework, and third party clearing).
| West Path Delivery 2023 | West Path Delivery 2023 WAML Loop No. 2 (Lundbreck) | 7 km NPS 48 | 2023-11-01 | In-Service | 2023-10-27 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 16 Dec 1, 2022 - CER Approval 35 Feb 15, 2024 - Facility Status Update (Estimate at Complete) | 83 - ROM 72 - Class 5 153 - EAC |  | 153 |  |  |  |  | Elevated costs due to construction scope of work (difficult terrain, design changes and rework, and third party clearing). Additional contractor costs due to unfavorable market conditions.
| West Path Delivery 2023 | West Path Delivery 2023 WAML Loop No. 2 (Turner Valley) | 24 km NPS 48 | 2023-11-01 | In-Service | 2023-11-01 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 16 Dec 1, 2022 - CER Approval 35 Feb 15, 2024 - Facility Status Update (Estimate at Complete) | 209 - ROM 209 - Class 5 260 - EAC |  | 260 |  |  |  |  | Elevated costs due to material cost increases, design changes and rework, and third party clearing.
Proposed | Compressor Station Unit Addition & Coolers | Wolf Lake Compressor Station Unit and Cooler Additions | 30 MW | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 362 - P70 | [5 empty] | 362
Approved | Receipt Meter Station | Wilkin Lake Receipt Meter Station | 884U Ultrasonic Meter | 2024-07-01 | Approved | 2023-12-14 | Oct 16, 2023 CER Application Dec 14, 2023 CER Approval44 | 5.9 |  |  | 5.9
| Delivery Meter Station | Willow Valley Interconnect Project | 2-1610U Ultrasonic Meter | 2024-04-24 | Under Construction | 2023-11-14 | Jan 5, 2023 - TTFP Notification Jan 18, 2023 - CER Application Filed 36 | 7.1 |  |  | 7.1
Scope & Cost Update | Yellowhead Mainline Expansion | Yellowhead Mainline (AP) | 215 km NPS 36 | 2027 | Proposed | 2023-05-09 | May 9, 2023 - TTFP Facility Update Presentation Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan | 1024 - ROM 1,815 - Class 5

## References
References
Annual Plans
i. | NGTL 2013 Annual Plan
ii. | NGTL 2014 Annual Plan
iii. | NGTL 2015 Annual Plan
iv. | NGTL 2016 Annual Plan
v. | NGTL 2017 Annual Plan
vi. | NGTL 2018 Annual Plan
vii. | NGTL 2019 Annual Plan
viii. | NGTL 2020 Annual Plan
ix. | NGTL 2021 Annual Plan
x. | NGTL 2022 Annual Plan
1 | 2018 Meter Stations and Laterals Abandonment Program
2 | 2018 Pipeline Decommissioning Program
3 | 2021 NGTL System Expansion Project
4 | Canada Energy Regulator Report for the 2021 NGTL System Expansion Project
5 | Application for the Construction of Edson Mainline Expansion Project
6 | Application for the Construction of Groundbirch Mainline Loop (Sunrise Section)
7 | GRA Application Filed
8 | Application for the Construction of North Corridor Expansion Project
9 | Application for North Montney Project
10 | Dec 4, 2018 – AUC Project Update Filed
11 | NGTL West Path Delivery 2022 CER
12 | GRA Application Filed
13 | (GRA) AUC Project Update Filed
14 | Gleichen-Cluny GRA Filed
15 | GRA Application Filed
16 | NGTL West Path Delivery 2023 CER
17 | NGTL GBML Loop (Saturn Section) & Saddle Hills CS C4 Unit Addition
18 | Canada Energy Regulator - REGDOCS - C10955 NOVA Gas Transmission Ltd. - Pioneer South Pipeline Acquisition (cer-rec.gc.ca)
19 | March 1, 2021 - GRA Application Approved
20 | April 30, 2021 - West Path Delivery Project
21 | North Corridor Expansion - GIC Approval
22 | GBML (Saturn) and Saddle Hills UA Application
23 | Emerson Creek Compressor Station
24 | Application for the construction of Chambers Creek Receipt Meter Station
25 | Edson Mainline Expansion CER Approval
26 | Hidden Lake and Hidden Lake North Cooler Additions Application
27 | Smoky River South Sales Meter Station Application
28 | McLeod River Sales Meter Station Application
29 | Hidden Lake and Hidden Lake North Cooler Additions CER Approval
30 | Emerson Creek Compressor Station Approval
31 | Pioneer South Pipeline Acquisition CER Approval
32 | Leismer Ethane Extraction Plant Tie-in
33 | 2021 Meter Station and Laterals Abandonment Program
34 | 2021 Meter Station and Laterals Decommissioning Program
35 | West Path Delivery 2023 Project CER Approval
36 | Willow Valley Interconnect Project
37 | Mildred Lake West Sales Meter Station Application
38 | 2022 Meter Stations and Laterals Abandonment Program
39 | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) and Berland River CS C3 Unit Addition Application
40 | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) and Berland River CS C3 Unit Addition Approval
41 | 2022 Meter Stations and Laterals Decommissioning Program
42 | Iosegun Sales Meter Station CER Project Notification
43 | Leming Lake Sales Lateral Loop (Field Lake Section) Application
44 | Wilkin Lake Receipt Meter Station Approval

## Facility Type Analysis (hidden)
Facility Type | Frequency
Abandonment | 0
Clearwater West Expansion | 0
Cogen Delivery Station | 0
Compressor Station | 1
Compressor Station Coolers | 1
Compressor Station Decomissioning | 0
Compressor Station Modifications | 0
Compressor Station Unit Addition | 1
Compressor Station Unit Addition & Coolers | 1
Connection Piping | 0
Control Valve Addition | 0
Crossover | 0
Delivery Meter Station | 4
Edson Mainline Expansion | 2
Expansion & Lateral Loop | 0
Extraction Connections | 0
Forestburg | 0
Grande Prairie Mainline Loop | 0
Groundbirch Mainline Loop | 1
Lateral Expansion | 0
Lateral Loop | 1
Meter Station & Lateral Abandonment | 3
NGTL System Expansion | 6
North Central Corridor Loop | 0
North Corridor Expansion | 4
North Montney Project | 0
North Path Delivery | 0
Northwest Mainline Loop | 0
Peace River Mainline Abandonment | 0
Pembina-Keephills Transmission Project | 0
Pipeline & Associated Decommissioning | 1
Pipeline Acquisition | 0
Pipeline Asset Purchase | 0
Pipeline Decommissioning | 0
Pipeline Replacement | 1
Pipeline Upgrade | 1
Receipt Meter Station | 2
Receipt Meter Station Expansion | 0
Saddle West Expansion | 0
Sales Meter Station | 0
Sales Meter Station Expansion | 0
Sales Meter Station Replacement | 0
Transmission Loop | 0
West Path Delivery 2022 | 3
West Path Delivery 2023 | 2
West Path Delivery Project | 0

## Forecast Costs (hidden)
Applied-for Facilities | Forecast Cost ($Millions)
Hidden Lake & Hidden Lake North Station Coolers
#REF!
#REF!
#REF!
#REF!
#REF!
West Path Delivery 2022 Edson Mainline No. 4 (Raven River) | 128 - ROM 141 - EAC
Groundbirch Mainline Loop (Sunrise Section)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Gleichen Transmission Looping (AP) Cluny Transmission Looping (AP) | 2.7
#REF!
#REF!
West Path Delivery 2023 WAML Loop No. 2 (Lundbreck) | 83 - ROM 72 - Class 5 153 - EAC
West Path Delivery 2022 WAML Loop No. 2 (Alberta British Columbia) | 57 - ROM 136 - EAC
#REF!
#REF!
#REF!
#REF!
#REF!
Chambers Creek Receipt Meter Station | 4
#REF!
#REF!
#REF!
#REF!
Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Saddle Hills Compressor Station Unit Addition
#REF!
#REF!
#REF!
#REF!
#REF!
#REF! | #REF!
#REF!
#REF!
#REF! | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Emerson Creek Compressor Station
#REF!
#REF!
2018 Meter Station and Laterals Abandonment Program
2018 Pipelines and Associated Facilities Decommissioning Program
#REF!
2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Brewster)
2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Dismal Creek)
2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Robb)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Colt Section)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Deep Valley)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Karr)
#REF!
#REF!
#REF!
#REF!
#REF!
2022 Meter Station and Laterals Abandonment Program | 23
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Alford Creek)
Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Elk River)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Grande Prairie Mainline Loop No. 4 (Valhalla North Section)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
McLeod River Sales Meter Station | 4
#REF!
#REF!
#REF!
#REF!
#REF!
Mildred Lake West Sales Meter Station | 6.6
North Corridor Expansion Project: Hidden Lake North Compressor Station Unit Addition
North Corridor Expansion Project: North Central Corridor Loop (North Star Section 2)
North Corridor Expansion Project: North Central Corridor Loop (Red Earth Section 3)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Pioneer South Pipeline Acquisition
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Smoky River South Sales Meter Station | 4.5
#REF!
#REF!
Spruce Grove and Stony Plain UPU – Installation (AP)
#REF!
#REF!
#REF!
Urban Pipeline Replacement Project: Edmonton UPR – NE Connector (AP)
#REF!
West Path Delivery 2023 WAML Loop No. 2 (Longview)
#REF!