## Summary & Notes
The Facility Status Update describes the current status of facilities that were applied for, are under construction or have been placed on-stream since the 2019 Annual Plan was issued on December 11, 2019 and maintains a record of the facilities for two years prior to the current year. Periodic updates are being provided based on the level of activity occurring with respect to facilities. Facilities with (AP) after the project name refer to facilities in the ATCO Pipelines footprint.
| Summary: | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024
| Total Costs by In-Service Year * | 557.3 | 3205.4 | 1857.9 | 3166.2 | 842 | 1468 | 461
Forecast Costs For NGTL projects greater than $25 million, the estimate type for the forecasted costs have been provided. The typical expected accuracy for the various estimate types are shown in the table below. These accuracy ranges are for projects with established technological complexity and can be greater depending on area knowledge, technological complexity, level of expertise, and certainty of facility scope. Forecasted costs reflect the dollar value, economic conditions, and estimation procedures at the time the estimates were completed.
Total Costs by In-Service Total Costs by In-Service Year are a summation of the last provided costs of all NGTL capacity capital projects with expected or realized in-service dates within a calendar year. Costs for non NGTL capacity capital projects, such as ATCO Pipelines, CIAC, decommissioning or abandonment projects, are excluded. These annual summations of costs will not match other regulatory filings with different costs bases. Variance Explanation Variance explanations are provided for all NGTL capacity capital projects with EAC costs equal to or greater than $25 million with a variance greater than 10% between the EAC and applied-for costs.
North Montney Project The North Montney Project was filed as a Section 52 application on November 8, 2013 comprised of the following facilities: North Montney Mainline (Aitken Creek Section), North Montney Mainline (Kahta Section), Aitken Creek Compressor Station, Saturn Compressor Station, Groundbirch Compressor Station, 14 receipt meter stations, a bi-directional storage meter station (Aitken Creek Interconnect) and a delivery meter station (Mackie Creek Interconnection). The NMML Variance was filed March 20, 2017 to vary Condition 4 in the Certificate and Order and to extend the Sunset Clause for the NMML. The Variance also includes the details on eight additional meter stations required for the new receipt contracts. North Montney costs are escalated to the year of in-service for each respective facility. The original Kahta Section was 119 km of NPS 42 with a ROT cost estimate of $530Million. Variance Application NEB Approval Order Received May 23, 2018. Mackie Creek North and Blair Creek receipt meter stations are currently under construction.
Northwest Mainline Loop (Bear Canyon North Section) Northwest Mainline Loop No. 2 (Bear Canyon North Section) is the combination of two previously presented facilities; Northwest Mainline Loop No. 2 (Bear Canyon North Section) and the Northwest Mainline Loop (Peace River Crossing Project). West Path Delivery Project: Turner Valley Compressor Station Unit Addition 7 Turner Valley Compressor Station Coolers has been combined with Turner Valley Compressor Station Unit Addition. Northwest Mainline Loop (Boundary Lake Section) Northwest Mainline Loop (Boundary Lake Section) was completed in two parts with ISD April 2017 and April 2018. The costs shown for 2018 are associated with the portion of the project completed in 2018.
Disclaimer The information provided in this document has been prepared to the best of management’s ability. TC does not represent or warrant that the information contained herein is accurate and complete in all respects or is fit for any purpose. Any of use of the information in its current or any manipulated form is the sole responsibility of the user. TC Energy is not responsible for any changes made to downloaded copies and/or results in data compiled, assumptions, and actions resulting from those changes. NGTL can only support use of the official PDF version as posted on TC Customer Express.

## Facilities Update
Report Updates | Facility Category | Applied-for Facilities | Description | Target In-Service Date | Status | Date of Status | References * | Forecast Cost * ($Millions) | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | Variance Explanation *
| Meter Station & Lateral Abandonment | 2015 Meter Station and Associated Lateral Abandonment | Barich Bigstone East Bigstone East B Clyde North Craigend North Dapp East Devenish South Daysland Hamlin Jones Lake East Killam North Minnow Lake South Sales Niobe Creek Niton North Pleasant West Ribstone Valhalla East Woking Nosehill Creek Lateral | Q4 2017 | Complete | 2018-05-01 | Aug 31, 2015 - TTFP Notification Oct 19, 2015 - NEB Application Filed 1 | 5.8
| Meter Station & Lateral Abandonment | 2016 Meter Station and Associated Lateral Abandonment | Coleman Enchant Grew Lake Grew Lake East Hotchkiss Hotchkiss East Meanook Rambling Creek East Sharrow South No.2 Steele Lake | Q3 2017 to Q1 2018 | Complete | 2019-06-01 | Nov 1, 2016 - TTFP Notification Dec 13, 2016 - NEB Application Filed 2 | 6.7
| Pipeline Decommissioning | 2016 Pipeline Decommissioning Program | Crossfield Lat Lp Mitsue Lat Lp Big Bend Lat Ricinus Lat Sedalia North Lat Tangent Lat (Tangent M/S) Atmore Lat (Atmore M/S) Bassano South Lateral | Q3 2017 to Q4 2019 | Complete | 2019-08-01 | Dec 19, 2016 - TTFP Notification Jan 23, 2017 - NEB Application Filed 3 | 5.6
| Meter Station & Lateral Abandonment | 2017 Meter Stations and Laterals Abandonment Program | Meter Stations w/Laterals Acadia East Acadia North Acadia Valley Bear Canyon West Big Bend East Blueberry Hill Blue Jay Donatville Hines Creek Hines Creek West Last Lake Lawrence Lake Manir Mills Tangent East Stand-Alone Meters Elinor Lake East Mega River Mega River No. 2 Rod Lake Rod Lake Sales Rossbear Lake Snowfall Creek Squirrel Mountain Owl Lake South Owl Lake South No. 2 Owl Lake South No. 3 Stand-Alone Laterals Alderson Lateral Kaybob South Lateral McNeill X-Over | Q1 2021 | Under Construction |  | Jun 29, 2017 - TTFP Notification Aug 21, 2017 - NEB Application Filed 4 | 16.4
| NGTL System Expansion | 2017 NGTL System Expansion Project: Northwest Mainline Loop (Boundary Lake Section) | 58 km NPS 36 33 km NPS 36 | April 2017 April 2018 | In-Service In-Service | June 2, 2017 Mar 30, 2018 | Oct 30, 2014 - TTFP Presentation, 2014 Annual Plan 5 Mar 31, 2015 - NEB Application Filed 6 Mar 14, 2017 - TTFP Update Jun 13, 2017 - TTFP Update Sep 4, 2018 - Appendix 2 Update (Estimate at Complete) | 384 - Class 5 442 - Class 4 424 - Class 3 495 - EAC | 185 | [6 empty] | Unfavourable construction conditions and increased prime costs.
| Meter Station & Lateral Abandonment | 2018 Meter Station and Laterals Abandonment Program | Meter Stations w/Laterals AECO A AECO I Andrew Chard Donnelly Esther Border Meadow Creek Mons Lake Mons Lake East Princess South Retlaw Rock Island Lake Rumsey West Saddle Lake West West Viking Stand-Alone Meter Stations Rock Island Lake South No. 2 Stand-Alone Laterals Boundary Lake South Flat Lake Lateral Ext. Marten Hills White Earth Creek | Q3 2022 | Under Construction |  | Aug 16, 2018 - TTFP Notification Sept 28, 2018 - NEB Application filed 7 | 17.9 18.1
| Pipeline & Associated Decommissioning | 2018 Pipelines and Associated Facilities Decommissioning Program | Pipeline Laterals Baxter Lake Calling Lake East Calling Lake South East Lat Loop Edgerton Flat Lake Lat Loop Flat Lake Lat Ext Judy Creek Sales North Lat Ext Loop Wainwright Wapiti Zama Lake Associated Facilities Edgerton Rec Judy Creek Sales Zama Lake No. 1 Rec Zama Lake No. 2 Rec Wapiti Rec PTI 360m Cross-over | Q4 2022 | Under Construction |  | Nov 14, 2018 - TTFP Notification Dec 7, 2018 - TTFP Notification Update Dec 18, 2018 - NEB Application Filed 8 | 14.3 28 - Class 5
| NGTL System Expansion | 2021 NGTL System Expansion Project: Beiseker Compressor Station Unit Addition | 30 MW | Apr 2021 - Apr 2022 | Approved | 2020-10-20 | Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 9 Feb 19, 2020 - CER Recommendation 10 Sep 8, 2020 - Facility Status Class Estimate Update | 120 - ROT 116 - Class 5 164 - Class 3 |  |  |  | 164 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Didsbury Compressor Station & Coolers | 30 MW | Apr 2021 - Apr 2022 | Approved | 2020-10-20 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Jun 20, 2018 - NEB Application Filed 9 Feb 19, 2020 - CER Recommendation 10 Sep 8, 2020 - Facility Status Class Estimate Update | 166 - ROT 116 - Class 5 153 - Class 3 |  |  |  | 153 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Brewster) | 49 km NPS 48 | Apr 2021 - Apr 2022 | Approved | 2020-10-20 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 9 Feb 19, 2020 - CER Recommendation 10 Sep 8, 2020 - Facility Status Class Estimate Update | 270 - ROT 287 - Class 5 315 - Class 3 |  |  |  | 315 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Dismal Creek) | 32 km NPS 48 | Apr 2021 - Apr 2022 | Approved | 2020-10-20 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Jun 20, 2018 - NEB Application Filed 9 Feb 19, 2020 - CER Recommendation 10 Sep 8, 2020 - Facility Status Class Estimate Update | 156 - ROT 179 - Class 5 285 - Class 3 |  |  |  | 285 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Robb) | 42 km NPS 48 | Apr 2021 - Apr 2022 | Approved | 2020-10-20 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 9 Feb 19, 2020 - CER Recommendation 10 Sep 8, 2020 - Facility Status Class Estimate Update | 232 - ROT 232 - Class 5 274 - Class 3 |  |  |  | 274 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Colt Section) | 14 km NPS 48 | Apr 2021 - Apr 2022 | Approved | 2020-10-20 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Jun 20, 2018 - NEB Application Filed 9 Feb 19, 2020 - CER Recommendation 10 Sep 8, 2020 - Facility Status Class Estimate Update | 73 - ROT 80 - Class 5 117 - Class 3 |  |  |  | 117 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Deep Valley) | 69 km NPS 48 | Apr 2021 - Apr 2022 | Approved | 2020-10-20 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Jun 20, 2018 - NEB Application Filed 9 Feb 19, 2020 - CER Recommendation 10 Sep 8, 2020 - Facility Status Class Estimate Update | 332 - ROT 377 - Class 5 530 - Class 3 |  |  |  | 530 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Karr) | 57 km NPS 48 | Apr 2021 - Apr 2022 | Approved | 2020-10-20 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 9 Feb 19, 2020 - CER Recommendation 10 Sep 8, 2020 - Facility Status Class Estimate Update | 298 - ROT 327 - Class 5 409 - Class 3 |  |  |  | 409 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
Combined Elmworth Section 2 & 3 into single row | NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.3 (Elmworth Section 2 & 3) | 44 km NPS 48 | Apr 2021 - Apr 2022 | Approved | 2020-10-20 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Jun 20, 2018 - NEB Application Filed 9 Feb 19, 2020 - CER Recommendation 10 Sep 8, 2020 - Facility Status Class Estimate Update | 283 - ROT 283 - Class 5 328 - Class 3 |  |  |  | 328 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.4 (Valhalla) | 36 km NPS 48 | Apr 2021 - Apr 2022 | Approved | 2020-10-20 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Jun 20, 2018 - NEB Application Filed 9 Feb 19, 2020 - CER Recommendation 10 Sep 8, 2020 - Facility Status Class Estimate Update | 152 - ROT 187 - Class 5 235 - Class 3 |  |  |  | 235 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: January Creek Control Valve Addition | Control Valve Addition | Apr 2021 - Apr 2022 | Approved | 2020-10-20 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Jun 20, 2018 - NEB Application Filed 9 Feb 19, 2020 – CER Recommendation 10 Sep 8, 2020 - Facility Status Class Estimate Update | 5 5 4 - Class 3 |  |  |  | 4 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Nordegg Compressor Station Unit Addition | 30 MW | Apr 2021 - Apr 2022 | Approved | 2020-10-20 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Jun 20, 2018 - NEB Application Filed 9 Feb 19, 2020 - CER Recommendation 10 Sep 8, 2020 - Facility Status Class Estimate Update | 145 - ROT 119 - Class 5 149 - Class 3 |  |  |  | 149 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| Pipeline Asset Purchase | Albersun Pipeline Asset Purchase | 179 km | TBD | In-Service | 2018-10-01 | May 12, 2015 - TTFP Presentation Apr 27, 2016 - NEB Application Filed 12 | 28 - Class 5 30 - Class 4 | 30
| Sales Meter Station | Alberta Montana Border Sales Meter Station Replacement | 2-1280U Ultrasonic Meter | 2020-07-01 | In-Service | 2020-06-29 | Sep 18, 2019 - TTFP Notification Oct 3, 2019 - CER Application Filed 13 | 4.6 |  |  | 4.6
| Receipt Meter Station | Anderson Lake Receipt Meter Station | 10104U Ultrasonic Meter | 2020-09-01 | In-Service | 2020-07-17 | Oct 8, 2019 - TTFP Notification 14 Oct 22, 2019 - CER Application Filed | 4 |  |  | 4
| Compressor Station Unit Addition | Berland River Compressor Station Unit Addition | 30 MW | TBD | Deferred |  | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 | 145 - ROT
| Receipt Meter Station Expansion | Bonanza Receipt Meter Station Expansion | 2-1284U Ultrasonic Meter | 2018-08-01 | In-Service | 2018-08-08 | Oct 16, 2017- TTFP Notification Nov 3, 2017 - NEB Application Filed 15 | 5.5 | 5.5
In-Service Nov 24, 2020 | Compressor Station Unit Addition | Buffalo Creek Compressor Station Unit Addition | 30 MW | 2020-11-01 | In-Service | 2020-11-24 | Dec 7, 2015 - TTFP Presentation, 2015 Annual Plan 16 Aug 16, 2016 - TTFP Presentation (Status Update/Deferral) Dec 4, 2017 - TTFP Presentation (Status Update), 2017 Annual Plan 11 Oct 1, 2018 - NEB Application Filed 17 | 139 - ROT 159 - Class 4 |  |  | 159
| Sales Meter Station Expansion | Christina Lake North Sales Meter Station Expansion | 2-1210U Ultrasonic Meter | 2018-03-01 | In-Service | 2018-03-08 | Jul 20, 2017 - TTFP Notification Aug 18, 2017 - NEB Application Filed 18 | 4.4 | 4.4
| Receipt Meter Station | Clark Lake South Receipt Meter Station | 1010-4U Ultrasonic Meter | 2019-06-01 | In-Service | 2019-05-31 | Aug 13, 2018 - TTFP Notification Sep 4, 2018 - NEB Application Filed 19 | 4.4 |  | 4.4
| 2021 Clearwater Unit Addition | Clearwater Compressor Station Unit Addition & Coolers | 30 MW | 2021-11-01 | Under Construction |  | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Jul 20, 2018 - TTFP Update Sep 26, 2018 - CER Application Filed 21 | 145 - ROT 128 - Class 5 |  |  |  | 128
| Clearwater West Expansion | Clearwater West Expansion: Clearwater Compressor Station Unit Addition | 30 MW | 2020-04-01 | In-Service | 2020-04-04 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Jun 4, 2018 - NEB Application Filed 20 Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 117 - ROT 118 - Class 4 144 - EAC |  |  | 144 |  |  |  |  | Elevated prime contractor costs due to unfavourable market conditions
| Clearwater West Expansion | Clearwater West Expansion: Grande Prairie Mainline Loop No.2 (Huallen) | 13 km NPS 48 | 2020-04-01 | In-Service | 2020-03-19 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Jun 4, 2018 - NEB Application Filed 20 Aug 11, 2020 - Appendix 2 Update (Estimate at Complete) | 59 - ROT 77 - Class 4 84 - EAC |  |  | 84
| Clearwater West Expansion | Clearwater West Expansion: Grande Prairie Mainline Loop No.3 (Elmworth Section 1) | 24 km NPS 48 | 2020-04-01 | In-Service | 2020-05-30 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Jun 4, 2018 - NEB Application Filed 20 Nov 10, 2020 - Facility Status Update (Estimate at Complete) | 150 - ROT 130 - Class 4 161 - EAC |  |  | 161 |  |  |  |  | Unfavourable construction conditions.
| Clearwater West Expansion | Clearwater West Expansion: Wolf Lake Compressor Station Unit Addition | 30 MW | 2020-04-01 | In-Service | 2020-04-25 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Jun 4, 2018 - NEB Application Filed 20 Aug 11, 2020 - Appendix 2 Update (Estimate at Complete) | 111 - ROT 126 - Class 4 155 - EAC |  |  | 155 |  |  |  |  | Elevated prime contractor costs due to unfavourable market conditions.
| Sales Meter Station Replacement | Cold Lake Border Sales Meter Station Replacement | 1010U Ultrasonic Meter | 2021-11-01 | Approved | 2020-07-17 | Aug 9, 2019 - TTFP Notification Aug 23, 2019 - NEB Application Filed 22 | 3.2 |  |  |  | 3.2
| Lateral Expansion | Cutbank River Lateral Expansion | 18 km NPS 30 13 km NPS 16 | TBD | Cancelled |  | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan 23 | 97 - ROT
| Receipt Meter Station | Cutbank River North Receipt Meter Station | 660U-2 Ultrasonic Meter | 2020-04-01 | In-Service | 2020-03-31 | May 22, 2019 - TTFP Notification Jun 25, 2019 - NEB Application Filed 24 | 3.2 |  |  | 3.2
| Receipt Meter Station | Dawson Creek East No. 2 Receipt Meter Station | 662U Ultrasonic Meter | 2020-07-01 | In-Service | 2020-06-12 | Sep 20, 2019 - TTFP Notification Oct 8, 2019 - CER Application Filed 26 | 3.8 |  |  | 3.8
In-Service Oct 27, 2020 | Receipt Meter Station | Dawson Creek No. 2 Receipt Meter Station | 10104U | 2020-10-01 | In-Service | 2020-10-27 | Dec 2, 2019 - TTFP Notification Dec 18, 2019 - CER Application Filed 25 | 4.4 |  |  | 4.4
| Receipt Meter Station | Dismal Creek North Receipt Meter Station | 1010-4U | 2018-10-01 | In-Service | 2018-11-29 | Nov 22, 2017 - NEB Application Filed 27 Nov 24, 2017 - TTFP Notification | 3.2 | 3.2
| Receipt Meter Station | Dorscheid Receipt Meter Station | 662U Ultrasonic Meter | 2019-12-01 | In-Service | 2019-12-05 | Jan 16, 2019 - TTFP Notification Feb 26, 2019 - NEB Application Filed 28 | 3.2 |  | 3.2
| Compressor Station Coolers | Drywood Compressor Station Coolers |  | 2018-11-01 | In-Service | 2018-10-30 | Nov 14, 2017 - TTFP Notification Dec 11, 2017 - NEB Application Filed 29 Oct 14, 2020 - Appendix 2 Update (Estimate at Complete) | 15 7 6.7 - EAC | 6.7
| Control Valve Addition | Edson Control Valve Addition | Control Valve Installation | 2019-04-01 | In-Service | 2019-05-05 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 May 29, 2018 - NEB Application Filed 30 | 5 6.7 |  | 6.7
| Edson Mainline Expansion | Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Alford Creek) | 45 km NPS 48 | 2022-04-01 | Applied for | 2019-04-03 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan 23 Apr 3, 2019 - NEB Application Filed 31 | 269 - ROT 269 - Class 5 |  |  |  |  | 269
| Edson Mainline Expansion | Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Elk River) | 40 km NPS 48 | 2022-04-01 | Applied for | 2019-04-03 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan 23 Apr 3, 2019 - NEB Application Filed 31 | 240 - ROT 240 - Class 5 |  |  |  |  | 240
| Compressor Station | Emerson Creek Compressor Station | 2-30 MW Units | 2024-04-01 | Proposed |  | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan 32 | 257 - ROT | [6 empty] | 257
| Extraction Connections | Empress Area Extraction Connections Project | 240 m Pipeline plus Valve Assemblies | Q3 2018 | In-Service | 2018-06-28 | Sep 8, 2017 - TTFP Notification Oct 5, 2017 - NEB Application Filed 33 | 17 - CIAC
| Abandonment | Etzikom Abandonment | 84 km NPS 10/6 | Q4 2019 | Denied | 2020-05-20 | Oct 3, 2018 - TTFP Notification Oct 31, 2018 - NEB Application Filed 34 | 18.2
| Compressor Station Modifications | Farrell Lake CS Modifications | Yard Piping Modifications | 2018-11-01 | In-Service | 2018-08-30 | Mar 27, 2018 - TTFP Notification | 9.1 | 9.1
| Forestburg | Forestburg Lateral Loop Forestburg East Sales Meter Station | 8.2 km NPS10 2-1080U Ultrasonic Meter | Q4 2019 | In-Service In-Service | Nov 7, 2019 Nov 9, 2019 | Oct 10, 2018 - TTFP Notification Nov 8, 2018 - NEB Application Filed 35 | 21.5 21.8 |  | 21.8
| Transmission Loop | Gleichen-Cluny Transmission Looping – Installation (AP) | 2.4 km NPS 3 2.0 km NPS 3 | 2021 | Proposed |  | Jun 16, 2020 – GRA Application Filed 96 | 2.7
| Receipt Meter Station Expansion | Gold Creek South Receipt Meter Station Expansion | 882 Orifice Meter | 2018-04-01 | In-Service | 2018-03-23 | Jul 26, 2018 - TTFP Notification Aug 19, 2017 - NEB Application Filed 36 | 3 | 3
| Receipt Meter Station Expansion | Gold Creek South Receipt Meter Station Expansion No. 2 | 10104U Ultrasonic Meter | 2019-07-01 | In-Service | 2019-12-06 | Oct 26, 2018 - TTFP Notification Nov 14, 2018 - NEB Application Filed 37 | 3.5 |  | 3.5
| Receipt Meter Station | Gold Creek West Receipt Meter Station | 12124U Ultrasonic Meter | 2019-04-01 | In-Service | 2019-01-21 | Apr 6, 2018 - TTFP Notification Apr 30, 2018 - NEB Application Filed 38 | 4.9 |  | 4.9
| Compressor Station Unit Addition | Goodfish Compressor Station Unit Addition | 30 MW | 2020-11-01 | In-Service | 2020-10-31 | Feb 13, 2018 - TTFP Facility Update Oct 1, 2018 - NEB Application Filed 17 | 120 - ROT 115 - Class 4 |  |  | 115
| Receipt Meter Station | Grace Creek North Receipt Meter Station | 660-2 Orifice Meter | 2018-02-01 | In-Service | 2018-03-07 | Jun 1, 2017 - TTFP Notification Jul 6, 2017 - NEB Application Filed 39 | 2 | 2
| Grande Prairie Mainline Loop | Grande Prairie Mainline Loop No. 2 (McLeod River North Section) | 35 km NPS 48 | 2019-11-01 | In-Service | 2020-04-08 | Jul 21, 2017 - TTFP Facility Update Nov 14, 2017 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 40 Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 108 - ROT 155 - ROT 237 - Class 4 317 - EAC |  | 317 | [5 empty] | Cost increase related to unseasonably wet weather which impacted field productivity rate, significant spending on procurement/deployment of matting, as well as complications on the Wildhay and Athabasca HDD.
| Grande Prairie Mainline Loop | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) | 33 km NPS 48 | 2024-04-01 | Proposed |  | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan 32 | 204 - ROT | [6 empty] | 204
| Receipt Meter Station Expansion | Grey Owl Creek North Receipt Meter Station Expansion | 882 Orifice Meter | 2018-04-01 | In-Service | 2018-03-27 | Jun 1, 2017 - TTFP Notification Jun 29, 2017 - NEB Application Filed 41 | 3.2 | 3.2
| Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition | Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Groundbirch Mainline Loop (Saturn Section) | 24 km NPS 42 | 2023-04-01 | Applied for | 2020-11-05 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan 32 Nov 5, 2020 - CER Application Filed 99 | 143 - ROT 140 - Class 5 | [5 empty] | 140
| Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition | Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Saddle Hills Compressor Station Unit Addition | 30 MW | 2023-04-01 | Applied for | 2020-11-05 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan 32 Nov 5, 2020 - CER Application Filed 99 | 159 - ROT 151 - Class 5 | [5 empty] | 151
| Groundbirch Mainline Loop | Groundbirch Mainline Loop (Sunrise Section) | 24 km NPS 42 | 2022-04-01 | Approved | 2019-10-24 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Oct 3, 2018 - TTFP Facility Update Apr 29, 2019 - NEB Application Filed 42 | 107 - ROT 155 - ROT 135 - ROT 140 - Class 4 |  |  |  |  | 140
Row Added | North Montney Project | Gundy West No. 2 | 880U Ultrasonic Meter | 2020-11-21 | Proposed | 2020-11-30 | Nov 30, 2020 - TTFP Notification | 3.6 |  |  |  | 3.6
| Compressor Station Modifications | Hidden Lake North C/S Modifications | Yard Piping Modifications and Wheel Change | 2018-04-01 | In-Service | 2018-04-20 | Aug 25, 2017 - TTFP Notification | 5 | 5
| Lateral Loop | Hythe Lateral Loop No. 2 | 14 km NPS 24 | Q4 2018 | In-Service | 2018-10-31 | Dec 7, 2015 - TTFP Presentation, 2015 Annual Plan 16 Aug 16, 2016 - TTFP Presentation (Status Update/Deferral) Sep 12, 2017 - TTFP Presentation (Scope/Status Update) Nov 1, 2017 - NEB Application Filed 43 May 7, 2019 - Appendix 2 Update (Estimate at Complete) | 41 - Class 5 42 - Class 5 40 - Class 4 41 - EAC | 41
| Sales Meter Station | Ipiatik Lake Sales Meter Station Modifications | Modifications | 2018-04-01 | In-Service | 2018-02-02 | Sep 6, 2017 - TTFP Notification Sep 29, 2017 - NEB Application Filed 44 | 1.3 | 1.3
| Keephills Expansion | Keephills Expansion (AP) | Control Station Meter Station | 2021 | Proposed |  | Jun 16, 2020 - GRA Application Filed 93 | 5.8
| Pipeline Upgrade | Lethbridge Urban Pipeline Upgrade (AP) | 10.8 km NPS 8 2.4 km NPS 6 Control Station 3 Delivery Stations | 2022 | Proposed |  | Aug 7, 2018 - TTFP Notification Jul 30, 2018 - GRA Application Filed 45 Jun 16, 2020 - GRA Application Filed97 | 40
| Receipt Meter Station Expansion | Livingstone Creek Receipt Meter Station Expansion | 10104U | 2018-11-01 | In-Service | 2018-11-14 | Mar 1, 2018 - TTFP Notification Mar 26, 2018 - NEB Application Filed 46 | 3.1 | 3.1
| Sales Meter Station | Liza Lake Sales Meter Station | NPS 3 Positive Displacement Meter | 2018-12-01 | In-Service | 2018-12-18 | Oct 16, 2018 - TTFP Notification, Streamlining Order | 2.1 | 2.1
| Expansion & Lateral Loop | Medicine Hat Expansion Medicine Hat and Suffield Lateral Loop | 58 km NPS 24 | 2024-11-01 | Proposed |  | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan 32 | 189 - ROT | [5 empty] | 189
| Sales Meter Station | Mildred Lake East Sales Meter Station | 660U Ultrasonic Meter | 2019-09-01 | In-Service | 2019-12-06 | Nov 30, 2018 - TTFP Notification Feb 13, 2019 - TTFP Notification Amendment Feb 14, 2019 - NEB Application Filed 47 | 3.2 4.1 |  | 4.1
| Receipt Meter Station Expansion | Minnow Lake West Receipt Meter Station Expansion | 2-1064U Ultrasonic Meter | 2018-11-01 | In-Service | 2018-11-01 | Aug 28, 2017 - TTFP Notification Sep 14, 2017 - NEB Application Filed 48 | 4.4 | 4.4
| Compressor Station Decomissioning | Moody Creek Compressor Station Decommissioning | Station decommissioning, and equipment transfer to Saturn Compressor Station | 2019-12-01 | Complete | 2019-10-02 | Apr 4, 2019 - TTFP Notification | 1 |  | 1
| Sales Meter Station | Muriel Creek Sales Meter Station | NPS 3 Positive Displacement Meter | 2019-03-01 | In-Service | 2019-03-01 | Jul 16, 2018 - TTFP Notification Aug 9, 2018 - TTFP Facility Update (Streamlining Order) | 2.1 |  | 2.1
| North Central Corridor Loop | North Central Corridor Loop (North Star Section 1) | 31 km NPS 48 | 2020-04-01 | In-Service | 2020-04-09 | Dec 7, 2015 - TTFP Presentation, 2015 Annual Plan 16 Aug 16, 2016 - TTFP Presentation (Status Update/Deferral) Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Oct 30, 2018 - NEB Application Filed 49 Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 200 - ROT 193 - ROT 170 - Class 4 165 - EAC |  |  | 165
| North Corridor Expansion | North Corridor Expansion Project: Hidden Lake North Compressor Station Unit Addition | 30 MW | 2023-04-01 | Applied for | 2019-04-04 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan 23 Apr 4, 2019 - NEB Application Filed 50 | 138 - ROT 138 - Class 5 | [5 empty] | 138
| North Corridor Expansion | North Corridor Expansion Project: North Central Corridor Loop (North Star Section 2) | 24 km NPS 48 | 2023-04-01 | Applied for | 2019-04-04 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan 23 Apr 4, 2019 - NEB Application Filed 50 | 155 - ROT 155 - Class 5 | [5 empty] | 155
| North Corridor Expansion | North Corridor Expansion Project: North Central Corridor Loop (Red Earth Section 3) | 32 km NPS 48 | 2023-04-01 | Applied for | 2019-04-04 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan 23 Apr 4, 2019 - NEB Application Filed 50 | 205 - ROT 205 - Class 5 | [5 empty] | 205
| North Corridor Expansion | North Corridor Expansion Project: Northwest Mainline Loop No.2 (Bear Canyon North Extension Section) | 25 km NPS 36 | 2023-04-01 | Applied for | 2019-04-04 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan 23 Apr 4, 2019 - NEB Application Filed 50 | 134 - ROT 134 - Class 5 | [5 empty] | 134
| Receipt Meter Station | North Heart River Receipt Meter Station | 442 Orifice Meter | 2018-07-01 | In-Service | 2018-06-08 | Nov 20, 2017 - TTFP Notification Dec 4, 2017 - NEB Application Filed 51 | 2.7 | 2.7
| North Montney Project | North Montney Project: Aitken Creek Compressor Station | 15 MW Bi-directional | TBD | Deferred |  | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan 52 Nov 8, 2013 - NEB Application Filed 53 Mar 20, 2017 - NEB Variance Application 54 | 72 - ROT 98 - Class 4
| North Montney Project | North Montney Project: Groundbirch Compressor Station | 2-15 MW Units Bi-directional | 2019-11-01 | In-Service | 2019-10-25 | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan 52 Nov 8, 2013 - NEB Application Filed 53 Mar 20, 2017 - NEB Variance Application 54 Aug 7, 2018 - Appendix 2 Class Estimate Update Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 103 - ROT 135 - Class 4 131 - Class 3 110 - EAC |  | 110 | [5 empty] | Lower construction costs due to execution efficiencies, improved equipment costs, and risk mitigation
| North Montney Project | North Montney Project: North Montney Mainline (Aitken Creek Section) | 182 km NPS 42 | 2019-09-01 | In-Service | 2020-01-31 | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan 52 Nov 8, 2013 - NEB Application Filed 53 Mar 20, 2017 - NEB Variance Application 54 Aug 7, 2018 - Appendix 2 Class Estimate Update Apr 7, 2020 - Appendix 2 Update (Estimate at Complete) | 762 - ROT 930 - Class 4 1,270 - Class 3 1,400 - EAC |  | 1400 | [5 empty] | Elevated prime contractor costs due to unfavorable market conditions as well as complications on the Peace River HDD
| North Montney Project | North Montney Project: North Montney Mainline (Kahta Section - North) | 95 km NPS 42 | TBD | Deferred |  | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan 52 Nov 8, 2013 - NEB Application Filed 53 Mar 20, 2017 - NEB Variance Application 54 | 331 - Class 4
| North Montney Project | North Montney Project: North Montney Mainline (Kahta Section - South) | 24 km NPS 42 | 2020-04-01 | In-Service | 2020-05-01 | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan 52 Nov 8, 2013 - NEB Application Filed 53 Mar 20, 2017 - NEB Variance Application 54 Aug 7, 2018 - Appendix 2 Class Estimate Update Aug 11, 2020 - Appendix 2 Update (Estimate at Complete) | 174 - Class 4 196 - Class 4 204 - EAC |  |  | 204 |  |  |  |  | Elevated prime contractor costs due to unfavorable market conditions
| North Montney Project | North Montney Project: Saturn Compressor Station Unit 2 | 15 MW Bi-directional | TBD | Deferred |  | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan 52 Nov 8, 2013 - NEB Application Filed 53 Mar 20, 2017 - NEB Variance Application 54 | 63 - ROT
| North Montney Project | North Montney Project: Saturn Compressor Station | 15 MW Bi-directional | 2020-04-01 | In-Service | 2020-04-10 | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan 52 Nov 8, 2013 - NEB Application Filed 53 Mar 20, 2017 - NEB Variance Application 54 Aug 7, 2018 - Appendix 2 Class Estimate Update Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 70 - ROT 86 - Class 4 94 - Class 4 74 - EAC |  |  | 74 |  |  |  |  | Lower costs due to repurposing of existing assets as well as execution efficiencies
| North Montney Project | North Montney Project: Remaining North Montney Mainline Receipt Meter Stations Included in Certificate * Kahta Creek, Kahta Creek North, Buckinghorse River, Mason Creek, Beatton River, Lily Halfway River, Aitken Creek West, Aitken Creek East Mackie Creek Interconnect | TBD TBD | TBD TBD | Certificate Approval June 10, 2015 |  | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan 52 Nov 8, 2013 - NEB Application Filed 53 | 66 - Class 5 34 - Class 4 8
| North Montney Project | North Montney Project: Remaining North Montney Mainline Receipt Meter Stations Included in Certificate * Receipt Meter Stations Subject to Variance Application Blair Creek Gundy Kobes Altares Aitken Creek Interconnect (bi-directional storage) New Receipt Meter Stations Mackie Creek North Altares South Townsend Townsend No. 2 Gundy West Old Alaska Aitken Creek South Aitken Creek West No. 2 | 2-16104U Ultrasonic 2-1284U Ultrasonic 2-1064U Ultrasonic 2-1064U Ultrasonic 2-2416U Ultrasonic 662 Orifice Meter 882 Orifice Meter 882 Orifice Meter 882 Orifice Meter 882 Orifice Meter 882 Orifice Meter 2-1284U Ultrasonic 442 Orifice Meter | Apr 2020 Sep 2019 Apr 2021 Sep 2019 Q3 2021 Sep 2019 Sep 2019 Sep 2019 Sep 2019 Sep 2019 Sep 2019 Sep 2019 Apr 2020 | ISD May 19, 2020 ISD Jan 31, 2020 ISD Jan 31, 2020 Und. Construction ISD Jan 31, 2020 ISD Jan 31, 2020 ISD Jan 31, 2020 ISD Jan 31, 2020 ISD Jan 31, 2020 ISD Jan 31, 2020 ISD Apr 27, 2020 |  | Mar 20, 2017 - NEB Variance Application 54 Apr 27, 2017 - TTFP Notifications May 18-25, 2017 - NEB Applications Filed Link to Application 55 Link to Application 56 Link to Application 57 Link to Application 57 Link to Application 58 Link to Application 59 Link to Application 60 Link to Application 61 | 39 - Class 4 28 - ROT |  |  | 67
| North Path Delivery | North Path Delivery Project: Amber Valley Compressor Station Unit Addition | 15 MW | 2019-11-01 | In-Service | 2020-03-05 | Mar 14, 2017 - TTFP Update Jun 13, 2017 - TTFP Update Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Feb 16, 2018 - NEB Application Filed 62 Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 100 - ROT 89 - ROT 81 - Class 4 100 - EAC |  | 100 | [5 empty] | Prime change orders, internal costs, and project schedule changes due to weather delays, piping alignment challenges, hydrotest delays and new Contractor onboarding resulted in increased costs for the project
| North Path Delivery | North Path Delivery Project: Meikle River Compressor Station Series Modifications | Modifications to Enable Series Operation | Q2 2020 | In-Service | 2020-06-11 | Dec 7, 2015 - TTFP Presentation, 2015 Annual Plan 16 Aug 16, 2016 - TTFP Presentation (Status Update/Deferral) Mar 14, 2017 - TTFP Update Jun 13, 2017 - TTFP Update Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Feb 16, 2018 - NEB Application Filed 62 Sep 8, 2020 - Facility Status Update (Estimate at Complete) | 16 17 17 52 - EAC |  |  | 52 |  |  |  |  | Unanticipated complexities associated with brownfield site. Wildfire activity impacted cost and execution plans.
| North Path Delivery | North Path Delivery Project: Northwest Mainline Loop No. 2 (Bear Canyon North Section) | 28 km NPS 36 | 2019-11-01 | In-Service | 2019-09-25 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Feb 16, 2018 - NEB Application Filed 62 Jan 2020 Appendix 2 Update (Estimate at Complete) | 99 - ROT 109 - Class 4 109 - Class 4 160 - EAC |  | 160 | [5 empty] | Elevated prime contractor costs due to unfavorable market conditions. Stopple bypass required to complete tie-in of new section increased costs and delayed in-service
| Northwest Mainline Loop | Northwest Mainline Loop (Boundary Lake North Section) | 23 km NPS 36 | 2019-04-01 | In-Service | 2019-03-23 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Dec 15, 2017 - NEB Application Filed 63 Jun 4, 2019 Appendix 2 Update (Estimate at Complete) | 115 - ROT 105 - Class 4 98 - EAC |  | 98
Row Added | North Montney Project | Old Alaska No. 2 | 660-2U Ultrasonic Meter | 2020-11-21 | Proposed | 2020-11-30 | Nov 30, 2020 - TTFP Notification | 3.4 |  |  |  | 3.4
Complete Oct 23, 2020 | Peace River Mainline Abandonment | Peace River Mainline Abandonment (Meikle River to Valleyview Section) | 266 km NPS 20 2.3 km NPS 4 | 2020-12-01 | Complete | 2020-10-23 | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan 52 Oct 30, 2014 - TTFP Presentation, 2014 Annual Plan 5 Jul 22, 2016 - TTFP Presentation (Filing/Scope Change) Aug 18, 2016 - NEB Application Filed 64 | 30 - Class 4
| Pembina-Keephills Transmission Project | Pembina-Keephills Transmission Project (AP) | 58 km NPS 30 | 2020-04-01 | In-Service | 2020-04-01 | May 8, 2018 - TTFP Notification Aug 1, 2018 - AUC Application Filed 65 Nov 30, 2018 - AUC Project Update Filed 66 Oct 14, 2020 - Appendix 2 Update (Estimate at Complete) | 155 157 230 230 - EAC
AUC Application October 9, 2020 | Acquisition | Pioneer Pipeline Asset Purchase (AP) | 131 km NPS 20 | 2021 | Applied for | 2020-10-09 | Oct 2, 2020 - TTFP Presentation Oct 9, 2020 - AUC Application Filed100 | 276 266
| Compressor Station Unit Addition & Coolers | Pipestone Compressor Station Unit Addition & Coolers | 30 MW | TBD | Deferred |  | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 | 145 - ROT
| Receipt Meter Station | Pipestone Creek Receipt Meter Station | 662U Ultrasonic Meter | 2019-11-01 | In-Service | 2019-10-22 | Feb 1, 2019 - TTFP Notification Feb 19, 2019 - NEB Application Filed 67 | 3.1 |  | 3.1
| Receipt Meter Station Expansion | Prairie Creek Receipt Meter Station Expansion | NPS 8 Separator Installation | 2019-12-01 | In-Service | 2019-12-13 | Oct 2, 2019 - TTFP Notification, Streamlining Order | 1.3 |  | 1.3
| Compressor Station Unit Addition & Coolers | Princess Compressor Station Unit Addition & Coolers | 30 MW | TBD | Deferred |  | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan 23 | 137 - ROT
| Cogen Delivery Station | Redwater Cogen Delivery #2 Station (AP) | 2-440T Turbine Meter | 2018-12-01 | In-Service | 2019-01-01 | Aug 7, 2018 - TTFP Notification Jul 30, 2018 - GRA Application Filed 68 | 1.1
| Receipt Meter Station Expansion | Resthaven Receipt Meter Station Expansion | 2-1280U Ultrasonic Meter | 2018-04-01 | In-Service | 2018-02-27 | May 11, 2017 - TTFP Notification May 26, 2017 - NEB Application Filed 69 | 4.3 | 4.3
| Receipt Meter Station | Rodney Creek Receipt Meter Station | 660-2 Orifice Meter | 2018-08-01 | In-Service | 2018-12-14 | Nov 6, 2017 - TTFP Notification Nov 22, 2017 - NEB Application Filed 70 | 2.2 | 2.2
| Lateral Loop | Saddle Lake Lateral Loop (Cold Lake Section) | 20 km NPS 20 | 2021-11-01 | Approved | 2020-07-17 | Feb 13, 2018 - TTFP Facility Update Aug 23, 2019 - NEB Application Filed 22 | 42 - ROT 65 - Class 4 |  |  |  | 65
| Saddle West Expansion | Saddle West Expansion: Clarkson Valley Control Valve | Control Valve Installation | 2019-06-01 | In-Service | 2019-05-30 | Jul 21, 2017 - TTFP Facility Update Oct 2, 2017 - NEB Application Filed 71 Aug 7, 2018 - Appendix 2 Class Estimate Update | 4.4 4.5 4.3 |  | 4.3
| Saddle West Expansion | Saddle West Expansion: Gordondale Lateral Loop No. 3 | 25 km NPS 36 | 2019-06-01 | In-Service | 2019-01-12 | Dec 5, 2016 - TTFP Notification, 2016 Annual Plan 72 Oct 2, 2017 - NEB Application Filed 71 Aug 7, 2018 - Appendix 2 Class Estimate Update May 7, 2019 - Appendix 2 Update (Estimate at Complete) | 96 - ROT 98 - Class 4 130 - Class 3 134 - EAC |  | 134
| Saddle West Expansion | Saddle West Expansion: Latornell Compressor Station Unit Addition | 30 MW | 2019-06-01 | In-Service | 2019-10-03 | Dec 5, 2016 - TTFP Notification, 2016 Annual Plan 72 Oct 2, 2017 - NEB Application Filed 71 Aug 7, 2018 - Appendix 2 Class Estimate Update Jan 7, 2020 - Appendix 2 Update (Estimate at Complete) | 101 - ROT 118 - Class 4 142 - Class 3 156 - EAC |  | 156 | [5 empty] | Elevated prime contractor costs due to unfavorable market conditions Increased costs associated with vibration issues and brownfield site conditions.
| Saddle West Expansion | Saddle West Expansion: Nordegg Compressor Station Unit Addition | 30 MW | 2019-06-01 | In-Service | 2019-09-14 | Feb 14, 2017 - TTFP Update Jul 21, 2017 - TTFP Facility Update Oct 2, 2017 - NEB Application Filed 71 Aug 7, 2018 - Appendix 2 Class Estimate Update Jan 7, 2020 Appendix 2 Update (Estimate at Complete) | 116 - ROT 112 - ROT 111 - Class 4 139 - Class 3 140 - EAC |  | 140 | [5 empty] | Elevated prime contractor costs due to unfavorable market conditions
| Saddle West Expansion | Saddle West Expansion: Saddle Hills Compressor Station Unit Addition and Control Valve Modifications | 30 MW | 2019-06-01 | In-Service | 2019-10-03 | Dec 5, 2016 - TTFP Presentation, 2016 annual Plan 72 Jun 13, 2017 - TTFP Update Oct 2, 2017 - NEB Application Filed 71 Aug 7, 2018 - Appendix 2 Class Estimate Update Jan 7, 2020 - Appendix 2 Update (Estimate at Complete) | 74 - ROT 119 - Class 5 118 - Class 4 145 - Class 3 173 - EAC |  | 173 | [5 empty] | Elevated prime contractor costs due to unfavorable market conditions Increased costs associated with vibration issues and brownfield site conditions.
| Saddle West Expansion | Saddle West Expansion: Swartz Creek Compressor Station Unit Addition | 30 MW | 2019-06-01 | In-Service | 2019-09-14 | Dec 5, 2016 - TTFP Presentation, 2016 Annual Plan 72 Oct 2, 2017 - NEB Application Filed 71 Aug 7, 2018 - Appendix 2 Class Estimate Update Jan 7, 2020 - Appendix 2 Update (Estimate at Complete) | 116 - ROT 116 - Class 4 142 - Class 3 146 - EAC |  | 146 | [5 empty] | Elevated prime contractor costs due to unfavorable market conditions
| Receipt Meter Station | Saturn No. 2 Receipt Meter Station | 2-1060U-4 Ultrasonic Meter | 2018-04-01 | In-Service | 2018-03-31 | Aug 9, 2017 - TTFP Notification Aug 29, 2017 - NEB Application Filed 73 | 3.8 | 3.8
| Delivery Meter Station | Scotford PDH Delivery Meter Station (AP) | 860T Turbine Meter | 2021-07-13 | Approved |  | May 1, 2018 - TTFP Notification | 2.6 (Includes $1.7M CIAC)
| Sales Meter Station | Sheerness No. 2 Sales Meter Station | 2-1210U Ultrasonic Meter | 2019-11-01 | In-Service | 2019-11-26 | Mar 8, 2019 - TTFP Notification Apr 1, 2019 - NEB Application Filed 74 | 4.2 |  | 4.2
| Lateral Loop | Smoky River Lateral Loop | 10 km NPS24 18 km NPS 24 | 2019-04-01 | In-Service In-Service | Mar 25, 2019 Jun 4, 2019 | Dec 5, 2016 - TTFP Presentation, 2016 Annual Plan 72 Sep 12, 2017 - TTFP Presentation (Scope/Status Update) Nov 29, 2017 - NEB Application Filed 75 Nov 19, 2019 - Appendix 2 Update (Estimate at Complete) | 54 - Class 5 118 - Class 5 91 - Class 4 89 - EAC |  | 89
| Sales Meter Station | Smoky River Sales Meter Station | 660U Ultrasonic Meter | 2020-03-01 | In-Service | 2020-04-29 | Jul 23, 2019 - TTFP Notification Aug 12, 2019 - NEB Application filed 76 | 2.9 |  |  | 2.9
| Pipeline Acquisition | South Airdrie Lateral - Pipeline Acquisition (AP) | 8.7 km NPS 6 | 2021 | Approved |  | Aug 7, 2018 - TTFP Notification Jul 30, 2018 GRA Application Filed 77 Jun 16, 2020 - GRA Application Filed94 | 1.9 1.4
| Installation (AP) | Spruce Grove and Stony Plain UPU – Installation (AP) | 5.4 km NPS 8 3 Delivery Stations | 2022 | Proposed |  | Jun 16, 2020 - GRA Application Filed 94 | 13.2
| Connection Piping | Stoney Transit/North Gate Connection Piping (AP) | 4.3 km NPS 8 | Q1 2019 | In-Service | 2019-03-08 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 May 25, 2018 - AUC Application Filed 78 Oct 14, 2020 - Appendix 2 Update (Estimate at Complete) | 8 15 - EAC
| Receipt Meter Station | Sunchild Receipt Meter Station | 880U-4 Ultrasonic Meter | 2020-04-01 | In-Service | 2020-03-19 | Jun 5, 2019 - TTFP Notification Jul 8, 2019 - NEB Application Filed 79 | 4 |  |  | 4
| Crossover | Sundre Crossover | 20 km NPS 42 | 2018-04-01 | In-Service | 2018-04-08 | Dec 7, 2015 - TTFP Presentation, 2015 Annual Plan 16 May 17, 2016 - TTFP Presentation (Scope Change) Nov 2016 - Appendix 2 Class Estimate Update Mar 24, 2017 - NEB Application Filed 80 Jul 21, 2017 - TTFP Facility Update Oct 14, 2020 - Appendix 2 Update (Estimate at Complete) | 240 - ROT 137 - Class 5 113 - Class 4 99 - Class 3 92 - EAC | 92
| Receipt Meter Station Expansion | Tony Creek No. 2 Receipt Meter Station Expansion | 16164U Ultrasonic Meter | 2019-08-01 | In-Service | 2019-07-23 | Oct 15, 2018 - TTFP Notification Nov 13, 2018 - NEB Application Filed 81 | 6 5.7 |  | 5.7
| Transmission Loop | Turin East Transmission Loop (AP) | 10.5 km NPS 4 | 2018 | In-Service | 2018-01-13 | Aug 16, 2017 - AUC Application filed | 5.6
| Pipeline Replacement | Urban Pipeline Replacement Project: Edmonton UPR – NE Connector (AP) | Control Station | 2021 | Approved |  | Oct 30, 2014 - TTFP Presentation Dec 4, 2018 – AUC Project Update Filed 82 Jun 16, 2020 - AUC Project Update Filed 95 | 11
| Receipt Meter Station Expansion | Valhalla North Receipt Meter Station Expansion | 882 | 2018-10-01 | In-Service | 2018-08-20 | Nov 27, 2017 - TTFP Notification Dec 19, 2017 - NEB Application Filed 83 | 3.1 3.0 | 3
| Compressor Station Unit Addition | Vermillion Compressor Station Unit Addition (AP) | 1 MW | 2021-04-01 | Deferred |  | Feb 13, 2018 - TTFP Facility Update | TBD
| Compressor Station Unit Addition & Coolers | Vetchland Compressor Station Unit Addition & Coolers | 30 MW | TBD | Deferred |  | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan 23 | 145 - ROT 137 - ROT
| West Path Delivery 2022 | West Path Delivery 2022 ABC Border Meter Station Expansion | 5 - NPS 20U Ultrasonic Meters | 2022-11-01 | Applied for | 2020-06-01 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan 32 Jun 1, 2020 - NEB Application Filed 92 | 8 |  |  |  |  | 8
| West Path Delivery 2022 | West Path Delivery 2022 Edson Mainline No. 4 (Raven River) | 18 km NPS 48 | 2022-11-01 | Applied for | 2020-06-01 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan 32 Jun 1, 2020 - NEB Application Filed 92 | 128 - ROT |  |  |  |  | 128
| West Path Delivery 2022 | West Path Delivery 2022 WAML Loop No. 2 (Alberta British Columbia) | 6 km NPS 48 | 2022-11-01 | Applied for | 2020-06-01 | Jan 21, 2020 - TTFP 2019 Annual Plan Update 32 Jun 1, 2020 - NEB Application Filed 92 | 57 - ROT |  |  |  |  | 57
| West Path Delivery 2023 | West Path Delivery 2023 WAML Loop No. 2 (Longview) | 9 km NPS 48 | 2023-11-01 | Applied for | 2020-10-22 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan 32 Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 98 | 65 - ROT 75 - Class 5 | [5 empty] | 75
| West Path Delivery 2023 | West Path Delivery 2023 WAML Loop No. 2 (Lundbreck) | 7 km NPS 48 | 2023-11-01 | Applied for | 2020-10-22 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan 32 Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 98 | 83 - ROT 72 - Class 5 | [5 empty] | 72
| West Path Delivery 2023 | West Path Delivery 2023 WAML Loop No. 2 (Turner Valley) | 24 km NPS 48 | 2023-11-01 | Applied for | 2020-10-22 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan 32 Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 98 | 209 - ROT 209 - Class 5 | [5 empty] | 209
| West Path Delivery Project | West Path Delivery Project: Burton Creek Compressor Station Unit Addition | 30 MW | 2020-06-01 | In Service | 2020-06-22 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Feb 12, 2018 - NEB Application Filed 84 Oct 14, 2020 - Appendix 2 Update (Estimate at Complete) | 116 - ROT 114 - Class 4 167 - EAC |  |  | 167 |  |  |  |  | The increased costs were related to constructability and productivity challenges compounded by site complexity.
| West Path Delivery Project | West Path Delivery Project: Turner Valley Compressor Station Unit Addition | 30 MW | 2020-06-01 | In Service | 2020-04-09 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Feb 12, 2018 - NEB Application Filed 84 Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 132 - ROT 106 - Class 4 101 - EAC |  |  | 101
| West Path Delivery Project | West Path Delivery Project: Western Alberta System Mainline Loop Rocky View Section | 22 km NPS 42 | 2020-06-01 | In-Service | 2020-03-21 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Feb 12, 2018 - NEB Application Filed 84 Aug 11, 2020 - Appendix 2 Update (Estimate at Complete) | 176 - ROT 189 - Class 4 183 - EAC |  |  | 183
| Sales Meter Station | Wiau Lake North Sales Meter Station | 2-640T Turbine Meter | 2019-07-01 | In-Service | 2019-02-08 | May 22, 2018 - TTFP Notification Jun 11, 2018 - NEB Application Filed 85 | 2.4 |  | 2.4
| Receipt Meter Station | Wildrose Receipt Meter Station | 2-2012U Ultrasonic Meter | 2018-05-01 | In-Service | 2018-10-01 | Jul 12, 2017 - TTFP Notification Sep 27, 2017 - NEB Application Filed 86 | 8.3 | 8.3
| Sales Meter Station | Wilkin Lake Sales Meter Station | LVS-4 Turbine Meter | 2018-12-01 | In-Service | 2018-11-15 | Mar 12, 2018 - TTFP Notification Mar 28, 2018 - NEB Application Filed 87 | 2 | 2
| Receipt Meter Station | Wilson Ridge Receipt Meter Station | 10104U Ultrasonic Meter | 2019-02-01 | In-Service | 2019-01-22 | Mar 1, 2018 - TTFP Notification Apr 11, 2018 - NEB Application Filed 88 | 3.9 |  | 3.9
| Compressor Station Unit Addition | Winchell Lake Compressor Station Unit Addition | 30 MW | 2019-11-01 | In-Service | 2019-11-08 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan 11 Mar 8, 2018 - NEB Application Filed 89 Approved Aug 30, 2018 Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 116 - ROT 99 - Class 4 102 - EAC |  | 102
| Receipt Meter Station | Wolf Lake South Receipt Meter Station | 1010-4U Ultrasonic Meter | 2019-09-01 | In-Service | 2019-09-18 | Nov 29, 2018 - TTFP Notification Dec 18, 2018 - NEB Application Filed 90 | 3.8 |  | 3.8
| Compressor Station Unit Addition | Woodenhouse Compressor Station Unit Addition | 30 MW | 2018-11-01 | In-Service | 2018-11-24 | Oct 30, 2014 - TTFP Presentation, 2014 Annual Plan 5 Dec 7, 2015 - TTFP Presentation, 2015 Annual Plan 16 Nov 7, 2016 - NEB Application Filed 91 Feb 2017 - Appendix 2 Class Estimate Update | 136 - Class 5 138 - Class 4 130 - Class 4 | 130
| Transmission Loop | Worsley McLennan Transmission Loop (AP) | 10.7 km NPS 6 | 2017 | In-Service | 2018-03-21 | Aug 2, 2017 - AUC Application Filed Oct 14, 2020 - Appendix 2 Update (Estimate at Complete) | 7.8 9.8 - EAC

## References
References
1 | Application for 2015 Meter Station and Associated Lateral Abandonment
2 | Application for 2015 Meter Station and Associated Lateral Abandonment
3 | 2016 Pipeline Decomissioning NEB Applications Filed
4 | Application for 2017 Meter Station and Associated Lateral Abandonment
5 | NGTL 2014 Annual Plan
6 | 2017 NGTL System Expansion Project Application
7 | 2018 Meter Stations and Laterals Abandonment Program
8 | 2018 Pipeline Decommissioning Program
9 | 2021 NGTL System Expansion Project
10 | Canada Energy Regulator Report for the 2021 NGTL System Expansion Project
11 | NGTL 2017 Annual Plan
12 | Application for the Albersun Pipeline Asset Purchase
13 | Alberta-Montana Border Sales Meter Station Replacement
14 | Application for the construction of Anderson Lake Receipt Meter Station
15 | Bonanza Receipt Meter Station Expansion
16 | NGTL 2015 Annual Plan
17 | Buffalo Creek B3 and Goodfish A2 Compressor Station Unit Additions
18 | Application for Christina Lake North Sales Meter Station Expansion
19 | Clark Lake South Receipt Meter Station
20 | NGTL Clearwater West Expansion Project
21 | Clearwater Compressor Station C7 Unit Addition
22 | Saddle Lake Lateral Loop (Cold Lake Section) Project
23 | NGTL 2018 Annual Plan
24 | Application for the Construction of Cutbank River North Receipt Meter Station
25 | Dawson Creek No. 2 Receipt Meter Station
26 | Dawson Creek East No. 2 Receipt Meter Station
27 | Appication for Dismal Creek North Receipt Meter Station
28 | Dorscheid Receipt Meter Station
29 | Drywood Compressor Station Cooler Addition
30 | Edson Control Valve Addition
31 | Application for the Construction of Edson Mainline Expansion Project
32 | NGTL 2019 Annual Plan
33 | Empress Area Extraction Connections Project
34 | Application for Approval for the Etzikom Abandonment Project
35 | Forestburg Lateral Loop and Forestburg East Sales Meter Station
36 | Gold Creek South Receipt Meter Station Expansion
37 | Gold Creek South Receipt Meter Station No. 2
38 | Gold Creek West Receipt Meter Station
39 | Grace Creek North Receipt Meter Station
40 | McLeod River North Project
41 | Grey Owl Creek North Receipt Meter Station Expansion
42 | Application for the Construction of Groundbirch Mainline Loop (Sunrise Section)
43 | Hythe Lateral Loop No. 2
44 | Ipiatik Lake Sales Meter Station
45 | GRA Application Filed
46 | Livingstone Creek Receipt Meter Station Expansion
47 | Mildred Lake East Sales Meter Station
48 | Minnow Lake West Receipt Meter Station Expansion
49 | North Central Corridor Loop (North Star Section 1)
50 | Application for the Construction of North Corridor Expansion Project
51 | North Heart River Receipt Meter Station
52 | NGTL 2013 Annual Plan
53 | Application for North Montney Project
54 | North Montney Mainlne Project - Application for Variance
55 | Application for the Mackie Creek North Receipt Meter Station
56 | Application for the Altares South Receipt Meter Station
57 | Application for Townsend Receipt Meter Station and Townsend No. 2 Receipt Meter Station
58 | Application for Gundy West Receipt Meter Station
59 | Application for the Old Alaska Receipt Meter Station
60 | Application for Aitken Creek South Receipt Meter Station
61 | Application for Aitken Creek West No. 2 Receipt Meter Station
62 | North Path Delivery Project
63 | Northwest Mainline Loop (Boundary Lake North Section)
64 | Application for the Peace River Mainline Abandonment
65 | Aug 1, 2018 - AUC Application Filed
66 | Nov 30, 2018 - AUC Project Update Filed
67 | Pipestone Creek Receipt Meter Station
68 | Jul 30, 2018 GRA Application Filed
69 | Resthaven Receipt Meter Station Expansion
70 | Rodney Creek Receipt Meter Station
71 | Saddle West Expansion
72 | NGTL 2016 Annual Plan
73 | Saturn No. 2 Receipt Meter Station
74 | Application for the Construction of Sheerness No. 2 Meter Station
75 | Smoky River Lateral Loop
76 | Application for the construction of Smoky River Sales Meter Station
77 | Jul 30, 2018 GRA Application Filed
78 | May 25, 2018 - AUC Application Filed
79 | Sunchild Receipt Meter Station
80 | Application for the Sundre Crossover
81 | Tony Creek No. 2 Receipt Meter Station Expansion
82 | Dec 4, 2018 – AUC Project Update Filed
83 | Valhalla North Receipt Meter Station Expansion
84 | West Path Delivery Project Application
85 | Wiau Lake North Sales Meter Station
86 | Wildrose Receipt Meter Station
87 | Wilkin Lake Sales Meter Station
88 | Wilson Ridge Receipt Meter Station
89 | Application for Winchell Lake Compressor Station Unit Addition
90 | Wolf Lake South Receipt Meter Station
91 | Application for the Woodenhouse Compressor Station C3 Unit Addition
92 | NGTL West Path Delivery 2022 CER
93 | GRA Application Filed
94 | GRA Application Filed
95 | (GRA) AUC Project Update Filed
96 | Gleichen-Cluny GRA Filed
97 | GRA Application Filed
98 | NGTL West Path Delivery 2023 CER
99 | NGTL GBML Loop (Saturn Section) & Saddle Hills CS C4 Unit Addition
100 | ATCO Pioneer AUC Application

## Facility Type Analysis (hidden)
Facility Type | Frequency
Abandonment | 1
Clearwater West Expansion | 4
Cogen Delivery Station | 1
Compressor Station | 1
Compressor Station Coolers | 1
Compressor Station Decomissioning | 1
Compressor Station Modifications | 2
Compressor Station Unit Addition | 4
Compressor Station Unit Addition & Coolers | 2
Connection Piping | 1
Control Valve Addition | 1
Crossover | 1
Delivery Meter Station | 1
Edson Mainline Expansion | 2
Expansion & Lateral Loop | 1
Extraction Connections | 1
Forestburg | 1
Grande Prairie Mainline Loop | 2
Groundbirch Mainline Loop | 1
Lateral Expansion | 1
Lateral Loop | 3
Meter Station & Lateral Abandonment | 4
NGTL System Expansion | 13
North Central Corridor Loop | 1
North Corridor Expansion | 4
North Montney Project | 11
North Path Delivery | 3
Northwest Mainline Loop | 1
Peace River Mainline Abandonment | 1
Pembina-Keephills Transmission Project | 1
Pipeline & Associated Decommissioning | 1
Pipeline Acquisition | 1
Pipeline Asset Purchase | 1
Pipeline Decommissioning | 1
Pipeline Replacement | 1
Pipeline Upgrade | 1
Receipt Meter Station | 15
Receipt Meter Station Expansion | 10
Saddle West Expansion | 6
Sales Meter Station | 8
Sales Meter Station Expansion | 1
Sales Meter Station Replacement | 1
Transmission Loop | 2
West Path Delivery 2022 | 3
West Path Delivery 2023 | 3
West Path Delivery Project | 3

## Forecast Costs (hidden)
Applied-for Facilities | Forecast Cost ($Millions)
Medicine Hat Expansion Medicine Hat and Suffield Lateral Loop
Pioneer Pipeline Asset Purchase (AP)
Hidden Lake North C/S Modifications | 5
Old Alaska No. 2 | 3.4
Scotford PDH Delivery Meter Station (AP)
Grace Creek North Receipt Meter Station | 2
West Path Delivery Project: Burton Creek Compressor Station Unit Addition | 116 - ROT 114 - Class 4 167 - EAC
Keephills Expansion (AP) | 5.8
Mildred Lake East Sales Meter Station
Pipestone Creek Receipt Meter Station | 3.1
West Path Delivery 2023 WAML Loop No. 2 (Lundbreck)
North Corridor Expansion Project: North Central Corridor Loop (North Star Section 2)
Saturn No. 2 Receipt Meter Station | 3.8
Gold Creek South Receipt Meter Station Expansion | 3
Ipiatik Lake Sales Meter Station Modifications | 1.3
Northwest Mainline Loop (Boundary Lake North Section)
Cold Lake Border Sales Meter Station Replacement | 3.2
Cutbank River North Receipt Meter Station | 3.2
Dismal Creek North Receipt Meter Station | 3.2
Dorscheid Receipt Meter Station | 3.2
Grey Owl Creek North Receipt Meter Station Expansion | 3.2
Gold Creek South Receipt Meter Station Expansion No. 2 | 3.5
Dawson Creek No. 2 Receipt Meter Station | 4.4
Saddle West Expansion: Latornell Compressor Station Unit Addition
Wiau Lake North Sales Meter Station | 2.4
West Path Delivery Project: Turner Valley Compressor Station Unit Addition | 132 - ROT 106 - Class 4 101 - EAC
Anderson Lake Receipt Meter Station | 4
Smoky River Lateral Loop
Saddle West Expansion: Saddle Hills Compressor Station Unit Addition and Control Valve Modifications
Pipestone Compressor Station Unit Addition & Coolers
Christina Lake North Sales Meter Station Expansion | 4.4
Clark Lake South Receipt Meter Station | 4.4
Dawson Creek East No. 2 Receipt Meter Station | 3.8
Liza Lake Sales Meter Station | 2.1
Alberta Montana Border Sales Meter Station Replacement | 4.6
Gold Creek West Receipt Meter Station | 4.9
Groundbirch Mainline Loop (Sunrise Section)
Bonanza Receipt Meter Station Expansion | 5.5
2016 Pipeline Decommissioning Program | 5.6
Spruce Grove and Stony Plain UPU – Installation (AP) | 13.2
2015 Meter Station and Associated Lateral Abandonment | 5.8
2016 Meter Station and Associated Lateral Abandonment | 6.7
Wilkin Lake Sales Meter Station | 2
Sheerness No. 2 Sales Meter Station | 4.2
Valhalla North Receipt Meter Station Expansion
West Path Delivery 2023 WAML Loop No. 2 (Turner Valley) | 209 - ROT 209 - Class 5
Farrell Lake CS Modifications | 9.1
Stoney Transit/North Gate Connection Piping (AP)
2017 Meter Stations and Laterals Abandonment Program | 16.4
#REF!
#REF!
Etzikom Abandonment | 18.2
Hythe Lateral Loop No. 2
2017 NGTL System Expansion Project: Northwest Mainline Loop (Boundary Lake Section)
2018 Meter Station and Laterals Abandonment Program
2018 Pipelines and Associated Facilities Decommissioning Program
2021 NGTL System Expansion Project: Beiseker Compressor Station Unit Addition
2021 NGTL System Expansion Project: Didsbury Compressor Station & Coolers
2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Brewster)
2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Dismal Creek)
2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Robb)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Colt Section)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Deep Valley)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Karr)
#REF!
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.3 (Elmworth Section 2 & 3)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.4 (Valhalla)
2021 NGTL System Expansion Project: January Creek Control Valve Addition
2021 NGTL System Expansion Project: Nordegg Compressor Station Unit Addition
Albersun Pipeline Asset Purchase
Berland River Compressor Station Unit Addition
Buffalo Creek Compressor Station Unit Addition
Clearwater Compressor Station Unit Addition & Coolers
Clearwater West Expansion: Clearwater Compressor Station Unit Addition
Clearwater West Expansion: Grande Prairie Mainline Loop No.2 (Huallen)
Clearwater West Expansion: Grande Prairie Mainline Loop No.3 (Elmworth Section 1)
Clearwater West Expansion: Wolf Lake Compressor Station Unit Addition
Cutbank River Lateral Expansion
Drywood Compressor Station Coolers
Edson Control Valve Addition
Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Alford Creek)
Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Elk River)
Emerson Creek Compressor Station
Empress Area Extraction Connections Project
Forestburg Lateral Loop Forestburg East Sales Meter Station
Goodfish Compressor Station Unit Addition
Grande Prairie Mainline Loop No. 2 (McLeod River North Section)
Grande Prairie Mainline Loop No. 4 (Valhalla North Section)
Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Groundbirch Mainline Loop (Saturn Section)
Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Saddle Hills Compressor Station Unit Addition
Gundy West No. 2 | 3.6
Lethbridge Urban Pipeline Upgrade (AP) | 40
Livingstone Creek Receipt Meter Station Expansion | 3.1
Minnow Lake West Receipt Meter Station Expansion | 4.4
Moody Creek Compressor Station Decommissioning | 1
Muriel Creek Sales Meter Station | 2.1
North Central Corridor Loop (North Star Section 1)
North Corridor Expansion Project: Hidden Lake North Compressor Station Unit Addition
North Corridor Expansion Project: North Central Corridor Loop (Red Earth Section 3)
North Corridor Expansion Project: Northwest Mainline Loop No.2 (Bear Canyon North Extension Section)
North Heart River Receipt Meter Station | 2.7
North Montney Project: Aitken Creek Compressor Station
North Montney Project: Groundbirch Compressor Station
North Montney Project: North Montney Mainline (Aitken Creek Section)
North Montney Project: North Montney Mainline (Kahta Section - North)
North Montney Project: North Montney Mainline (Kahta Section - South)
North Montney Project: Saturn Compressor Station Unit 2
#REF!
North Montney Project: Remaining North Montney Mainline Receipt Meter Stations Included in Certificate * Receipt Meter Stations Subject to Variance Application Blair Creek Gundy Kobes Altares Aitken Creek Interconnect (bi-directional storage) New Receipt Meter Stations Mackie Creek North Altares South Townsend Townsend No. 2 Gundy West Old Alaska Aitken Creek South Aitken Creek West No. 2
North Path Delivery Project: Amber Valley Compressor Station Unit Addition
North Path Delivery Project: Meikle River Compressor Station Series Modifications
North Path Delivery Project: Northwest Mainline Loop No. 2 (Bear Canyon North Section)
Peace River Mainline Abandonment (Meikle River to Valleyview Section)
Pembina-Keephills Transmission Project (AP)
Prairie Creek Receipt Meter Station Expansion | 1.3
Princess Compressor Station Unit Addition & Coolers
Redwater Cogen Delivery #2 Station (AP) | 1.1
Resthaven Receipt Meter Station Expansion | 4.3
Rodney Creek Receipt Meter Station | 2.2
Saddle Lake Lateral Loop (Cold Lake Section)
Saddle West Expansion: Clarkson Valley Control Valve
Saddle West Expansion: Gordondale Lateral Loop No. 3
Saddle West Expansion: Nordegg Compressor Station Unit Addition
Saddle West Expansion: Swartz Creek Compressor Station Unit Addition
Smoky River Sales Meter Station | 2.9
South Airdrie Lateral - Pipeline Acquisition (AP)
Sunchild Receipt Meter Station | 4
Sundre Crossover
Tony Creek No. 2 Receipt Meter Station Expansion
Turin East Transmission Loop (AP) | 5.6
Urban Pipeline Replacement Project: Edmonton UPR – NE Connector (AP) | 11
Vermillion Compressor Station Unit Addition (AP)
Vetchland Compressor Station Unit Addition & Coolers
West Path Delivery 2022 ABC Border Meter Station Expansion
West Path Delivery 2022 Edson Mainline No. 4 (Raven River)
West Path Delivery 2022 WAML Loop No. 2 (Alberta British Columbia)
West Path Delivery 2023 WAML Loop No. 2 (Longview)
West Path Delivery Project: Western Alberta System Mainline Loop Rocky View Section
Wildrose Receipt Meter Station