## Summary & Notes
The Facility Status Update describes the current status of facilities that were applied for, are under construction or have been placed on-stream since the 2021 Annual Plan was issued on December 17, 2021 and maintains a record of the facilities for two years prior to the current year. Periodic updates are being provided based on the level of activity occurring with respect to facilities. Facilities with (AP) after the project name refer to facilities in the ATCO Pipelines footprint.
| Summary: | 2019 | 2020 | 2021 | 2022 | 2023 | 2024+
| Total Costs by In-Service Year * | 3205.4 | 1892.9 | 3707.2 | 714.5 | 1315 | 876
Forecast Costs For NGTL projects greater than $25 million, the estimate type for the forecasted costs have been provided. The typical expected accuracy for the various estimate types are shown in the table below. These accuracy ranges are for projects with established technological complexity and can be greater depending on area knowledge, technological complexity, level of expertise, and certainty of facility scope. Forecasted costs reflect the dollar value, economic conditions, and estimation procedures at the time the estimates were completed.
Total Costs by In-Service Total Costs by In-Service Year are a summation of the last provided costs of all NGTL capacity capital projects with expected or realized in-service dates within a calendar year. Costs for non NGTL capacity capital projects, such as ATCO Pipelines, CIAC, decommissioning or abandonment projects, are excluded. These annual summations of costs will not match other regulatory filings with different costs bases. Variance Explanation Variance explanations are provided for all NGTL capacity capital projects with EAC costs equal to or greater than $25 million with a variance greater than 10% between the EAC and applied-for costs.
North Montney Project The North Montney Project was filed as a Section 52 application on November 8, 2013 comprised of the following facilities: North Montney Mainline (Aitken Creek Section), North Montney Mainline (Kahta Section), Aitken Creek Compressor Station, Saturn Compressor Station, Groundbirch Compressor Station, 14 receipt meter stations, a bi-directional storage meter station (Aitken Creek Interconnect) and a delivery meter station (Mackie Creek Interconnection). The NMML Variance was filed March 20, 2017 to vary Condition 4 in the Certificate and Order and to extend the Sunset Clause for the NMML. The Variance also includes the details on eight additional meter stations required for the new receipt contracts. North Montney costs are escalated to the year of in-service for each respective facility. The original Kahta Section was 119 km of NPS 42 with a ROM cost estimate of $530Million. Variance Application NEB Approval Order Received May 23, 2018. Mackie Creek North and Blair Creek receipt meter stations are currently under construction.
Northwest Mainline Loop (Bear Canyon North Section) Northwest Mainline Loop No. 2 (Bear Canyon North Section) is the combination of two previously presented facilities; Northwest Mainline Loop No. 2 (Bear Canyon North Section) and the Northwest Mainline Loop (Peace River Crossing Project). West Path Delivery Project: Turner Valley Compressor Station Unit Addition 7 Turner Valley Compressor Station Coolers has been combined with Turner Valley Compressor Station Unit Addition.
Disclaimer The information provided in this document has been prepared to the best of management’s ability. TC does not represent or warrant that the information contained herein is accurate and complete in all respects or is fit for any purpose. Any of use of the information in its current or any manipulated form is the sole responsibility of the user. TC Energy is not responsible for any changes made to downloaded copies and/or results in data compiled, assumptions, and actions resulting from those changes. NGTL can only support use of the official PDF version as posted on TC Customer Express.

## Facilities Update
Report Updates | Facility Category | Applied-for Facilities | Description | Target In-Service Date | Status | Date of Status | References * | Forecast Cost * ($Millions) | 2019 | 2020 | 2021 | 2022 | 2023 | 2024+ | Variance Explanation
| Meter Station & Lateral Abandonment | 2016 Meter Station and Associated Lateral Abandonment | Coleman Enchant Grew Lake Grew Lake East Hotchkiss Hotchkiss East Meanook Rambling Creek East Sharrow South No.2 Steele Lake | Q3 2017 to Q1 2018 | Complete | 2019-06-01 | Nov 1, 2016 - TTFP Notification Dec 13, 2016 - NEB Application Filed 1 | 6.7
| Pipeline Decommissioning | 2016 Pipeline Decommissioning Program | Crossfield Lat Lp Mitsue Lat Lp Big Bend Lat Ricinus Lat Sedalia North Lat Tangent Lat (Tangent M/S) Atmore Lat (Atmore M/S) Bassano South Lateral | Q3 2017 to Q4 2019 | Complete | 2019-08-01 | Dec 19, 2016 - TTFP Notification Jan 23, 2017 - NEB Application Filed 2 | 5.6
| Meter Station & Lateral Abandonment | 2017 Meter Stations and Laterals Abandonment Program | Meter Stations w/Laterals Acadia East Acadia North Acadia Valley Bear Canyon West Big Bend East Blueberry Hill Blue Jay Donatville Hines Creek Hines Creek West Last Lake Lawrence Lake Manir Mills Tangent East Stand-Alone Meters Elinor Lake East Mega River Mega River No. 2 Rod Lake Rod Lake Sales Rossbear Lake Snowfall Creek Squirrel Mountain Owl Lake South Owl Lake South No. 2 Owl Lake South No. 3 Stand-Alone Laterals Alderson Lateral Kaybob South Lateral McNeill X-Over | Q1 2021 | Complete | 2021-03-01 | Jun 29, 2017 - TTFP Notification Aug 21, 2017 - NEB Application Filed 3 | 16.4
| Meter Station & Lateral Abandonment | 2018 Meter Station and Laterals Abandonment Program | Meter Stations w/Laterals AECO A AECO I Andrew Chard Donnelly Esther Border Meadow Creek Mons Lake Mons Lake East Princess South Retlaw Rock Island Lake Rumsey West Saddle Lake West West Viking Stand-Alone Meter Stations Rock Island Lake South No. 2 Stand-Alone Laterals Boundary Lake South Flat Lake Lateral Ext. Marten Hills White Earth Creek | Q3 2022 | Under Construction |  | Aug 16, 2018 - TTFP Notification Sept 28, 2018 - NEB Application filed 4 | 17.9 18.1
| Pipeline & Associated Decommissioning | 2018 Pipelines and Associated Facilities Decommissioning Program | Pipeline Laterals Baxter Lake Calling Lake East Calling Lake South East Lat Loop Edgerton Flat Lake Lat Loop Flat Lake Lat Ext Judy Creek Sales North Lat Ext Loop Wainwright Wapiti Zama Lake Associated Facilities Edgerton Rec Judy Creek Sales Zama Lake No. 1 Rec Zama Lake No. 2 Rec Wapiti Rec PTI 360m Cross-over | Q4 2022 | Under Construction |  | Nov 14, 2018 - TTFP Notification Dec 7, 2018 - TTFP Notification Update Dec 18, 2018 - NEB Application Filed 5 | 14.3 28 - Class 5
| NGTL System Expansion | 2021 NGTL System Expansion Project: Beiseker Compressor Station Unit Addition | 30 MW | Apr 2021 - Apr 2022 | In-service | 2021-09-30 | Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 6 Feb 19, 2020 - CER Recommendation 7 Sep 8, 2020 - Facility Status Class Estimate Update | 120 - ROM 116 - Class 5 164 - Class 3 |  |  | 164 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Didsbury Compressor Station & Coolers | 30 MW | Apr 2021 - Apr 2022 | In-service | 2021-09-22 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 6 Feb 19, 2020 - CER Recommendation 7 Sep 8, 2020 - Facility Status Class Estimate Update | 166 - ROM 116 - Class 5 153 - Class 3 |  |  | 153
| NGTL System Expansion | 2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Brewster) | 49 km NPS 48 | Apr 2021 - Apr 2022 | Under Construction | Q1 2021 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 6 Feb 19, 2020 - CER Recommendation 7 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate | 270 - ROM 287 - Class 5 315 - Class 3 378 - Class 3 |  |  | 378 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Dismal Creek) | 32 km NPS 48 | Apr 2021 - Apr 2022 | Under Construction | Q1 2021 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 6 Feb 19, 2020 - CER Recommendation 7 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate | 156 - ROM 179 - Class 5 285 - Class 3 375 - Class 3 |  |  | 375 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Robb) | 42 km NPS 48 | Apr 2021 - Apr 2022 | Under Construction | Q1 2021 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 6 Feb 19, 2020 - CER Recommendation 7 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate | 232 - ROM 232 - Class 5 274 - Class 3 378 - Class 3 |  |  | 378 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Colt Section) | 14 km NPS 48 | Apr 2021 - Apr 2022 | Under Construction | Q1 2021 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 6 Feb 19, 2020 - CER Recommendation 7 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate | 73 - ROM 80 - Class 5 117 - Class 3 134 - Class 3 |  |  | 134 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Deep Valley) | 69 km NPS 48 | Apr 2021 - Apr 2022 | Under Construction | Q1 2021 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 6 Feb 19, 2020 - CER Recommendation 7 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate | 332 - ROM 377 - Class 5 530 - Class 3 665 - Class 3 |  |  | 665 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Karr) | 57 km NPS 48 | Apr 2021 - Apr 2022 | Under Construction | Q1 2021 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 13, 2018 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 6 Feb 19, 2020 - CER Recommendation 7 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate | 298 - ROM 327 - Class 5 409 - Class 3 454 - Class 3 |  |  | 454 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
In-Service | NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.3 (Elmworth Section 2 & 3) | 44 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2021-11-10 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 6 Feb 19, 2020 - CER Recommendation 7 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate | 283 - ROM 283 - Class 5 328 - Class 3 357 - Class 3 |  |  | 357 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
In-Service | NGTL System Expansion | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.4 (Valhalla) | 36 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2021-11-25 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 6 Feb 19, 2020 - CER Recommendation 7 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate | 152 - ROM 187 - Class 5 235 - Class 3 228 - Class 3 |  |  | 228 |  |  |  | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| NGTL System Expansion | 2021 NGTL System Expansion Project: January Creek Control Valve Addition | Control Valve Addition | Apr 2021 - Apr 2022 | In-service | Q1 2021 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 6 Feb 19, 2020 – CER Recommendation 7 Sep 8, 2020 - Facility Status Class Estimate Update | 5 5 4 - Class 3 |  |  | 4
EAC | NGTL System Expansion | 2021 NGTL System Expansion Project: Nordegg Compressor Station Unit Addition | 30 MW | Apr 2021 - Apr 2022 | In-service | 2021-08-18 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 6 Feb 19, 2020 – CER Recommendation 7 Sep 8, 2020 - Facility Status Class Estimate Update Nov 18, 2021 - Facility Status Update (Estimate at Complete) | 145 - ROM 119 - Class 5 149 - Class 3 143 - EAC |  |  | 143
| Delivery Meter Station | Alberta Montana Border Sales Meter Station Replacement | 2-1280U Ultrasonic Meter | 2020-07-01 | In-Service | 2020-06-29 | Sep 18, 2019 - TTFP Notification Oct 3, 2019 - CER Application Filed 8 | 4.6 |  | 4.6
| Receipt Meter Station | Anderson Lake Receipt Meter Station | 10104U Ultrasonic Meter | 2020-09-01 | In-Service | 2020-07-17 | Oct 8, 2019 - TTFP Notification Oct 22, 2019 - CER Application Filed9 | 4 |  | 4
| Compressor Station Unit Addition | Berland River Compressor Station Unit Addition | 30 MW | TBD | Deferred |  | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v | 145 - ROM
Proposed | Compressor Station Unit Addition | Berland River Compressor Station Unit and Coolers Addition | 30 MW | 2026-04-01 | Proposed | 2021-12-06 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix | 166 - ROM | [5 empty] | 166
| Compressor Station Unit Addition | Buffalo Creek Compressor Station Unit Addition | 30 MW | 2020-11-01 | In-Service | 2020-11-24 | Dec 7, 2015 - TTFP Presentation, 2015 Annual Plan iii Aug 16, 2016 - TTFP Presentation (Status Update/Deferral) Dec 4, 2017 - TTFP Presentation (Status Update), 2017 Annual Plan v Oct 1, 2018 - NEB Application Filed 10 Jan 22, 2021 - Appendix 2 Update (Estimate at Complete) | 139 - ROM 159 - Class 4 187 - EAC |  | 187 |  |  |  |  | Costs for the access road construction and overall prime cost increase resulted in the increased costs for the project.
Approved | Receipt Meter Station | Chambers Creek Receipt Meter Station | 860U-4 | 2022-04-01 | Approved | 2021-11-25 | May 25, 2021 - TTFP Notification Jun 16, 2021 - CER Application Filed78 | 4 |  |  |  | 4
| Receipt Meter Station | Clark Lake South Receipt Meter Station | 1010-4U Ultrasonic Meter | 2019-06-01 | In-Service | 2019-05-31 | Aug 13, 2018 - TTFP Notification Sep 4, 2018 - NEB Application Filed 11 | 4.4 | 4.4
| 2021 Clearwater Unit Addition | Clearwater Compressor Station Unit Addition & Coolers | 30 MW | 2021-11-01 | In-Service | 2021-11-01 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jul 20, 2018 - TTFP Update Sep 26, 2018 - CER Application Filed 13 | 145 - ROM 128 - Class 5 |  |  | 128
| Clearwater West Expansion | Clearwater West Expansion: Clearwater Compressor Station Unit Addition | 30 MW | 2020-04-01 | In-Service | 2020-04-04 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 4, 2018 - NEB Application Filed 12 Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 117 - ROM 118 - Class 4 144 - EAC |  | 144 |  |  |  |  | Elevated prime contractor costs due to unfavourable market conditions
| Clearwater West Expansion | Clearwater West Expansion: Grande Prairie Mainline Loop No.2 (Huallen) | 13 km NPS 48 | 2020-04-01 | In-Service | 2020-03-19 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 4, 2018 - NEB Application Filed 12 Aug 11, 2020 - Appendix 2 Update (Estimate at Complete) | 59 - ROM 77 - Class 4 84 - EAC |  | 84
| Clearwater West Expansion | Clearwater West Expansion: Grande Prairie Mainline Loop No.3 (Elmworth Section 1) | 24 km NPS 48 | 2020-04-01 | In-Service | 2020-05-30 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 4, 2018 - NEB Application Filed 12 Nov 10, 2020 - Facility Status Update (Estimate at Complete) | 150 - ROM 130 - Class 4 161 - EAC |  | 161 |  |  |  |  | Unfavourable construction conditions.
| Clearwater West Expansion | Clearwater West Expansion: Wolf Lake Compressor Station Unit Addition | 30 MW | 2020-04-01 | In-Service | 2020-04-25 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 4, 2018 - NEB Application Filed 12 Aug 11, 2020 - Appendix 2 Update (Estimate at Complete) | 111 - ROM 126 - Class 4 155 - EAC |  | 155 |  |  |  |  | Elevated prime contractor costs due to unfavourable market conditions.
| Delivery Meter Station Replacement | Cold Lake Border Sales Meter Station Replacement | 1010U Ultrasonic Meter | 2021-11-01 | In-Service | 2021-07-07 | Aug 9, 2019 - TTFP Notification Aug 23, 2019 - NEB Application Filed 14 | 3.2 |  |  | 3.2
| Receipt Meter Station | Cutbank River North Receipt Meter Station | 660U-2 Ultrasonic Meter | 2020-04-01 | In-Service | 2020-03-31 | May 22, 2019 - TTFP Notification Jun 25, 2019 - NEB Application Filed 15 | 3.2 |  | 3.2
| Receipt Meter Station | Dawson Creek East No. 2 Receipt Meter Station | 662U Ultrasonic Meter | 2020-07-01 | In-Service | 2020-06-12 | Sep 20, 2019 - TTFP Notification Oct 8, 2019 - CER Application Filed 17 | 3.8 |  | 3.8
| Receipt Meter Station | Dawson Creek No. 2 Receipt Meter Station | 10104U | 2020-10-01 | In-Service | 2020-10-27 | Dec 2, 2019 - TTFP Notification Dec 18, 2019 - CER Application Filed 16 | 4.4 |  | 4.4
| Receipt Meter Station | Dorscheid Receipt Meter Station | 662U Ultrasonic Meter | 2019-12-01 | In-Service | 2019-12-05 | Jan 16, 2019 - TTFP Notification Feb 26, 2019 - NEB Application Filed 18 | 3.2 | 3.2
| Control Valve Addition | Edson Control Valve Addition | Control Valve Installation | 2019-04-01 | In-Service | 2019-05-05 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v May 29, 2018 - NEB Application Filed 19 | 5 6.7 | 6.7
| Edson Mainline Expansion | Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Alford Creek) | 45 km NPS 48 | 2022-11-01 | Approved | 2021-06-18 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 3, 2019 - NEB Application Filed 20 June 18, 2021 - CER Approval79 | 269 - ROM 269 - Class 5 |  |  |  | 269
| Edson Mainline Expansion | Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Elk River) | 40 km NPS 48 | 2022-11-01 | Approved | 2021-06-18 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 3, 2019 - NEB Application Filed 20 June 18, 2021 - CER Approval79 | 240 - ROM 240 - Class 5 |  |  |  | 240
| Compressor Station | Emerson Creek Compressor Station | 2-30 MW Units | 2024-04-01 | Applied for | 2021-06-01 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii June 1, 2021 - CER Application Filed 77 | 257 - ROM 278 - Class 5 | [5 empty] | 278
| Abandonment | Etzikom Abandonment | 84 km NPS 10/6 | Q4 2019 | Denied | 2020-05-20 | Oct 3, 2018 - TTFP Notification Oct 31, 2018 - NEB Application Filed 21 | 18.2
| Lateral Loop & Delivery Meter Station | Forestburg Lateral Loop Forestburg East Sales Meter Station | 8.2 km NPS10 2-1080U Ultrasonic Meter | Q4 2019 | In-Service In-Service | Nov 7, 2019 Nov 9, 2019 | Oct 10, 2018 - TTFP Notification Nov 8, 2018 - NEB Application Filed 22 | 21.5 21.8 | 21.8
| Lateral Loop | Gleichen-Cluny Transmission Looping – Installation (AP) | 2.4 km NPS 3 2.0 km NPS 3 | 2021 | Approved | 2021-03-18 | Jun 16, 2020 – GRA Application Filed 65 Mar 1, 2021 - GRA Application Approved 73 | 2.7
| Receipt Meter Station Expansion | Gold Creek South Receipt Meter Station Expansion No. 2 | 10104U Ultrasonic Meter | 2019-07-01 | In-Service | 2019-12-06 | Oct 26, 2018 - TTFP Notification Nov 14, 2018 - NEB Application Filed 23 | 3.5 | 3.5
| Receipt Meter Station | Gold Creek West Receipt Meter Station | 12124U Ultrasonic Meter | 2019-04-01 | In-Service | 2019-01-21 | Apr 6, 2018 - TTFP Notification Apr 30, 2018 - NEB Application Filed 24 | 4.9 | 4.9
| Compressor Station Unit Addition | Goodfish Compressor Station Unit Addition | 30 MW | 2020-11-01 | In-Service | 2020-10-31 | Feb 13, 2018 - TTFP Facility Update Oct 1, 2018 - NEB Application Filed 10 Jan 22, 2021 - Appendix 2 Update (Estimate at Complete) | 120 - ROM 115 - Class 4 121 - EAC |  | 121
| Grande Prairie Mainline Loop | Grande Prairie Mainline Loop No. 2 (McLeod River North Section) | 35 km NPS 48 | 2019-11-01 | In-Service | 2020-04-08 | Jul 21, 2017 - TTFP Facility Update Nov 14, 2017 - TTFP Facility Update Jun 20, 2018 - NEB Application Filed 25 Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 108 - ROM 155 - ROM 237 - Class 4 317 - EAC | 317 | [5 empty] | Cost increase related to unseasonably wet weather which impacted field productivity rate, significant spending on procurement/deployment of matting, as well as complications on the Wildhay and Athabasca HDD.
| Grande Prairie Mainline Loop | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) | 33 km NPS 48 | TBD | Cancelled | 2021-05-07 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii | 204 - ROM
Proposed | Pipe Looping | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) | 33km NPS 48 | 2026-04-01 | Proposed | 2021-12-06 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix | 281 - ROM | [5 empty] | 281
| Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition | Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Groundbirch Mainline Loop (Saturn Section) | 24 km NPS 42 | 2023-04-01 | Approved | 2021-05-13 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Nov 5, 2020 - CER Application Filed 68 May, 13, 2021 - CER Approval76 | 143 - ROM 140 - Class 5 |  |  |  |  | 140
2024-04-01 | Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition | Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Saddle Hills Compressor Station Unit Addition | 30 MW | 2024-04-01 | Approved | 2021-05-13 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Nov 5, 2020 - CER Application Filed 68 May, 13, 2021 - CER Approval76 | 159 - ROM 151 - Class 5 | [5 empty] | 151
| Groundbirch Mainline Loop | Groundbirch Mainline Loop (Sunrise Section) | 24 km NPS 42 | 2023-04-01 | Approved | 2019-10-24 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Oct 3, 2018 - TTFP Facility Update Apr 29, 2019 - NEB Application Filed 26 | 107 - ROM 155 - ROM 135 - ROM 140 - Class 4 |  |  |  |  | 140
| North Montney Project | Gundy West No. 2 | 880U Ultrasonic Meter | 2021-11-21 | In-Service | 2021-10-25 | Nov 30, 2020 - TTFP Notification Jan 12, 2021 - CER Application Filed 70 | 3.6 |  |  | 3.6
Approved | Compressor Station Coolers | Hidden Lake & Hidden Lake North Station Coolers | Coolers | 2023-04-01 | Approved | 2021-12-10 | Dec 7, 2020 - TTFP Notification Jun 22, 2021 - CER Application Filed 80 Dec 10, 2021 - CER Approval 84 | 45 - ROM 47 - Class 4 |  |  |  |  | 47
Proposed | Pipe Looping | Inland Looping (AP) | 9km NPS 36 | 2024-04-01 | Proposed | 2021-12-06 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix | 40 - ROM
| Keephills Expansion | Keephills Expansion (AP) | Control Station Meter Station | 2021 | In-Service | 2021-04-22 | Jun 16, 2020 - GRA Application Filed 62 Mar 1, 2021 - GRA Application Approved 73 | 5.8
| Pipeline Upgrade | Lethbridge Urban Pipeline Upgrade (AP) | 10.8 km NPS 8 2.4 km NPS 6 Control Station 3 Delivery Stations | 2022 | Approved |  | Aug 7, 2018 - TTFP Notification Jul 30, 2018 - GRA Application Filed 27 Jun 16, 2020 - GRA Application Filed 66 Mar 1, 2021 - GRA Application Approved 73 | 40
EAC | North Montney Project | Mackie Creek North Altares South Townsend Townsend No. 2 Gundy West Old Alaska Aitken Creek South Aitken Creek West No. 2 | 662 Orifice Meter 882 Orifice Meter 882 Orifice Meter 882 Orifice Meter 882 Orifice Meter 882 Orifice Meter 2-1284U Ultrasonic 442 Orifice Meter | Sep 2019 Sep 2019 Sep 2019 Sep 2019 Sep 2019 Sep 2019 Sep 2019 Apr 2020 | ISD Feb 7, 2020 ISD Jan 31, 2020 ISD Jan 31, 2020 ISD Jan 31, 2020 ISD Jan 31, 2020 ISD Jan 31, 2020 ISD Jan 31, 2020 ISD Apr 27, 2020 | 2021-11-18 | NEB Applications Filed Link to Application 33 Link to Application 34 Link to Application 35 Link to Application 35 Link to Application 36 Link to Application 37 Link to Application 38 Link to Application 39 Nov 18, 2021 - Facility Status Update (Estimate at Complete) | 28 - ROM 30 - EAC |  | 30
| Delivery Meter Station | McLeod River Sales Meter Station | 860U Ultrasonic Meter | 2022-10-01 | Applied for | 2021-10-26 | Oct 12, 2021 - TTFP Notification Oct 26, 2021 - CER Application Filed 83 | 4 |  |  |  | 4
| Expansion & Lateral Loop | Medicine Hat Expansion Medicine Hat and Suffield Lateral Loop | 58 km NPS 24 | N/A | Cancelled |  | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii | 189 - ROM |  |  |  |  | 0
| Delivery Meter Station | Mildred Lake East Sales Meter Station | 660U Ultrasonic Meter | 2019-09-01 | In-Service | 2019-12-06 | Nov 30, 2018 - TTFP Notification Feb 13, 2019 - TTFP Notification Amendment Feb 14, 2019 - NEB Application Filed 28 | 3.2 4.1 | 4.1
| Compressor Station Decomissioning | Moody Creek Compressor Station Decommissioning | Station decommissioning, and equipment transfer to Saturn Compressor Station | 2019-12-01 | Complete | 2019-10-02 | Apr 4, 2019 - TTFP Notification | 1 | 1
| Delivery Meter Station | Muriel Creek Sales Meter Station | NPS 3 Positive Displacement Meter | 2019-03-01 | In-Service | 2019-03-01 | Jul 16, 2018 - TTFP Notification Aug 9, 2018 - TTFP Facility Update (Streamlining Order) | 2.1 | 2.1
| North Central Corridor Loop | North Central Corridor Loop (North Star Section 1) | 31 km NPS 48 | 2020-04-01 | In-Service | 2020-04-09 | Dec 7, 2015 - TTFP Presentation, 2015 Annual Plan iii Aug 16, 2016 - TTFP Presentation (Status Update/Deferral) Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Oct 30, 2018 - NEB Application Filed 29 Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 200 - ROM 193 - ROM 170 - Class 4 165 - EAC |  | 165
| North Corridor Expansion | North Corridor Expansion Project: Hidden Lake North Compressor Station Unit Addition | 30 MW | 2023-04-01 | Approved | 2021-05-05 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 30 May 5, 2021 - CER Approval75 | 138 - ROM 138 - Class 5 |  |  |  |  | 138
| North Corridor Expansion | North Corridor Expansion Project: North Central Corridor Loop (North Star Section 2) | 24 km NPS 48 | 2023-04-01 | Approved | 2021-05-05 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 30 May 5, 2021 - CER Approval75 | 155 - ROM 155 - Class 5 |  |  |  |  | 155
| North Corridor Expansion | North Corridor Expansion Project: North Central Corridor Loop (Red Earth Section 3) | 32 km NPS 48 | 2023-04-01 | Approved | 2021-05-05 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 30 May 5, 2021 - CER Approval75 | 205 - ROM 205 - Class 5 |  |  |  |  | 205
| North Corridor Expansion | North Corridor Expansion Project: Northwest Mainline Loop No.2 (Bear Canyon North Extension Section) | 25 km NPS 36 | 2023-04-01 | Approved | 2021-05-05 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 30 May 5, 2021 - CER Approval75 | 134 - ROM 134 - Class 5 |  |  |  |  | 134
| North Montney Project | North Montney Project: Aitken Creek Compressor Station | 15 MW Bi-directional | TBD | Deferred |  | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan i Nov 8, 2013 - NEB Application Filed 31 Mar 20, 2017 - NEB Variance Application 32 | 72 - ROM 98 - Class 4
| North Montney Project | North Montney Project: Groundbirch Compressor Station | 2-15 MW Units Bi-directional | 2019-11-01 | In-Service | 2019-10-25 | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan i Nov 8, 2013 - NEB Application Filed 31 Mar 20, 2017 - NEB Variance Application 32 Aug 7, 2018 - Appendix 2 Class Estimate Update Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 103 - ROM 135 - Class 4 131 - Class 3 110 - EAC | 110 | [5 empty] | Lower construction costs due to execution efficiencies, improved equipment costs, and risk mitigation
| North Montney Project | North Montney Project: North Montney Mainline (Aitken Creek Section) | 182 km NPS 42 | 2019-09-01 | In-Service | 2020-01-31 | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan i Nov 8, 2013 - NEB Application Filed 31 Mar 20, 2017 - NEB Variance Application 32 Aug 7, 2018 - Appendix 2 Class Estimate Update Apr 7, 2020 - Appendix 2 Update (Estimate at Complete) | 762 - ROM 930 - Class 4 1,270 - Class 3 1,400 - EAC | 1400 | [5 empty] | Elevated prime contractor costs due to unfavorable market conditions as well as complications on the Peace River HDD
| North Montney Project | North Montney Project: North Montney Mainline (Kahta Section - North) | 95 km NPS 42 | TBD | Deferred |  | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan i Nov 8, 2013 - NEB Application Filed 31 Mar 20, 2017 - NEB Variance Application 32 | 331 - Class 4
| North Montney Project | North Montney Project: North Montney Mainline (Kahta Section - South) | 24 km NPS 42 | 2020-04-01 | In-Service | 2020-05-01 | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan i Nov 8, 2013 - NEB Application Filed 31 Mar 20, 2017 - NEB Variance Application 32 Aug 7, 2018 - Appendix 2 Class Estimate Update Aug 11, 2020 - Appendix 2 Update (Estimate at Complete) | 174 - Class 4 196 - Class 4 204 - EAC |  | 204 |  |  |  |  | Elevated prime contractor costs due to unfavorable market conditions
| North Montney Project | North Montney Project: Saturn Compressor Station Unit 2 | 15 MW Bi-directional | TBD | Deferred |  | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan i Nov 8, 2013 - NEB Application Filed 31 Mar 20, 2017 - NEB Variance Application 32 | 63 - ROM
| North Montney Project | North Montney Project: Saturn Compressor Station | 15 MW Bi-directional | 2020-04-01 | In-Service | 2020-04-10 | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan i Nov 8, 2013 - NEB Application Filed 31 Mar 20, 2017 - NEB Variance Application 32 Aug 7, 2018 - Appendix 2 Class Estimate Update Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 70 - ROM 86 - Class 4 94 - Class 4 74 - EAC |  | 74 |  |  |  |  | Lower costs due to repurposing of existing assets as well as execution efficiencies
| North Path Delivery | North Path Delivery Project: Amber Valley Compressor Station Unit Addition | 15 MW | 2019-11-01 | In-Service | 2020-03-05 | Mar 14, 2017 - TTFP Update Jun 13, 2017 - TTFP Update Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 16, 2018 - NEB Application Filed 40 Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 100 - ROM 89 - ROM 81 - Class 4 100 - EAC | 100 | [5 empty] | Prime change orders, internal costs, and project schedule changes due to weather delays, piping alignment challenges, hydROMest delays and new Contractor onboarding resulted in increased costs for the project
| North Path Delivery | North Path Delivery Project: Meikle River Compressor Station Series Modifications | Modifications to Enable Series Operation | Q2 2020 | In-Service | 2020-06-11 | Dec 7, 2015 - TTFP Presentation, 2015 Annual Plan iii Aug 16, 2016 - TTFP Presentation (Status Update/Deferral) Mar 14, 2017 - TTFP Update Jun 13, 2017 - TTFP Update Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 16, 2018 - NEB Application Filed 40 Sep 8, 2020 - Facility Status Update (Estimate at Complete) | 16 17 17 52 - EAC |  | 52 |  |  |  |  | Unanticipated complexities associated with brownfield site. Wildfire activity impacted cost and execution plans.
| North Path Delivery | North Path Delivery Project: Northwest Mainline Loop No. 2 (Bear Canyon North Section) | 28 km NPS 36 | 2019-11-01 | In-Service | 2019-09-25 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 16, 2018 - NEB Application Filed 40 Jan 2020 Appendix 2 Update (Estimate at Complete) | 99 - ROM 109 - Class 4 109 - Class 4 160 - EAC | 160 | [5 empty] | Elevated prime contractor costs due to unfavorable market conditions. Stopple bypass required to complete tie-in of new section increased costs and delayed in-service
| Northwest Mainline Loop | Northwest Mainline Loop (Boundary Lake North Section) | 23 km NPS 36 | 2019-04-01 | In-Service | 2019-03-23 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Dec 15, 2017 - NEB Application Filed 41 Jun 4, 2019 Appendix 2 Update (Estimate at Complete) | 115 - ROM 105 - Class 4 98 - EAC | 98
| North Montney Project | Old Alaska No. 2 | 660-2U Ultrasonic Meter | 2021-11-21 | In-Service | 2021-10-25 | Nov 30, 2020 - TTFP Notification Jan 14, 2021 - CER Application Filed 71 | 3.4 |  |  | 3.4
| Peace River Mainline Abandonment | Peace River Mainline Abandonment (Meikle River to Valleyview Section) | 266 km NPS 20 2.3 km NPS 4 | 2020-12-01 | Complete | 2020-10-23 | Oct 22, 2013 - TTFP Presentation, 2013 Annual Plan i Oct 30, 2014 - TTFP Presentation, 2014 Annual Plan ii Jul 22, 2016 - TTFP Presentation (Filing/Scope Change) Aug 18, 2016 - NEB Application Filed 42 | 30 - Class 4
| Pembina-Keephills Transmission Project | Pembina-Keephills Transmission Project (AP) | 58 km NPS 30 | 2020-04-01 | In-Service | 2020-04-01 | May 8, 2018 - TTFP Notification Aug 1, 2018 - AUC Application Filed 43 Nov 30, 2018 - AUC Project Update Filed 44 Oct 14, 2020 - Appendix 2 Update (Estimate at Complete) | 155 157 230 230 - EAC
In-Service | Interconnect | Pioneer Interconnect | Interconnect | 2021-08-01 | In-Service | 2021-11-05 | Feb 9, 2021 - TTFP Notification Sep 17, 2021 - Streamlining Order Notification | 2 |  |  | 2
| Acquisition | Pioneer Pipeline Asset Purchase (AP) | 101 km NPS 20 | 2021 | Approved | 2021-06-15 | Oct 2, 2020 - TTFP Presentation Oct 9, 2020 - AUC Application Filed 69 Jan 15, 2021 - NGTL CER Application Filed 72 Jun 15, 2021 - AUC Approval81 | 276 266 198
| Acquisition | Pioneer South Pipeline Acquisition | 30 km NPS 20 | 2021-10-01 | Applied for | 2021-01-15 | Jan 15, 2021 - CER Application Filed 72 | 68 |  |  | 68
| Compressor Station Unit Addition & Coolers | Pipestone Compressor Station Unit Addition & Coolers | 30 MW | TBD | Deferred |  | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v | 145 - ROM
| Receipt Meter Station | Pipestone Creek Receipt Meter Station | 662U Ultrasonic Meter | 2019-11-01 | In-Service | 2019-10-22 | Feb 1, 2019 - TTFP Notification Feb 19, 2019 - NEB Application Filed 45 | 3.1 | 3.1
| Receipt Meter Station Expansion | Prairie Creek Receipt Meter Station Expansion | NPS 8 Separator Installation | 2019-12-01 | In-Service | 2019-12-13 | Oct 2, 2019 - TTFP Notification, Streamlining Order | 1.3 | 1.3
| Compressor Station Unit Addition & Coolers | Princess Compressor Station Unit Addition & Coolers | 30 MW | TBD | Deferred |  | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi | 137 - ROM
| Delivery Meter Station | Redwater Cogen Delivery #2 Station (AP) | 2-440T Turbine Meter | 2018-12-01 | In-Service | 2019-01-01 | Aug 7, 2018 - TTFP Notification Jul 30, 2018 - GRA Application Filed 46 | 1.1
| Lateral Loop | Saddle Lake Lateral Loop (Cold Lake Section) | 20 km NPS 20 | 2021-11-01 | In-Service | 2021-06-29 | Feb 13, 2018 - TTFP Facility Update Aug 23, 2019 - NEB Application Filed 14 Oct 6,2021 - Appendix 2 Update (Estimate at Complete) | 42 - ROM 65 - Class 4 66 - EAC |  |  | 66
| Saddle West Expansion | Saddle West Expansion: Clarkson Valley Control Valve | Control Valve Installation | 2019-06-01 | In-Service | 2019-05-30 | Jul 21, 2017 - TTFP Facility Update Oct 2, 2017 - NEB Application Filed 47 Aug 7, 2018 - Appendix 2 Class Estimate Update | 4.4 4.5 4.3 | 4.3
| Saddle West Expansion | Saddle West Expansion: Gordondale Lateral Loop No. 3 | 25 km NPS 36 | 2019-06-01 | In-Service | 2019-01-12 | Dec 5, 2016 - TTFP Notification, 2016 Annual Plan iv Oct 2, 2017 - NEB Application Filed 47 Aug 7, 2018 - Appendix 2 Class Estimate Update May 7, 2019 - Appendix 2 Update (Estimate at Complete) | 96 - ROM 98 - Class 4 130 - Class 3 134 - EAC | 134
| Saddle West Expansion | Saddle West Expansion: Latornell Compressor Station Unit Addition | 30 MW | 2019-06-01 | In-Service | 2019-10-03 | Dec 5, 2016 - TTFP Notification, 2016 Annual Plan iv Oct 2, 2017 - NEB Application Filed 47 Aug 7, 2018 - Appendix 2 Class Estimate Update Jan 7, 2020 - Appendix 2 Update (Estimate at Complete) | 101 - ROM 118 - Class 4 142 - Class 3 156 - EAC | 156 | [5 empty] | Elevated prime contractor costs due to unfavorable market conditions Increased costs associated with vibration issues and brownfield site conditions.
| Saddle West Expansion | Saddle West Expansion: Nordegg Compressor Station Unit Addition | 30 MW | 2019-06-01 | In-Service | 2019-09-14 | Feb 14, 2017 - TTFP Update Jul 21, 2017 - TTFP Facility Update Oct 2, 2017 - NEB Application Filed 47 Aug 7, 2018 - Appendix 2 Class Estimate Update Jan 7, 2020 Appendix 2 Update (Estimate at Complete) | 116 - ROM 112 - ROM 111 - Class 4 139 - Class 3 140 - EAC | 140 | [5 empty] | Elevated prime contractor costs due to unfavorable market conditions
| Saddle West Expansion | Saddle West Expansion: Saddle Hills Compressor Station Unit Addition and Control Valve Modifications | 30 MW | 2019-06-01 | In-Service | 2019-10-03 | Dec 5, 2016 - TTFP Presentation, 2016 annual Plan iv Jun 13, 2017 - TTFP Update Oct 2, 2017 - NEB Application Filed 47 Aug 7, 2018 - Appendix 2 Class Estimate Update Jan 7, 2020 - Appendix 2 Update (Estimate at Complete) | 74 - ROM 119 - Class 5 118 - Class 4 145 - Class 3 173 - EAC | 173 | [5 empty] | Elevated prime contractor costs due to unfavorable market conditions Increased costs associated with vibration issues and brownfield site conditions.
| Saddle West Expansion | Saddle West Expansion: Swartz Creek Compressor Station Unit Addition | 30 MW | 2019-06-01 | In-Service | 2019-09-14 | Dec 5, 2016 - TTFP Presentation, 2016 Annual Plan iv Oct 2, 2017 - NEB Application Filed 47 Aug 7, 2018 - Appendix 2 Class Estimate Update Jan 7, 2020 - Appendix 2 Update (Estimate at Complete) | 116 - ROM 116 - Class 4 142 - Class 3 146 - EAC | 146 | [5 empty] | Elevated prime contractor costs due to unfavorable market conditions
| Delivery Meter Station | Scotford PDH Delivery Meter Station (AP) | 860T Turbine Meter | 2021-07-13 | In-Service | 2021-03-26 | May 1, 2018 - TTFP Notification | 2.6 (Includes $1.7M CIAC)
| Delivery Meter Station | Sheerness No. 2 Sales Meter Station | 2-1210U Ultrasonic Meter | 2019-11-01 | In-Service | 2019-11-26 | Mar 8, 2019 - TTFP Notification Apr 1, 2019 - NEB Application Filed 48 | 4.2 | 4.2
| Lateral Loop | Smoky River Lateral Loop | 10 km NPS24 18 km NPS 24 | 2019-04-01 | In-Service In-Service | Mar 25, 2019 Jun 4, 2019 | Dec 5, 2016 - TTFP Presentation, 2016 Annual Plan iv Sep 12, 2017 - TTFP Presentation (Scope/Status Update) Nov 29, 2017 - NEB Application Filed 49 Nov 19, 2019 - Appendix 2 Update (Estimate at Complete) | 54 - Class 5 118 - Class 5 91 - Class 4 89 - EAC | 89
| Delivery Meter Station | Smoky River Sales Meter Station | 660U Ultrasonic Meter | 2020-03-01 | In-Service | 2020-04-29 | Jul 23, 2019 - TTFP Notification Aug 12, 2019 - NEB Application filed 50 | 2.9 |  | 2.9
| Delivery Meter Station | Smoky River South Sales Meter Station | NPS 3 Positive Displacement Meter | 2022-01-01 | Applied for | 2021-08-26 | May 20, 2021 - TTFP Notification Aug 26, 2021 - NEB Application Filed 82 | 4.5 |  |  |  | 4.5
In-Service | Pipeline Acquisition | South Airdrie Lateral - Pipeline Acquisition (AP) | 8.7 km NPS 6 | 2021 | In-Service | 2021-07-05 | Aug 7, 2018 - TTFP Notification Jul 30, 2018 - GRA Application Filed 51 Jun 16, 2020 - GRA Application Filed 63 | 1.9 1.4
| Installation (AP) | Spruce Grove and Stony Plain UPU – Installation (AP) | 5.4 km NPS 8 3 Delivery Stations | 2023 | Approved |  | Jun 16, 2020 - GRA Application Filed 63 Mar 1,2021 - GRA Application Approved 73 | 13.2
| Connection Piping | Stoney Transit/North Gate Connection Piping (AP) | 4.3 km NPS 8 | Q1 2019 | In-Service | 2019-03-08 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v May 25, 2018 - AUC Application Filed 52 Oct 14, 2020 - Appendix 2 Update (Estimate at Complete) | 8 15 - EAC
| Receipt Meter Station | Sunchild Receipt Meter Station | 880U-4 Ultrasonic Meter | 2020-04-01 | In-Service | 2020-03-19 | Jun 5, 2019 - TTFP Notification Jul 8, 2019 - NEB Application Filed 53 | 4 |  | 4
| Receipt Meter Station Expansion | Tony Creek No. 2 Receipt Meter Station Expansion | 16164U Ultrasonic Meter | 2019-08-01 | In-Service | 2019-07-23 | Oct 15, 2018 - TTFP Notification Nov 13, 2018 - NEB Application Filed 54 | 6 5.7 | 5.7
| Pipeline Replacement | Urban Pipeline Replacement Project: Edmonton UPR – NE Connector (AP) | Control Station | 2021 | Approved |  | Oct 30, 2014 - TTFP Presentation Dec 4, 2018 – AUC Project Update Filed 55 Jun 16, 2020 - AUC Project Update Filed 64 | 11
EAC | North Montney Project | Variance Application Meters Blair Creek Gundy Kobes Altares Aitken Creek Interconnect | 2-16104U Ultrasonic 2-1284U Ultrasonic 2-1064U Ultrasonic 2-1064U Ultrasonic 2-2416U Ultrasonic | Apr 2020 Sep 2019 Apr 2021 Sep 2019 Q3 2021 | ISD May 19, 2020 ISD Jan 31, 2020 ISD Feb 26, 2021 ISD Jan 31, 2020 ISD Jun 25, 2021 | 2021-11-18 | Variance Application 32 Nov 18, 2021 - Facility Status Update (Estimate at Complete) | 39 - Class 4 38 - EAC |  | 38
Cancelled | Compressor Station Unit Addition | Vermillion Compressor Station Unit Addition (AP) | 1 MW | 2021-04-01 | Cancelled |  | Feb 13, 2018 - TTFP Facility Update | TBD
| Compressor Station Unit Addition & Coolers | Vetchland Compressor Station Unit Addition & Coolers | 30 MW | TBD | Deferred |  | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi | 145 - ROM 137 - ROM
| West Path Delivery 2022 | West Path Delivery 2022 ABC Border Meter Station Expansion | 5 - NPS 20U Ultrasonic Meters | 2022-11-01 | Approved | 2021-04-30 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Jun 1, 2020 - NEB Application Filed 61 April 30, 2021 - Approval 74 | 8 |  |  |  | 8
| West Path Delivery 2022 | West Path Delivery 2022 Edson Mainline No. 4 (Raven River) | 18 km NPS 48 | 2022-11-01 | Approved | 2021-04-30 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Jun 1, 2020 - NEB Application Filed 61 April 30, 2021 - Approval 74 | 128 - ROM |  |  |  | 128
| West Path Delivery 2022 | West Path Delivery 2022 WAML Loop No. 2 (Alberta British Columbia) | 6 km NPS 48 | 2022-11-01 | Approved | 2021-04-30 | Jan 21, 2020 - TTFP 2019 Annual Plan Update vii Jun 1, 2020 - NEB Application Filed 61 April 30, 2021 - Approval 74 | 57 - ROM |  |  |  | 57
| West Path Delivery 2023 | West Path Delivery 2023 WAML Loop No. 2 (Longview) | 9 km NPS 48 | 2023-11-01 | Applied for | 2020-10-22 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 67 | 65 - ROM 75 - Class 5 |  |  |  |  | 75
| West Path Delivery 2023 | West Path Delivery 2023 WAML Loop No. 2 (Lundbreck) | 7 km NPS 48 | 2023-11-01 | Applied for | 2020-10-22 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 67 | 83 - ROM 72 - Class 5 |  |  |  |  | 72
| West Path Delivery 2023 | West Path Delivery 2023 WAML Loop No. 2 (Turner Valley) | 24 km NPS 48 | 2023-11-01 | Applied for | 2020-10-22 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 67 | 209 - ROM 209 - Class 5 |  |  |  |  | 209
| West Path Delivery Project | West Path Delivery Project: Burton Creek Compressor Station Unit Addition | 30 MW | 2020-06-01 | In-Service | 2020-06-22 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 12, 2018 - NEB Application Filed 56 Oct 14, 2020 - Appendix 2 Update (Estimate at Complete) | 116 - ROM 114 - Class 4 167 - EAC |  | 167 |  |  |  |  | The increased costs were related to constructability and productivity challenges compounded by site complexity.
| West Path Delivery Project | West Path Delivery Project: Turner Valley Compressor Station Unit Addition | 30 MW | 2020-06-01 | In-Service | 2020-04-09 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 12, 2018 - NEB Application Filed 56 Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 132 - ROM 106 - Class 4 101 - EAC |  | 101
| West Path Delivery Project | West Path Delivery Project: Western Alberta System Mainline Loop Rocky View Section | 22 km NPS 42 | 2020-06-01 | In-Service | 2020-03-21 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Feb 12, 2018 - NEB Application Filed 56 Aug 11, 2020 - Appendix 2 Update (Estimate at Complete) | 176 - ROM 189 - Class 4 183 - EAC |  | 183
| Delivery Meter Station | Wiau Lake North Sales Meter Station | 2-640T Turbine Meter | 2019-07-01 | In-Service | 2019-02-08 | May 22, 2018 - TTFP Notification Jun 11, 2018 - NEB Application Filed 57 | 2.4 | 2.4
| Receipt Meter Station | Wilson Ridge Receipt Meter Station | 10104U Ultrasonic Meter | 2019-02-01 | In-Service | 2019-01-22 | Mar 1, 2018 - TTFP Notification Apr 11, 2018 - NEB Application Filed 58 | 3.9 | 3.9
| Compressor Station Unit Addition | Winchell Lake Compressor Station Unit Addition | 30 MW | 2019-11-01 | In-Service | 2019-11-08 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Mar 8, 2018 - NEB Application Filed 59 Approved Aug 30, 2018 Jul 7, 2020 - Appendix 2 Update (Estimate at Complete) | 116 - ROM 99 - Class 4 102 - EAC | 102
| Receipt Meter Station | Wolf Lake South Receipt Meter Station | 1010-4U Ultrasonic Meter | 2019-09-01 | In-Service | 2019-09-18 | Nov 29, 2018 - TTFP Notification Dec 18, 2018 - NEB Application Filed 60 | 3.8 | 3.8

## References
References
Annual Plans
i. | NGTL 2013 Annual Plan
ii. | NGTL 2014 Annual Plan
iii. | NGTL 2015 Annual Plan
iv. | NGTL 2016 Annual Plan
v. | NGTL 2017 Annual Plan
vi. | NGTL 2018 Annual Plan
vii. | NGTL 2019 Annual Plan
viii. | NGTL 2020 Annual Plan
ix. | NGTL 2021 Annual Plan
1 | Application for 2015 Meter Station and Associated Lateral Abandonment
2 | 2016 Pipeline Decomissioning NEB Applications Filed
3 | Application for 2017 Meter Station and Associated Lateral Abandonment
4 | 2018 Meter Stations and Laterals Abandonment Program
5 | 2018 Pipeline Decommissioning Program
6 | 2021 NGTL System Expansion Project
7 | Canada Energy Regulator Report for the 2021 NGTL System Expansion Project
8 | Alberta-Montana Border Sales Meter Station Replacement
9 | Application for the construction of Anderson Lake Receipt Meter Station
10 | Buffalo Creek B3 and Goodfish A2 Compressor Station Unit Additions
11 | Clark Lake South Receipt Meter Station
12 | NGTL Clearwater West Expansion Project
13 | Clearwater Compressor Station C7 Unit Addition
14 | Saddle Lake Lateral Loop (Cold Lake Section) Project
15 | Application for the Construction of Cutbank River North Receipt Meter Station
16 | Dawson Creek No. 2 Receipt Meter Station
17 | Dawson Creek East No. 2 Receipt Meter Station
18 | Dorscheid Receipt Meter Station
19 | Edson Control Valve Addition
20 | Application for the Construction of Edson Mainline Expansion Project
21 | Application for Approval for the Etzikom Abandonment Project
22 | Forestburg Lateral Loop and Forestburg East Sales Meter Station
23 | Gold Creek South Receipt Meter Station No. 2
24 | Gold Creek West Receipt Meter Station
25 | McLeod River North Project
26 | Application for the Construction of Groundbirch Mainline Loop (Sunrise Section)
27 | GRA Application Filed
28 | Mildred Lake East Sales Meter Station
29 | North Central Corridor Loop (North Star Section 1)
30 | Application for the Construction of North Corridor Expansion Project
31 | Application for North Montney Project
32 | North Montney Mainlne Project - Application for Variance
33 | Application for the Mackie Creek North Receipt Meter Station
34 | Application for the Altares South Receipt Meter Station
35 | Application for Townsend Receipt Meter Station and Townsend No. 2 Receipt Meter Station
36 | Application for Gundy West Receipt Meter Station
37 | Application for the Old Alaska Receipt Meter Station
38 | Application for Aitken Creek South Receipt Meter Station
39 | Application for Aitken Creek West No. 2 Receipt Meter Station
40 | North Path Delivery Project
41 | Northwest Mainline Loop (Boundary Lake North Section)
42 | Application for the Peace River Mainline Abandonment
43 | Aug 1, 2018 - AUC Application Filed
44 | Nov 30, 2018 - AUC Project Update Filed
45 | Pipestone Creek Receipt Meter Station
46 | Jul 30, 2018 GRA Application Filed
47 | Saddle West Expansion
48 | Application for the Construction of Sheerness No. 2 Meter Station
49 | Smoky River Lateral Loop
50 | Application for the construction of Smoky River Sales Meter Station
51 | Jul 30, 2018 GRA Application Filed
52 | May 25, 2018 - AUC Application Filed
53 | Sunchild Receipt Meter Station
54 | Tony Creek No. 2 Receipt Meter Station Expansion
55 | Dec 4, 2018 – AUC Project Update Filed
56 | West Path Delivery Project Application
57 | Wiau Lake North Sales Meter Station
58 | Wilson Ridge Receipt Meter Station
59 | Application for Winchell Lake Compressor Station Unit Addition
60 | Wolf Lake South Receipt Meter Station
61 | NGTL West Path Delivery 2022 CER
62 | GRA Application Filed
63 | GRA Application Filed
64 | (GRA) AUC Project Update Filed
65 | Gleichen-Cluny GRA Filed
66 | GRA Application Filed
67 | NGTL West Path Delivery 2023 CER
68 | NGTL GBML Loop (Saturn Section) & Saddle Hills CS C4 Unit Addition
69 | ATCO Pioneer AUC Application
70 | Gundy West No. 2 Receipt Meter Station
71 | Old Alaska No. 2 Receipt Meter Station
72 | Canada Energy Regulator - REGDOCS - C10955 NOVA Gas Transmission Ltd. - Pioneer South Pipeline Acquisition (cer-rec.gc.ca)
73 | March 1, 2021 - GRA Application Approved
74 | April 30, 2021 - West Path Delivery Project
75 | North Corridor Expansion - GIC Approval
76 | GBML (Saturn) and Saddle Hills UA Application
77 | Emerson Creek Compressor Station
78 | Application for the construcion of Chambers Creek Receipt Meter Station
79 | Edson Mainline Expansion CER Approval
80 | Hidden Lake and Hidden Lake North Cooler Additions Application
81 | Pioneer (AP) AUC Approval
82 | Smoky River South Sales Meter Station Application
83 | McLeod River Sales Meter Station Application
84 | Hidden Lake and Hidden Lake North Cooler Additions CER Approval

## Facility Type Analysis (hidden)
Facility Type | Frequency
Abandonment | 1
Clearwater West Expansion | 4
Cogen Delivery Station | 0
Compressor Station | 1
Compressor Station Coolers | 1
Compressor Station Decomissioning | 1
Compressor Station Modifications | 0
Compressor Station Unit Addition | 5
Compressor Station Unit Addition & Coolers | 3
Connection Piping | 1
Control Valve Addition | 1
Crossover | 0
Delivery Meter Station | 8
Edson Mainline Expansion | 2
Expansion & Lateral Loop | 1
Extraction Connections | 0
Forestburg | 0
Grande Prairie Mainline Loop | 2
Groundbirch Mainline Loop | 1
Lateral Expansion | 0
Lateral Loop | 3
Meter Station & Lateral Abandonment | 3
NGTL System Expansion | 12
North Central Corridor Loop | 1
North Corridor Expansion | 4
North Montney Project | 11
North Path Delivery | 3
Northwest Mainline Loop | 1
Peace River Mainline Abandonment | 1
Pembina-Keephills Transmission Project | 1
Pipeline & Associated Decommissioning | 1
Pipeline Acquisition | 1
Pipeline Asset Purchase | 0
Pipeline Decommissioning | 1
Pipeline Replacement | 1
Pipeline Upgrade | 1
Receipt Meter Station | 10
Receipt Meter Station Expansion | 3
Saddle West Expansion | 6
Sales Meter Station | 0
Sales Meter Station Expansion | 0
Sales Meter Station Replacement | 0
Transmission Loop | 0
West Path Delivery 2022 | 3
West Path Delivery 2023 | 1
West Path Delivery Project | 0

## Forecast Costs (hidden)
Applied-for Facilities | Forecast Cost ($Millions)
Hidden Lake & Hidden Lake North Station Coolers
Old Alaska No. 2 | 3.4
#REF!
North Path Delivery Project: Meikle River Compressor Station Series Modifications
Saddle West Expansion: Latornell Compressor Station Unit Addition
#REF!
West Path Delivery 2022 ABC Border Meter Station Expansion | 8
Groundbirch Mainline Loop (Sunrise Section)
Inland Looping (AP)
Pioneer Interconnect | 2
Vermillion Compressor Station Unit Addition (AP)
Mildred Lake East Sales Meter Station
#REF!
#REF!
#REF!
North Path Delivery Project: Amber Valley Compressor Station Unit Addition
Clearwater West Expansion: Wolf Lake Compressor Station Unit Addition
Cold Lake Border Sales Meter Station Replacement | 3.2
#REF!
Dawson Creek No. 2 Receipt Meter Station | 4.4
#REF!
Gleichen-Cluny Transmission Looping – Installation (AP) | 2.7
Dawson Creek East No. 2 Receipt Meter Station | 3.8
Redwater Cogen Delivery #2 Station (AP) | 1.1
West Path Delivery 2023 WAML Loop No. 2 (Longview) | 65 - ROM 75 - Class 5
West Path Delivery 2022 Edson Mainline No. 4 (Raven River) | 128 - ROM
Anderson Lake Receipt Meter Station | 4
Saddle West Expansion: Saddle Hills Compressor Station Unit Addition and Control Valve Modifications
Saddle West Expansion: Clarkson Valley Control Valve
Peace River Mainline Abandonment (Meikle River to Valleyview Section)
#REF!
Chambers Creek Receipt Meter Station | 4
Cutbank River North Receipt Meter Station | 3.2
#REF!
Alberta Montana Border Sales Meter Station Replacement | 4.6
Gold Creek South Receipt Meter Station Expansion No. 2 | 3.5
Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Groundbirch Mainline Loop (Saturn Section)
#REF!
2016 Pipeline Decommissioning Program | 5.6
Sheerness No. 2 Sales Meter Station | 4.2
#REF!
2016 Meter Station and Associated Lateral Abandonment | 6.7
#REF! | #REF!
Saddle West Expansion: Nordegg Compressor Station Unit Addition
#REF!
Vetchland Compressor Station Unit Addition & Coolers | 145 - ROM 137 - ROM
#REF!
Smoky River Lateral Loop
2017 Meter Stations and Laterals Abandonment Program | 16.4
#REF!
#REF!
Emerson Creek Compressor Station
#REF!
#REF!
2018 Meter Station and Laterals Abandonment Program
2018 Pipelines and Associated Facilities Decommissioning Program
2021 NGTL System Expansion Project: Beiseker Compressor Station Unit Addition
2021 NGTL System Expansion Project: Didsbury Compressor Station & Coolers
2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Brewster)
2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Dismal Creek)
2021 NGTL System Expansion Project: Edson Mainline Loop No.4 (Robb)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Colt Section)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Deep Valley)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Karr)
#REF!
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.3 (Elmworth Section 2 & 3)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.4 (Valhalla)
2021 NGTL System Expansion Project: January Creek Control Valve Addition
2021 NGTL System Expansion Project: Nordegg Compressor Station Unit Addition
#REF!
Berland River Compressor Station Unit Addition
Buffalo Creek Compressor Station Unit Addition
Clark Lake South Receipt Meter Station | 4.4
Clearwater Compressor Station Unit Addition & Coolers
Clearwater West Expansion: Clearwater Compressor Station Unit Addition
Clearwater West Expansion: Grande Prairie Mainline Loop No.2 (Huallen)
Clearwater West Expansion: Grande Prairie Mainline Loop No.3 (Elmworth Section 1)
#REF!
#REF!
Dorscheid Receipt Meter Station | 3.2
Edson Control Valve Addition
Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Alford Creek)
Edson Mainline Expansion Project: Edson Mainline Loop No.4 (Elk River)
#REF!
Etzikom Abandonment | 18.2
Gold Creek West Receipt Meter Station | 4.9
Goodfish Compressor Station Unit Addition
Grande Prairie Mainline Loop No. 2 (McLeod River North Section)
Grande Prairie Mainline Loop No. 4 (Valhalla North Section)
Grande Prairie Mainline Loop No. 4 (Valhalla North Section)
Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Saddle Hills Compressor Station Unit Addition
Gundy West No. 2 | 3.6
#REF!
#REF!
Keephills Expansion (AP) | 5.8
Mackie Creek North Altares South Townsend Townsend No. 2 Gundy West Old Alaska Aitken Creek South Aitken Creek West No. 2
McLeod River Sales Meter Station | 4
Medicine Hat Expansion Medicine Hat and Suffield Lateral Loop
Moody Creek Compressor Station Decommissioning | 1
Muriel Creek Sales Meter Station | 2.1
#REF!
North Central Corridor Loop (North Star Section 1)
North Corridor Expansion Project: Hidden Lake North Compressor Station Unit Addition
North Corridor Expansion Project: North Central Corridor Loop (North Star Section 2)
North Corridor Expansion Project: North Central Corridor Loop (Red Earth Section 3)
North Corridor Expansion Project: Northwest Mainline Loop No.2 (Bear Canyon North Extension Section)
North Montney Project: Aitken Creek Compressor Station
#REF!
North Montney Project: North Montney Mainline (Kahta Section - South)
#REF!
North Montney Project: Saturn Compressor Station Unit 2
North Montney Project: Saturn Compressor Station
North Path Delivery Project: Northwest Mainline Loop No. 2 (Bear Canyon North Section)
Northwest Mainline Loop (Boundary Lake North Section)
Pioneer Pipeline Asset Purchase (AP)
Pioneer South Pipeline Acquisition | 68
Pipestone Compressor Station Unit Addition & Coolers
#REF!
#REF!
Pipestone Creek Receipt Meter Station | 3.1
Prairie Creek Receipt Meter Station Expansion | 1.3
Princess Compressor Station Unit Addition & Coolers
Saddle Lake Lateral Loop (Cold Lake Section)
Saddle West Expansion: Gordondale Lateral Loop No. 3
Saddle West Expansion: Swartz Creek Compressor Station Unit Addition
Scotford PDH Delivery Meter Station (AP)
Smoky River Sales Meter Station | 2.9
#REF!
Smoky River South Sales Meter Station | 4.5
#REF!
South Airdrie Lateral - Pipeline Acquisition (AP)
Spruce Grove and Stony Plain UPU – Installation (AP)
Stoney Transit/North Gate Connection Piping (AP)
Sunchild Receipt Meter Station
Tony Creek No. 2 Receipt Meter Station Expansion
Urban Pipeline Replacement Project: Edmonton UPR – NE Connector (AP)
Variance Application Meters Blair Creek Gundy Kobes Altares Aitken Creek Interconnect
West Path Delivery 2022 WAML Loop No. 2 (Alberta British Columbia)
#REF!