## Summary & Notes
The Facility Status Update describes the current status of facilities that were applied for, are under construction or have been placed on-stream since the 2024 Annual Plan was issued on February 03, 2025 and maintains a record of the facilities for two years prior to the current year. Periodic updates are being provided based on the level of activity occurring with respect to facilities. Facilities with (AP) after the project name refer to facilities in the ATCO Pipelines footprint.
| Summary: | 2024 | 2025 | 2026 | 2027 | 2028 | 2029
| Total Costs by In-Service Year * | 1397.4 | 19 | 611.8 | 415 | 273 | 480
Forecast Costs There are two methodologies for forecasting costs and for NGTL projects greater than $25 million, the estimate type are identified. For a Class Estimate, the target accuracy for the various estimate types are shown in the table below. These accuracy ranges are for typical TC Energy projects with established technological complexity. It should be noted that for non-typical TC Energy projects the accuracy range could widen towards the upper limit of the AACE ranges for a class of estimate (i.e. depending on area knowledge, technological complexity, level of expertise, and certainty of facility scope). If a cost estimate for an NGTL project is based on the wider accuracy range, the estimate range will be provided in the Variance Explanation column. Forecasted costs reflect the dollar value, economic conditions, and estimation procedures at the time the estimates were completed. For a Parametic Estimate, TC Energy may also baseline cost estimates using a probabilistic assessment driven by the risks and uncertainties associated with the project. Typically, the plausible outcomes are expressed as a P-Value and range between P10-P90. The Value indicates the confidence level of a particular cost estimate and indicates the expected probability that the final cost will be equal-to or less-than the specified estimate value. For example, a 70% confidence level for an estimate value (often noted as a P70) indicates an expected 70% probability that the final result will be less than (more favorable) or equal to the P70 cost estimate.
Total Costs by In-Service Total Costs by In-Service Year are a summation of the last provided costs of all NGTL capacity capital projects with expected or realized in-service dates within a calendar year. Costs for non NGTL capacity capital projects, such as ATCO Pipelines, CIAC, decommissioning or abandonment projects, are excluded. These annual summations of costs will not match other regulatory filings with different costs bases. Variance Explanation Variance explanations are provided for all NGTL capacity capital projects with EAC costs equal to or greater than $25 million with a variance greater than 10% between the EAC and applied-for costs.
Disclaimer The information provided in this document has been prepared to the best of management’s ability. TC does not represent or warrant that the information contained herein is accurate and complete in all respects or is fit for any purpose. Any of use of the information in its current or any manipulated form is the sole responsibility of the user. TC Energy is not responsible for any changes made to downloaded copies and/or results in data compiled, assumptions, and actions resulting from those changes. NGTL can only support use of the official PDF version as posted on TC Customer Express.

## Facilities Update
Report Updates | Facility Category | Applied-for Facilities | Description | Target In-Service Date | Status | Date of Status | References * | Forecast Cost * ($Millions) | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Variance Explanation
| DDA | 2021 Meter Station and Laterals Abandonment Program | Pipeline Laterals & Meters 12 - 151.2 km 9 Receipt 1 Delivery Stand-Alone Meters 3 Receipt 1 Delivery | Q1 2025 | Complete | 2025-04-08 | Mar 7, 2022 - TTFP Notification May 3, 2022 - CER Application Filed 13 | 13
| DDA | 2021 Meter Station and Laterals Decommisioning Program | Pipeline Laterals & Meters 5 - 120.7 km 2 Receipt 1 Delivery | Q4 2024 | Complete | 2025-04-08 | Jun 13, 2022 - TTFP Notification Aug 22, 2022 - CER Application Filed 14 | 7.1
| Pipeline | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Deep Valley) | 69 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2024-05-15 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 1 Feb 19, 2020 - CER Recommendation 2 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Sep 17, 2024 - Facility Status Update (Estimate at Complete) | 332 - ROM 377 - Class 5 530 - Class 3 665 - Class 3 970 - EAC | 970 | [5 empty] | Delayed regulatory approval impacted cost and execution plans. Multiple construction seasons with prime contractor complications and redesign of Simonette HDD.
Completed | DDA | 2022 Meter Station and Laterals Abandonment Program | Pipeline Laterals & Meters 23 - 167.5 km 22 Receipt 1 Delivery 7 Producer Tie-ins | Q2 2025 | Complete | 2025-09-25 | Apr 6, 2023 - TTFP Facility Notification May 23, 2023 - CER Application Filed 17 | 23
Completed | DDA | 2022 Meter Station and Laterals Decommissioning Program | Pipeline Laterals & Meters 23 - 310.34 km 2 Receipt | Q2 2025 | Complete | 2025-05-25 | Jun 19, 2023 - TTFP Notification Aug 21, 2023 - CER Application Filed20 | 18.6
Target ISD updated | DDA | 2024 Meter Station and Laterals Abandonment Program | Pipeline Laterals & Meters 26 - 196.2 km 26 Receipt Meter Stations 1 Delivery Meter Station 5 Producer Tie-ins | Q3 2026 | Approved | 2025-04-08 | June 18, 2024 - CER Application Filed26 Apr 8, 2025 - TTFP Notification | 25.4
Target ISD updated | DDA | 2024 Meter Station and Laterals Decommissioning Program | Pipeline Laterals & Meters 38 - 452.5 km 8 Receipt Meter Stations 2 Producer Tie-Ins | Q3 2027 | Approved | 2025-04-08 | Aug 13, 2024 - CER Application Filed27 Apr 8, 2025 - TTFP Notification | 34
Proposed | DDA | 2025 Meter Station and Laterals Abandonment Program | Pipeline Laterals, PTIs & Meters 27 - 207.2 km 35 meter stations | Q3 2027 | Applied for | 2025-07-30 | Jul 30, 2025 - CER Application Filed 40 | 40.9
Proposed | DDA | 2025 Meter Station and Laterals Decommissioning Program | Pipeline Laterals 16-186.8 km | Q3 2027 | Applied for | 2025-07-23 | Jul 23, 2025 - CER Application Filed 41 | 11.3
Changed forecast cost to match GRA | Compressor Station | Atusis Creek Compressor Station - Refurbishment (AP) | Compressor Upgrade | 2027 | Applied for | 2025-09-22 | Sep 22, 2025 - GRA Application Filed | 4.8
Targeted ISD | Compressor Station | Berland River Compressor Station Unit and Coolers Addition | 30 MW | Late Q2 / early Q3 2026 | Under Construction | 2024-09-16 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix Sep 7, 2022 - TTFP Facilites Update Aug 1, 2023 - CER Application Filed18 Dec 21, 2023 - CER Approval19 | 166 - ROM 254 - Class 5 255 - Class 4 |  |  | 255
| Delivery Lateral | Coaldale Lateral East #2 Branch Loop (AP) | 2.2 km NPS 4 | 2025-10-01 | Applied for | 2025-06-17 | June 17, 2025 - TTFP Notification May 20, 2025 - AUC Application Filed28 | 4.2
| Receipt Meter Station | Codner South Receipt Meter Station | 10104U Ultrasonic Meter | 2025-08-01 | In-Service | 2025-07-23 | Oct 29, 2024 - TTFP Notification | 6.4 | 6.4
| Receipt Meter Station | Dawson Creek No.2A Meter Station | 1010-4U | 2026-07-01 | Proposed | 2025-08-12 | Aug 12, 2025 - TTFP Notification | 5.5 |  | 5.5
| Compressor Station | Emerson Creek Compressor Station | 2-30 MW Units | 2024-04-01 | In-Service | 2024-04-01 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii June 1, 2021 - CER Application Filed 11 Dec 22, 2021- CER Approval12 July 18, 2024 - Facility Status Update (Estimate at Complete) | 257 - ROM 278 - Class 5 274 - EAC | 274
EAC cost added | Pipeline | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) | 33km NPS 48 | 2026-04-01 | In-Service | 2025-09-25 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix Sep 7, 2022 - TTFP Facilites Update Aug 1, 2023 - CER Application Filed18 Dec 21, 2023 - CER Approval19 | 281 - ROM 342 - Class 5 323 - Class 4 237 - EAC |  |  | 237
Cost estimate update and applied for with CER | Pipeline | Grande Prairie Mainline Loop (Colt Section) | 18 km NPS 48 | 2028-04-01 | Applied for | 2026-02-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Dec 10, 2024 - TTFP Presentation, 2024 Annual Plan xii Feb 12, 2026 - CER Application Filed43 | 404 - P70 273 - Class 3 |  |  |  |  | 273
Cost estimate update and ISD | Pipeline | Grande Prairie Mainline Loop (Greenview Section) | 15 km NPS 48 | 2029-04-01 | Proposed | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Dec 10, 2024 - TTFP Presentation, 2024 Annual Plan xii | 205 - P70 253 - Class 3 | [5 empty] | 253
Cost estimate update and ISD | Pipeline | Grande Prairie Mainline Loop (Karr North Section) | 16 km NPS 48 | 2029-04-01 | Proposed | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Dec 10, 2024 - TTFP Presentation, 2024 Annual Plan xii | 238 - P70 227 - Class 4 | [5 empty] | 227
Cost estimate update and CER approval | Pipeline | Grande Prairie Mainline Loop (McLeod South Section) | 21 km NPS 48 | 2027-04-01 | Approved | 2026-01-16 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Dec 10, 2024 - TTFP Presentation, 2024 Annual Plan xii Aug 11, 2025 - CER Application Filed38 Jan 16, 2026 - CER Approval 42 | 321 - P70 262 - Class 3 |  |  |  | 262
| Compressor Station | Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Saddle Hills Compressor Station Unit Addition | 30 MW | 2024-04-01 | In-Service | 2024-04-19 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Nov 5, 2020 - CER Application Filed 8 May, 13, 2021 - CER Approval 10 July 18, 2024 - Facility Status Update (Estimate at Complete) | 159 - ROM 151 - Class 5 123 - EAC | 123
| Pipeline | Inland Looping (AP) | 9km NPS 20 | 2025-11-01 | In-Service | 2025-02-14 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix June 21, 2023 - Facility Status Update | 40 - ROM
| Delivery Meter Station | Iosegun Sales Meter Station | 440T Turbine Meter | 2024-09-01 | In-Service | 2024-08-29 | Sep 11, 2023 - CER Application Filed21 Feb 15, 2024 - TTFP Notification | 3.3 | 3.3
Under Construction | Pipeline | Leming Loop (Field Lake Section) | 17 km NPS 20 | Apr 2026 | Under Construction | 2025-10-07 | Dec 13, 2022 - TTFP Presentation, 2022 Annual Plan x May 9, 2023 - TTFP Facility Update Presentation Mar 01, 2024 - CER Application Filed22 Sep 20, 2024 - CER Approval24 | 270 - ROM 107 - Class 5 105 - Class 4 |  |  | 105
Under Construction | Pipeline | Leming Loop (Sand Section) | 18 km NPS 20 | 2027-04-01 | Under Construction | 2025-10-07 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Jan 10, 2025 - CER Application Filed25 Aug 21, 2025 - CER Approval35 | 149 - ROM 153 - Class 4 |  |  |  | 153
| Other | Lethbridge Urban Pipeline Upgrade (AP) | 10.8 km NPS 8 2.4 km NPS 6 Control Station 3 Delivery Stations | Q3 2024 | In-Service | 2024-01-11 | Aug 7, 2018 - TTFP Notification Jul 30, 2018 - GRA Application Filed 3 Jun 16, 2020 - GRA Application Filed 7 Mar 1, 2021 - GRA Application Approved 9 | 40
| Receipt Meter Station | Mackie Creek North Receipt Meter Station Expansion | 682U Ultrasonic Meter | 2024-01-01 | In-Service | 2023-12-15 | Jun 20, 2023, - TTFP Notification | 1.1 | 1.1
In-service | Receipt Meter Station | Mackie Creek North Receipt Meter Station Expansion - Phase 2 | 682 Orifice Meter | 2025-11-01 | In-Service | 2025-12-05 | Dec 3, 2024 - TTFP Notification Dec 10, 2024 - CER Application Filed36 Feb 26, 2025 - CER Approval37 | 3.9 |  | 3.9
| Delivery Meter Station | Mildred Lake West Sales Meter Station | 2-1010U Ultrasonic Meter | 2024-04-01 | In-Service | 2024-04-01 | Nov 30, 2022 - TTFP Notification Mar 13, 2023 - CER Application Filed 16 | 6.6 | 6.6
| Receipt Meter Station | Pipestone Creek Meter Station Expansion | 662-U Ultrasonic | 2026-04-01 | Under Construction | 2025-10-10 | Apr 8, 2025 - TTFP Notification Jul 31, 2025 - CER Approval30 | 3.9 |  |  | 3.9
In-service | Receipt Meter Station | Saturn No. 3 Receipt Meter Station | 1010-U Ultrasonic Meter | 2025-11-01 | In-Service | 2025-11-28 | Jan 17, 2025 - TTFP Notification Aug 6, 2025 - CER Approval32 | 4.3 |  | 4.3
| Other | Spruce Grove and Stony Plain UPU – Installation (AP) | 5.4 km NPS 6 3 Delivery Stations | Q1 2024 | In-Service | 2024-03-22 | Jun 16, 2020 - GRA Application Filed 5 Mar 1,2021 - GRA Application Approved 9 | 13.2 11.5
| Receipt Meter Station | Tawadina Creek #2 Meter Station | 860-U Ultrasonic | 2026-03-01 | Under Construction | 2025-11-05 | Apr 8, 2025 - TTFP Notification Jul 31, 2025 - CER Approval31 Nov 5, 2025 - Under Construction | 4.8 |  |  | 4.8
| Receipt Meter Station | Tremblay North Meter Station | 662U | 2026-09-01 | Proposed | 2025-08-12 | Aug 12, 2025 - TTFP Notification | 5.3 |  | 5.3
Status changed to complete | Other | Urban Pipeline Replacement Project: Edmonton UPR – NE Connector (AP) | Control Station | 2026 | Complete | 2024 | Oct 30, 2014 - TTFP Presentation Dec 4, 2018 – AUC Project Update Filed 4 Jun 16, 2020 - AUC Project Update Filed 6 | 11
| Tie-in | Whiskey Jack Ethane Extraction Plant Tie-In | NPS 36 Connection, Valves, Tees | 2026-04-01 | Approved | 2025-06-13 | Feb 12, 2025 - TTFP Notification June 13, 2025 - CER Approval29 | 6.1 |  |  | 6.1
| Receipt Meter Station | Wilkin Lake Receipt Meter Station | 884U Ultrasonic Meter | 2024-07-01 | In-Service | 2024-08-28 | Oct 16, 2023 - CER Application Dec 14, 2023 - CER Approval23 | 5.9 | 5.9
| Delivery Meter Station | Willow Valley Interconnect Project | 2-1610U Ultrasonic Meter | 2024-04-24 | In-Service | 2024-04-01 | Jan 5, 2023 - TTFP Notification Jan 18, 2023 - CER Application Filed 15 | 7.1 | 7.1
| Compressor Station | Yellowhead Compressor Station (AP) | 16.4 MW | 2027 | Applied for | 2025-08-21 | May 9, 2023 - TTFP Facility Update Presentation Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Aug 22, 2024 - TTFP Update Sep 17, 2024 - AUC Need Application33 Aug 21, 2025 - AUC Need Application Approval34 Nov 04, 2025 - AUC Facilities Application39 | 103 - ROM 138 - Class 5 272 - Class 4 191 - Class 3
Name updated to Yellowhead Pipeline | Pipeline | Yellowhead Pipeline (AP) | 235 km NPS 36 Control Stations | 2027 | Applied for | 2025-08-21 | May 9, 2023 - TTFP Facility Update Presentation Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Aug 22, 2024 - TTFP Update Sep 17, 2024 - AUC Need Application33 Aug 21, 2025 - AUC Need Application Approval34 Nov 04, 2025 - AUC Facilities Application39 | 1,024 - ROM 1,815 - Class 5 2,541 - Class 4 2,746 - Class 3

## References
References
Annual Plans
i. | NGTL 2013 Annual Plan
ii. | NGTL 2014 Annual Plan
iii. | NGTL 2015 Annual Plan
iv. | NGTL 2016 Annual Plan
v. | NGTL 2017 Annual Plan
vi. | NGTL 2018 Annual Plan
vii. | NGTL 2019 Annual Plan
viii. | NGTL 2020 Annual Plan
ix. | NGTL 2021 Annual Plan
x. | NGTL 2022 Annual Plan
xi. | NGTL 2023 Annual Plan
xii. | NGTL 2024 Annual Plan
1 | 2021 NGTL System Expansion Project
2 | Canada Energy Regulator Report for the 2021 NGTL System Expansion Project
3 | GRA Application Filed
4 | Dec 4, 2018 – AUC Project Update Filed
5 | GRA Application Filed
6 | (GRA) AUC Project Update Filed
7 | GRA Application Filed
8 | NGTL GBML Loop (Saturn Section) & Saddle Hills CS C4 Unit Addition
9 | March 1, 2021 - GRA Application Approved
10 | GBML (Saturn) and Saddle Hills UA Application
11 | Emerson Creek Compressor Station
12 | Emerson Creek Compressor Station Approval
13 | 2021 Meter Station and Laterals Abandonment Program
14 | 2021 Meter Station and Laterals Decommissioning Program
15 | Willow Valley Interconnect Project
16 | Mildred Lake West Sales Meter Station Application
17 | 2022 Meter Stations and Laterals Abandonment Program
18 | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) and Berland River CS C3 Unit Addition Application
19 | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) and Berland River CS C3 Unit Addition Approval
20 | 2022 Meter Stations and Laterals Decommissioning Program
21 | Iosegun Sales Meter Station CER Project Notification
22 | Leming Lake Sales Lateral Loop (Field Lake Section) Application
23 | Wilkin Lake Receipt Meter Station Approval
24 | Leming Lake Sales Lateral Loop (Field Lake Section) Approval
25 | Leming Lake Sales Lateral Loop (Sand Section) Application
26 | 2024 Meter Station and Laterals Abandonment Program
27 | 2024 Meter Station and Laterals Decommissioning Program
28 | ATCO Coaldale Potato - AUC Facility Application
29 | Whiskey Jack Lake Ethane Extraction Plant Tie-in CER Approval
30 | Pipestone Creek Meter Station Expansion CER Approval
31 | Tawadina Creek #2 Meter Station CER Approval
32 | Saturn No. 3 Receipt Meter Station CER Approval
33 | Yellowhead Mainline Need Assessment Application
34 | Yellowhead Mainline Need Assessment Application Approval
35 | Leming Lake Sales Lateral Loop (Sand Section) CER Approval
36 | Mackie Creek North Receipt Meter Station Phase II Expansion Application
37 | Mackie Creek North Receipt Meter Station Phase II Expansion CER Approval
38 | Grande Prairie Mainline Loop No. 3 (McLeod South Section) Project CER Application
39 | Yellowhead Project Facility Application (30422-A001)
40 | 2025 Meter Station and Laterals Abandonment Program
41 | 2025 Meter Station and Laterals Decommissioning Program
42 | Grande Prairie Mainline Loop No. 3 (McLeod South Section) Project CER Application Approval
43 | Grande Prairie Mainline Loop No. 3 (Colt Section) Project CER Application

## Facility Type Analysis (hidden)
Facility Type | Frequency
Abandonment | #REF!
Clearwater West Expansion | #REF!
Cogen Delivery Station | #REF!
Compressor Station | #REF!
Compressor Station Coolers | #REF!
Compressor Station Decomissioning | #REF!
Compressor Station Modifications | #REF!
Compressor Station Unit Addition | #REF!
Compressor Station Unit Addition & Coolers | #REF!
Connection Piping | #REF!
Control Valve Addition | #REF!
Crossover | #REF!
Delivery Meter Station | #REF!
Edson Mainline Expansion | #REF!
Expansion & Lateral Loop | #REF!
Extraction Connections | #REF!
Forestburg | #REF!
Grande Prairie Mainline Loop | #REF!
Groundbirch Mainline Loop | #REF!
Lateral Expansion | #REF!
Lateral Loop | #REF!
Meter Station & Lateral Abandonment | #REF!
NGTL System Expansion | #REF!
North Central Corridor Loop | #REF!
North Corridor Expansion | #REF!
North Montney Project | #REF!
North Path Delivery | #REF!
Northwest Mainline Loop | #REF!
Peace River Mainline Abandonment | #REF!
Pembina-Keephills Transmission Project | #REF!
Pipeline & Associated Decommissioning | #REF!
Pipeline Acquisition | #REF!
Pipeline Asset Purchase | #REF!
Pipeline Decommissioning | #REF!
Pipeline Replacement | #REF!
Pipeline Upgrade | #REF!
Receipt Meter Station | #REF!
Receipt Meter Station Expansion | #REF!
Saddle West Expansion | #REF!
Sales Meter Station | #REF!
Sales Meter Station Expansion | #REF!
Sales Meter Station Replacement | #REF!
Transmission Loop | #REF!
West Path Delivery 2022 | #REF!
West Path Delivery 2023 | #REF!
West Path Delivery Project | #REF!

## Forecast Costs (hidden)
Applied-for Facilities | Forecast Cost ($Millions)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF! | #REF!
Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Saddle Hills Compressor Station Unit Addition
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Emerson Creek Compressor Station
#REF!
#REF!
#REF! | #REF!
#REF! | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF! | #REF!
#REF!
#REF!
#REF! | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Deep Valley)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
2022 Meter Station and Laterals Abandonment Program | 23
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Codner South Receipt Meter Station | 6.4
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Mackie Creek North Receipt Meter Station Expansion | 1.1
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Mildred Lake West Sales Meter Station | 6.6
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Yellowhead Compressor Station (AP)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Spruce Grove and Stony Plain UPU – Installation (AP)
#REF!
#REF!
#REF!