## Summary & Notes
The Facility Status Update describes the current status of facilities that were applied for, are under construction or have been placed on-stream since the 2024 Annual Plan was issued on February 03, 2025 and maintains a record of the facilities for two years prior to the current year. Periodic updates are being provided based on the level of activity occurring with respect to facilities. Facilities with (AP) after the project name refer to facilities in the ATCO Pipelines footprint.
| Summary: | 2023 | 2024 | 2025 | 2026 | 2027 | 2028+
| Total Costs by In-Service Year * | 1926.7 | 1391 | 14.6 | 697.8 | 474 | 2975
Forecast Costs There are two methodologies for forecasting costs and for NGTL projects greater than $25 million, the estimate type are identified. For a Class Estimate, the target accuracy for the various estimate types are shown in the table below. These accuracy ranges are for typical TC Energy projects with established technological complexity. It should be noted that for non-typical TC Energy projects the accuracy range could widen towards the upper limit of the AACE ranges for a class of estimate (i.e. depending on area knowledge, technological complexity, level of expertise, and certainty of facility scope). If a cost estimate for an NGTL project is based on the wider accuracy range, the estimate range will be provided in the Variance Explanation column. Forecasted costs reflect the dollar value, economic conditions, and estimation procedures at the time the estimates were completed. For a Parametic Estimate, TC Energy may also baseline cost estimates using a probabilistic assessment driven by the risks and uncertainties associated with the project. Typically, the plausible outcomes are expressed as a P-Value and range between P10-P90. The Value indicates the confidence level of a particular cost estimate and indicates the expected probability that the final cost will be equal-to or less-than the specified estimate value. For example, a 70% confidence level for an estimate value (often noted as a P70) indicates an expected 70% probability that the final result will be less than (more favorable) or equal to the P70 cost estimate.
Total Costs by In-Service Total Costs by In-Service Year are a summation of the last provided costs of all NGTL capacity capital projects with expected or realized in-service dates within a calendar year. Costs for non NGTL capacity capital projects, such as ATCO Pipelines, CIAC, decommissioning or abandonment projects, are excluded. These annual summations of costs will not match other regulatory filings with different costs bases. Variance Explanation Variance explanations are provided for all NGTL capacity capital projects with EAC costs equal to or greater than $25 million with a variance greater than 10% between the EAC and applied-for costs.
2021 NGTL System Expansion Project GPML Loop No.2 (Colt Section) in-service March 24, 2023, acheiving 100% Project capacity. GPML Loop No. 2 (Simonette River) in-service May 2024. In October 2024, Estimates at Complete were updated for all projects included in the 2021 NGTL System Expansion Project to total $3.6B. Disclaimer The information provided in this document has been prepared to the best of management’s ability. TC does not represent or warrant that the information contained herein is accurate and complete in all respects or is fit for any purpose. Any of use of the information in its current or any manipulated form is the sole responsibility of the user. TC Energy is not responsible for any changes made to downloaded copies and/or results in data compiled, assumptions, and actions resulting from those changes. NGTL can only support use of the official PDF version as posted on TC Customer Express.

## Facilities Update
Report Updates | Facility Category | Applied-for Facilities | Description | Target In-Service Date | Status | Date of Status | References * | Forecast Cost * ($Millions) | 2023 | 2024 | 2025 | 2026 | 2027 | 2028+ | Variance Explanation
| DDA | 2018 Pipelines and Associated Facilities Decommissioning Program | Pipeline Laterals Baxter Lake Calling Lake East Calling Lake South East Lat Loop Edgerton Flat Lake Lat Loop Flat Lake Lat Ext Judy Creek Sales North Lat Ext Loop Wainwright Wapiti Zama Lake Associated Facilities Edgerton Rec Judy Creek Sales Zama Lake No. 1 Rec Zama Lake No. 2 Rec Wapiti Rec PTI 360m Cross-over | Q4 2022 | Complete | 2023-03-03 | Nov 14, 2018 - TTFP Notification Dec 7, 2018 - TTFP Notification Update Dec 18, 2018 - NEB Application Filed 1 | 14.3 28 - Class 5
| DDA | 2021 Meter Station and Laterals Abandonment Program | Pipeline Laterals & Meters 12 - 151.2 km 9 Receipt 1 Delivery Stand-Alone Meters 3 Receipt 1 Delivery | Q1 2025 | Complete | 2025-04-08 | Mar 7, 2022 - TTFP Notification May 3, 2022 - CER Application Filed 22 | 13
| DDA | 2021 Meter Station and Laterals Decommisioning Program | Pipeline Laterals & Meters 5 - 120.7 km 2 Receipt 1 Delivery | Q4 2024 | Complete | 2025-04-08 | Jun 13, 2022 - TTFP Notification Aug 22, 2022 - CER Application Filed 23 | 7.1
| Pipeline | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Colt Section) | 14 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2023-03-24 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 2 Feb 19, 2020 - CER Recommendation 3 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Sept 12, 2023 - Facility Status Update (Estimate at Complete) | 73 - ROM 80 - Class 5 117 - Class 3 134 - Class 3 211 - EAC | 211 | [5 empty] | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| Pipeline | 2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Deep Valley) | 69 km NPS 48 | Apr 2021 - Apr 2022 | In-Service | 2024-05-15 | Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Jun 20, 2018 - NEB Application Filed 2 Feb 19, 2020 - CER Recommendation 3 Sep 8, 2020 - Facility Status Class Estimate Update May 7, 2021 - Revised Class Estimate Sep 17, 2024 - Facility Status Update (Estimate at Complete) | 332 - ROM 377 - Class 5 530 - Class 3 665 - Class 3 970 - EAC |  | 970 |  |  |  |  | Delayed regulatory approval impacted cost and execution plans. Multiple construction seasons with prime contractor complications and redesign of Simonette HDD.
| DDA | 2022 Meter Station and Laterals Abandonment Program | Pipeline Laterals & Meters 23 - 167.5 km 22 Receipt 1 Delivery 7 Producer Tie-ins | Q2 2025 | Approved | 2023-12-15 | Apr 6, 2023 - TTFP Facility Notification May 23, 2023 - CER Application Filed 27 | 23
| DDA | 2022 Meter Station and Laterals Decommissioning Program | Pipeline Laterals & Meters 23 - 310.34 km 2 Receipt | Q2 2025 | Approved | 2023-12-21 | Jun 19, 2023 - TTFP Notification Aug 21, 2023 - CER Application Filed30 | 18.6
| DDA | 2024 Meter Station and Laterals Abandonment Program | Pipeline Laterals & Meters 26 - 196.2 km 26 Receipt Meter Stations 1 Delivery Meter Station 5 Producer Tie-ins | Q1 2026 | Approved | 2025-04-08 | June 18, 2024 - CER Application Filed36 Apr 8, 2025 - TTFP Notification | 25.4
| DDA | 2024 Meter Station and Laterals Decommissioning Program | Pipeline Laterals & Meters 38 - 452.5 km 8 Receipt Meter Stations 2 Producer Tie-Ins | Q2 2026 | Approved | 2025-04-08 | Aug 13, 2024 - CER Application Filed37 Apr 8, 2025 - TTFP Notification | 34
Updated in-service date from Apr 2026 to Q1 2027 | Compressor Station | Berland River Compressor Station Unit and Coolers Addition | 30 MW | Q1 2027 | Under Construction | 2024-09-16 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix Sep 7, 2022 - TTFP Facilites Update Aug 1, 2023 - CER Application Filed28 Dec 21, 2023 - CER Approval29 | 166 - ROM 254 - Class 5 255 - Class 4 |  |  |  | 255
Added | Delivery Lateral | Coaldale Lateral East #2 Branch Loop (AP) | 2.2 km NPS 4 | 2025-10-01 | Applied for | 2025-06-17 | June 17, 2025 - TTFP Notification May 20, 2025 - AUC Application Filed38 | 4.2
| Receipt Meter Station | Codner South Receipt Meter Station | 10104U Ultrasonic Meter | 2025-08-01 | Under Construction | 2025-03-18 | Oct 29, 2024 - TTFP Notification | 6.4 |  |  | 6.4
| Compressor Station | Emerson Creek Compressor Station | 2-30 MW Units | 2024-04-01 | In-Service | 2024-04-01 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii June 1, 2021 - CER Application Filed 16 Dec 22, 2021- CER Approval20 July 18, 2024 - Facility Status Update (Estimate at Complete) | 257 - ROM 278 - Class 5 274 - EAC |  | 274
| Pipeline | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) | 33km NPS 48 | 2026-04-01 | Under Construction | 2024-11-12 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix Sep 7, 2022 - TTFP Facilites Update Aug 1, 2023 - CER Application Filed28 Dec 21, 2023 - CER Approval29 | 281 - ROM 342 - Class 5 323 - Class 4 |  |  |  | 323
| Pipeline | Grande Prairie Mainline Loop (Colt Section) | 20 km NPS 48 | 2028-04-01 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Dec 10, 2024 - TTFP Presentation, 2024 Annual Plan xii | 404 - P70 | [5 empty] | 404
| Pipeline | Grande Prairie Mainline Loop (Deep Valley North Section) | 14 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi | 254 - P70 | [5 empty] | 254
| Pipeline | Grande Prairie Mainline Loop (Deep Valley South Section) | 23 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi | 379 - P70 | [5 empty] | 379
| Pipeline | Grande Prairie Mainline Loop (Hornbeck Section) | 13 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi | 238 - P70 | [5 empty] | 238
| Pipeline | Grande Prairie Mainline Loop (Greenview Section) | 15 km NPS 48 | 2028-04-01 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Dec 10, 2024 - TTFP Presentation, 2024 Annual Plan xii | 205 - P70 | [5 empty] | 205
| Pipeline | Grande Prairie Mainline Loop (Karr North Section) | 16 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Dec 10, 2024 - TTFP Presentation, 2024 Annual Plan xii | 238 - P70 | [5 empty] | 238
| Pipeline | Grande Prairie Mainline Loop (Karr South Section) | 25 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Dec 10, 2024 - TTFP Presentation, 2024 Annual Plan xii | 332 - P70 | [5 empty] | 332
| Pipeline | Grande Prairie Mainline Loop (McLeod North Section) | 13 km NPS 48 | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi | 211 - P70 | [5 empty] | 211
| Pipeline | Grande Prairie Mainline Loop (McLeod South Section) | 21 km NPS 48 | 2027-04-01 | Proposed | 2025-02-03 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Dec 10, 2024 - TTFP Presentation, 2024 Annual Plan xii | 321 - P70 |  |  |  |  | 321
| Pipeline | Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Groundbirch Mainline Loop (Saturn Section) | 24 km NPS 42 | 2023-12-01 | In-Service | 2023-12-01 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Nov 5, 2020 - CER Application Filed 12 May, 13, 2021 - CER Approval 15 May 1, 2024 - Facility Status Update (Estimate at Complete) | 143 - ROM 140 - Class 5 144 - EAC | 144
| Compressor Station | Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Saddle Hills Compressor Station Unit Addition | 30 MW | 2024-04-01 | In-Service | 2024-04-19 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Nov 5, 2020 - CER Application Filed 12 May, 13, 2021 - CER Approval 15 July 18, 2024 - Facility Status Update (Estimate at Complete) | 159 - ROM 151 - Class 5 123 - EAC |  | 123
| Pipeline | Groundbirch Mainline Loop (Sunrise Section) | 24 km NPS 42 | 2023-04-01 | In-Service | 2023-04-16 | Jul 21, 2017 - TTFP Facility Update Dec 4, 2017 - TTFP Presentation, 2017 Annual Plan v Oct 3, 2018 - TTFP Facility Update Apr 29, 2019 - NEB Application Filed 4 Sep 12, 2023 - Facility Status Update (Estimate at Complete) | 107 - ROM 155 - ROM 135 - ROM 140 - Class 4 176 - EAC | 176 | [5 empty] | Delayed regulatory approval impacted cost and execution plans. Elevated prime contractor costs due to unfavorable market conditions.
| Compressor Station | Hidden Lake & Hidden Lake North Station Coolers | Coolers | 2023-04-01 | In-Service | 2023-03-30 | Dec 7, 2020 - TTFP Notification Jun 22, 2021 - CER Application Filed 17 Dec 10, 2021 - CER Approval 19 Sept 12, 2023 - Facility Status Update (Estimate at Complete) | 45 - ROM 47 - Class 4 53 - EAC | 53 | [5 empty] | Elevated prime contractor costs.
| Pipeline | Inland Looping (AP) | 9km NPS 20 | 2025-11-01 | In-Service | 2025-02-14 | Dec 6, 2021 - TTFP Presentation, 2021 Annual Plan ix June 21, 2023 - Facility Status Update | 40 - ROM
| Delivery Meter Station | Iosegun Sales Meter Station | 440T Turbine Meter | 2024-09-01 | In-Service | 2024-08-29 | Sep 11, 2023 - CER Application Filed31 Feb 15, 2024 - TTFP Notification | 3.3 |  | 3.3
| Tie-in | Leismer Ethane Extraction Plant Tie-in | NPS 30 Connection, Valves, Tees | 2023-04-01 | In-Service | 2023-05-01 | Apr 06, 2022 - TTFP Notification Apr 26, 2022 - CER Application Filed21 | 3.2 | 3.2
| Pipeline | Leming Loop (Field Lake Section) | 17 km NPS 20 | Apr 2026 | Approved | 2024-09-20 | Dec 13, 2022 - TTFP Presentation, 2022 Annual Plan x May 9, 2023 - TTFP Facility Update Presentation Mar 01, 2024 - CER Application Filed32 Sep 20, 2024 - CER Approval34 | 270 - ROM 107 - Class 5 105 - Class 4 |  |  |  | 105
| Pipeline | Leming Loop (Sand Section) | 18 km NPS 20 | 2027-04-01 | Applied for | Jan 10, 2025 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Jan 10, 2025 - CER Application Filed35 | 149 - ROM 153 - Class 4 |  |  |  |  | 153
| Other | Lethbridge Urban Pipeline Upgrade (AP) | 10.8 km NPS 8 2.4 km NPS 6 Control Station 3 Delivery Stations | Q3 2024 | In-Service | 2024-01-11 | Aug 7, 2018 - TTFP Notification Jul 30, 2018 - GRA Application Filed 5 Jun 16, 2020 - GRA Application Filed 10 Mar 1, 2021 - GRA Application Approved 13 | 40
| Receipt Meter Station | Mackie Creek North Receipt Meter Station Expansion | 682U Ultrasonic Meter | 2024-01-01 | In-Service | 2023-12-15 | Jun 20, 2023, - TTFP Notification | 1.1 |  | 1.1
| Receipt Meter Station | Mackie Creek North Receipt Meter Station Expansion - Phase 2 | 682 Orifice Meter | 2025-11-01 | Proposed | 2024-11-26 | Dec 3, 2024 - TTFP Notification | 3.9 |  |  | 3.9
| Delivery Meter Station | Mildred Lake West Sales Meter Station | 2-1010U Ultrasonic Meter | 2024-04-01 | In-Service | 2024-04-01 | Nov 30, 2022 - TTFP Notification Mar 13, 2023 - CER Application Filed 26 | 6.6 |  | 6.6
| Compressor Station | North Corridor Expansion Project: Hidden Lake North Compressor Station Unit Addition | 30 MW | 2023-04-01 | In-Service | 2023-05-07 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 6 May 5, 2021 - CER Approval 14 Sept 12, 2023 - Facility Status Update (Estimate at Complete) | 138 - ROM 138 - Class 5 195 - EAC | 195 | [5 empty] | Elevated prime contractor costs.
| Pipeline | North Corridor Expansion Project: North Central Corridor Loop (North Star Section 2) | 24 km NPS 48 | 2023-04-01 | In-Service | 2023-01-19 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 6 May 5, 2021 - CER Approval 14 Apr 11, 2023 - Facility Status Update (Estimate at Complete) | 155 - ROM 155 - Class 5 198 - EAC | 198 | [5 empty] | Issuance of a Stop Work Order by the CER, resulting in unplanned standby and delay with commencement of work.
| Pipeline | North Corridor Expansion Project: North Central Corridor Loop (Red Earth Section 3) | 32 km NPS 48 | 2023-04-01 | In-Service | 2023-04-11 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 6 May 5, 2021 - CER Approval 14 July 11, 2023 - Facility Status Update (Estimate at Complete) | 205 - ROM 205 - Class 5 289 - EAC | 289 | [5 empty] | Elevated prime contractor costs due to unfavorable market conditions. Issuance of a Stop Work Order by the CER, resulting in unplanned standby and delay with commencement of work.
| Pipeline | North Corridor Expansion Project: Northwest Mainline Loop No.2 (Bear Canyon North Extension Section) | 25 km NPS 36 | 2023-04-01 | In-Service | 2023-03-23 | Nov 14, 2018 - TTFP Presentation, 2018 Annual Plan vi Apr 4, 2019 - NEB Application Filed 6 May 5, 2021 - CER Approval 14 Sept 12, 2023 - Facility Status Update (Estimate at Complete) | 134 - ROM 134 - Class 5 132 - EAC | 132 | [5 empty] | Favourable prime contractor costs due to competitive market conditions for smaller diameter pipelines.
| Compressor Station | Peers Compressor Station Unit Addition (AP) | 5-15 MW | 2027 | Proposed | 2023-05-09 | May 9, 2023 - TTFP Facility Update Presentation Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Aug 22, 2024 - TTFP Update | 103 - ROM 138 - Class 5 272 - Class 4
| Receipt Meter Station | Pipestone Creek Meter Station Expansion | 662-U Ultrasonic | 2026-04-01 | Proposed | 2025-04-08 | Apr 8, 2025 - TTFP Notification | 3.9 |  |  |  | 3.9
| Receipt Meter Station | Saturn No. 3 Receipt Meter Station | 1010-U Ultrasonic Meter | 2025-11-01 | Proposed | 2025-02-07 | Jan 17, 2025 - TTFP Notification | 4.3 |  |  | 4.3
| Delivery Meter Station | Smoky River South Sales Meter Station | NPS 3 Positive Displacement Meter | 2022-09-01 | In-Service | 2023-07-05 | May 20, 2021 - TTFP Notification Aug 26, 2021 - NEB Application Filed 18 | 4.5 | 4.5
| Other | Spruce Grove and Stony Plain UPU – Installation (AP) | 5.4 km NPS 6 3 Delivery Stations | Q1 2024 | In-Service | 2024-03-22 | Jun 16, 2020 - GRA Application Filed 8 Mar 1,2021 - GRA Application Approved 13 | 13.2 11.5
| Receipt Meter Station | Tawadina Creek #2 Meter Station | 860-U Ultrasonic | 2026-03-01 | Proposed | 2025-04-08 | Apr 8, 2025 - TTFP Notification | 4.8 |  |  |  | 4.8
| Other | Urban Pipeline Replacement Project: Edmonton UPR – NE Connector (AP) | Control Station | 2025 | Approved |  | Oct 30, 2014 - TTFP Presentation Dec 4, 2018 – AUC Project Update Filed 7 Jun 16, 2020 - AUC Project Update Filed 9 | 11
| Compressor Station | Vetchland Compressor Station Unit and Cooler Additions | 30 MW | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi | 352 - P70 | [5 empty] | 352
| Pipeline | West Path Delivery 2023 WAML Loop No. 2 (Longview) | 9 km NPS 48 | 2023-11-01 | In-Service | 2023-10-19 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 11 Dec 1, 2022 - CER Approval 24 Feb 15, 2024 - Facility Status Update (Estimate at Complete) | 65 - ROM 75 - Class 5 108 - EAC | 108 | [5 empty] | Elevated costs due to construction scope of work (material cost increases, design changes and rework, and third party clearing).
| Pipeline | West Path Delivery 2023 WAML Loop No. 2 (Lundbreck) | 7 km NPS 48 | 2023-11-01 | In-Service | 2023-10-27 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 11 Dec 1, 2022 - CER Approval 24 Feb 15, 2024 - Facility Status Update (Estimate at Complete) | 83 - ROM 72 - Class 5 153 - EAC | 153 | [5 empty] | Elevated costs due to construction scope of work (difficult terrain, design changes and rework, and third party clearing). Additional contractor costs due to unfavorable market conditions.
| Pipeline | West Path Delivery 2023 WAML Loop No. 2 (Turner Valley) | 24 km NPS 48 | 2023-11-01 | In-Service | 2023-11-01 | Nov 12, 2019 - TTFP Presentation, 2019 Annual Plan vii Oct 14, 2020 - Appendix 2 Class Estimate Update Oct 22, 2020 - CER Application Filed 11 Dec 1, 2022 - CER Approval 24 Feb 15, 2024 - Facility Status Update (Estimate at Complete) | 209 - ROM 209 - Class 5 260 - EAC | 260 | [5 empty] | Elevated costs due to material cost increases, design changes and rework, and third party clearing.
| Tie-in | Whiskey Jack Ethane Extraction Plant Tie-In | NPS 36 Connection, Valves, Tees | 2026-04-01 | Proposed | 2025-02-12 | Feb 12, 2025 - TTFP Notification | 6.1 |  |  |  | 6.1
| Receipt Meter Station | Wilkin Lake Receipt Meter Station | 884U Ultrasonic Meter | 2024-07-01 | In-Service | 2024-08-28 | Oct 16, 2023 - CER Application Dec 14, 2023 - CER Approval33 | 5.9 |  | 5.9
| Delivery Meter Station | Willow Valley Interconnect Project | 2-1610U Ultrasonic Meter | 2024-04-24 | In-Service | 2024-04-01 | Jan 5, 2023 - TTFP Notification Jan 18, 2023 - CER Application Filed 25 | 7.1 |  | 7.1
| Compressor Station | Wolf Lake Compressor Station Unit and Cooler Additions | 30 MW | 2028-2030 | Proposed* Requirement and in-service timing of facility contingent upon the finalization of commercial arrangements | 2024-03-12 | Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi | 362 - P70 | [5 empty] | 362
| Pipeline | Yellowhead Mainline (AP) | 226 km NPS 36 Control Stations | 2027 | Proposed | 2023-05-09 | May 9, 2023 - TTFP Facility Update Presentation Feb 22, 2024 - TTFP Presentation, 2023 Annual Plan xi Aug 22, 2024 - TTFP Update | 1024 - ROM 1,815 - Class 5 2,541 - Class 4

## References
References
Annual Plans
i. | NGTL 2013 Annual Plan
ii. | NGTL 2014 Annual Plan
iii. | NGTL 2015 Annual Plan
iv. | NGTL 2016 Annual Plan
v. | NGTL 2017 Annual Plan
vi. | NGTL 2018 Annual Plan
vii. | NGTL 2019 Annual Plan
viii. | NGTL 2020 Annual Plan
ix. | NGTL 2021 Annual Plan
x. | NGTL 2022 Annual Plan
xi. | NGTL 2023 Annual Plan
xii. | NGTL 2024 Annual Plan
1 | 2018 Pipeline Decommissioning Program
2 | 2021 NGTL System Expansion Project
3 | Canada Energy Regulator Report for the 2021 NGTL System Expansion Project
4 | Application for the Construction of Groundbirch Mainline Loop (Sunrise Section)
5 | GRA Application Filed
6 | Application for the Construction of North Corridor Expansion Project
7 | Dec 4, 2018 – AUC Project Update Filed
8 | GRA Application Filed
9 | (GRA) AUC Project Update Filed
10 | GRA Application Filed
11 | NGTL West Path Delivery 2023 CER
12 | NGTL GBML Loop (Saturn Section) & Saddle Hills CS C4 Unit Addition
13 | March 1, 2021 - GRA Application Approved
14 | North Corridor Expansion - GIC Approval
15 | GBML (Saturn) and Saddle Hills UA Application
16 | Emerson Creek Compressor Station
17 | Hidden Lake and Hidden Lake North Cooler Additions Application
18 | Smoky River South Sales Meter Station Application
19 | Hidden Lake and Hidden Lake North Cooler Additions CER Approval
20 | Emerson Creek Compressor Station Approval
21 | Leismer Ethane Extraction Plant Tie-in
22 | 2021 Meter Station and Laterals Abandonment Program
23 | 2021 Meter Station and Laterals Decommissioning Program
24 | West Path Delivery 2023 Project CER Approval
25 | Willow Valley Interconnect Project
26 | Mildred Lake West Sales Meter Station Application
27 | 2022 Meter Stations and Laterals Abandonment Program
28 | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) and Berland River CS C3 Unit Addition Application
29 | Grande Prairie Mainline Loop No. 4 (Valhalla North Section) and Berland River CS C3 Unit Addition Approval
30 | 2022 Meter Stations and Laterals Decommissioning Program
31 | Iosegun Sales Meter Station CER Project Notification
32 | Leming Lake Sales Lateral Loop (Field Lake Section) Application
33 | Wilkin Lake Receipt Meter Station Approval
34 | Leming Lake Sales Lateral Loop (Field Lake Section) Approval
35 | Leming Lake Sales Lateral Loop (Sand Section) Application
36 | 2024 Meter Station and Laterals Abandonment Program
37 | 2024 Meter Station and Laterals Decommissioning Program
38 | ATCO Coaldale Potato - AUC Facility Application

## Facility Type Analysis (hidden)
Facility Type | Frequency
Abandonment | #REF!
Clearwater West Expansion | #REF!
Cogen Delivery Station | #REF!
Compressor Station | #REF!
Compressor Station Coolers | #REF!
Compressor Station Decomissioning | #REF!
Compressor Station Modifications | #REF!
Compressor Station Unit Addition | #REF!
Compressor Station Unit Addition & Coolers | #REF!
Connection Piping | #REF!
Control Valve Addition | #REF!
Crossover | #REF!
Delivery Meter Station | #REF!
Edson Mainline Expansion | #REF!
Expansion & Lateral Loop | #REF!
Extraction Connections | #REF!
Forestburg | #REF!
Grande Prairie Mainline Loop | #REF!
Groundbirch Mainline Loop | #REF!
Lateral Expansion | #REF!
Lateral Loop | #REF!
Meter Station & Lateral Abandonment | #REF!
NGTL System Expansion | #REF!
North Central Corridor Loop | #REF!
North Corridor Expansion | #REF!
North Montney Project | #REF!
North Path Delivery | #REF!
Northwest Mainline Loop | #REF!
Peace River Mainline Abandonment | #REF!
Pembina-Keephills Transmission Project | #REF!
Pipeline & Associated Decommissioning | #REF!
Pipeline Acquisition | #REF!
Pipeline Asset Purchase | #REF!
Pipeline Decommissioning | #REF!
Pipeline Replacement | #REF!
Pipeline Upgrade | #REF!
Receipt Meter Station | #REF!
Receipt Meter Station Expansion | #REF!
Saddle West Expansion | #REF!
Sales Meter Station | #REF!
Sales Meter Station Expansion | #REF!
Sales Meter Station Replacement | #REF!
Transmission Loop | #REF!
West Path Delivery 2022 | #REF!
West Path Delivery 2023 | #REF!
West Path Delivery Project | #REF!

## Forecast Costs (hidden)
Applied-for Facilities | Forecast Cost ($Millions)
Groundbirch Mainline Loop (Sunrise Section)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF! | #REF!
Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Saddle Hills Compressor Station Unit Addition
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Emerson Creek Compressor Station
#REF!
#REF!
West Path Delivery 2023 WAML Loop No. 2 (Longview) | 65 - ROM 75 - Class 5 108 - EAC
#REF! | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Groundbirch Mainline (Saturn Section) & Saddle Hills Unit Addition: Groundbirch Mainline Loop (Saturn Section)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF! | #REF!
#REF!
#REF!
#REF! | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
2018 Pipelines and Associated Facilities Decommissioning Program
#REF!
#REF!
#REF!
#REF!
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Colt Section)
2021 NGTL System Expansion Project: Grande Prairie Mainline Loop No.2 (Deep Valley)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
2022 Meter Station and Laterals Abandonment Program | 23
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Codner South Receipt Meter Station | 6.4
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Grande Prairie Mainline Loop (McLeod North Section)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Mackie Creek North Receipt Meter Station Expansion | 1.1
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Mildred Lake West Sales Meter Station | 6.6
North Corridor Expansion Project: Hidden Lake North Compressor Station Unit Addition
North Corridor Expansion Project: North Central Corridor Loop (North Star Section 2)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Peers Compressor Station Unit Addition (AP)
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Smoky River South Sales Meter Station
#REF!
#REF!
#REF!
Spruce Grove and Stony Plain UPU – Installation (AP)
#REF!
#REF!
#REF!